## COVER
FINAL TOP-LAYER SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP) 2018/19

## INTRODUCTION
INTRODUCTION | In terms of the Local Government: Municipal Finance Management Act, Act 56 of 2003, Section 69(3)(a) states that the Accounting Officer must no later than 14 days after the approval of an annual budget submit to the mayor a draft service delivery and budget implementation plan for the budget year. And further section 53 (1) (c) (ii) states that a Mayor of the Municipality must approve the service delivery and budget implementation plan of the municipality within 28 days after the approval of the final budget. MFMA Circular 13 of 2005 gives effect to the provisions of Section 53 (1) (c)(ii) of the Local Government: Municipal Finance Management Act. The Circular states that the Service Delivery and Budget Implementation Plan give effect to the Integrated Development Plan and the Budget of the Municipality. It provides a vital link and alignment between the Integrated Development and the Budget of the Municipality.
LEGISLATION FRAMEWORK | Section 1 of the Local Government: Municipal Finance Management Act, Act 56 of 2003 defines the Service Delivery and Budget Implementation Plan as: “a detailed plan approved by the mayor of a municipality in terms of section 53 (1) (c) (ii) for implementing the municipality’s delivery of services and the execution of its annual budget and which must include (as part of the top-layer) the following: (a) Projections for each month of – (i) Revenue to be collected by source; and (ii) Operational and capital expenditure, by vote (b) Service delivery targets and performance indicators for each quarter” Section 69 (3) (a) of the MFMA requires the accounting officer to submit a draft to the mayor no later than 14 days after the approval of the budget and drafts of the performance agreements as required in terms of Section 57 (1) (b) of the Municipal Systems Act. Section 53 (1) (c) requires that a municipality’s Service Delivery and Budget Implementation Plan be approved by the Mayor within 28 days after the approval of the budget. The mayor must ensure that the revenue and expenditure projection for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public with 14 days after approval. The SDBIP may be revised at lower layers of the plan by the municipal manager and directors taking into consideration each months or quarterly actual performance. The top-layer SDBIP and its targets cannot be revised without notifying council, any changes to the top-layer SDBIP targets, performance indicators must be approved by council following the adjustment budget in terms of section 54 (1) (c) of the MFMA. The council approval is meant to avoid a situation where service delivery targets may be revised downwards in the event of poor performance.
SDBIP METHODOLOGY | The IDP objectives need to be quantified and translated into key performance indicators. The budget is then aligned to the objectives, projects and activities to enable the SDBIP to serve as a monitoring tool for service delivery. The SDBIP is a layered plan that comprises the top layer as well as the lower layer SDBIP. The top layer deals with consolidated service delivery targets and time frames for top management, whereas the lower layer consists of detailed outputs that are broken down into smaller outputs and then linked and assigned to middle and lower managers. The following are the minimum required components of a top-layer SDBIP: (a) Monthly projections of revenue to be collected for each source (b) Monthly projections of expenditure (operating and capital) and revenue for each vote (c) Quarterly projections of service delivery targets and performance indicators for each vote (d) Ward information for expenditure and service delivery (e) Detailed capital works plan broken down by ward over three years The diagram below shows the process for approving the SDBIP including how the departmental SDBIPs roll up into the draft SDBIP:
POLOKWANE MUNICIPALITY STRATEGIC INTENT AND OBJECTIVES | Vision “The Ultimate in Innovation and Sustainable Development” Mission “Provide cost effective services which promote sustainable livelihood through socio economic development and good governance” Value Statement "Sustainable Development through Responsive Innovation" Values • Sustainable Development • Innovation • Responsiveness
POLOKWANE MUNICIPALITY SERVICE DELIVERY PRIORITIES | • Provision of basic services, which include electricity provision, water and sanitation and refuse removal • Strengthen the local economic development structures and expansion of expanded public works programme • Upgrading of informal settlements and promotion of sustainable human settlements • Overhaul of ageing service delivery infrastructure and maintenance of municipal facilities • Improving transport, roads and bridges • Improving sports and recreational facilities and promotion of social cohesion • Development of municipal capacity to manage disaster risk and protection of environment • Ensure long-term planning capacity, monitoring and evaluation • Promotion of sound financial management to ensure financial sustainability • Promotion of good governance and the participation of local communities in the municipal affairs
POLOKWANE MUNICIPALITY’S IDP STRATEGIC OBJECTIVES | • To ensure efficiency and effectiveness of Municipal administration • To ensure the provision of basic and environmental services in a sustainable way to our communities • To ensure social protection and education outcomes • Promotion of economic growth ,job creation and Sustainable human settlement • To ensure community confidence in the system of local government • To enhance Financial Viability and Financial Management
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN REPORTING CYCLE | The Service Delivery and Budget Implementation Plan is a management tool that will be used by the Executive Management Committee to monitor institutional performance, departmental performance, SBU performance and individual performance of employees. The Service Delivery and Budget Implementation Plan will be used by Mayoral Committee and Council to play oversight on the performance of the municipality and will be used as the basis of reporting municipal performance to the community of Polokwane and all interested stakeholders. It will serve as a early warning system for poor performance and will allow for timeous intervention to correct poor performance. The reporting cycle of this Service Delivery and Budget Implementation Plan is aligned to the Council approved PMS Framework and the PMS Policy. Reporting will be done:

## FINANCIAL PROJECTIONS
LIM354 Polokwane - Supporting Table SA25 Consolidated budgeted monthly revenue and expenditure
Description | Ref | Budget Year 2018/19 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2018/19 | Budget Year +1 2019/20 | Budget Year +2 2020/21
Revenue By Source
Property rates |  | 31900 | 41197 | 54444 | 42718 | 36977 | 44304 | 33316 | 25832 | 41852 | 40586 | 26141 | 42217 | 461484 | 498403 | 538275
Service charges - electricity revenue |  | 72922 | 94175 | 124456 | 97652 | 84527 | 101278 | 76160 | 59051 | 95672 | 92779 | 59758 | 96514 | 1054944 | 1155164 | 1270681
Service charges - water revenue |  | 17174 | 22179 | 29311 | 22998 | 19907 | 23852 | 17937 | 13907 | 22532 | 21851 | 14074 | 22728 | 248450 | 273919 | 301309
Service charges - sanitation revenue |  | 7088 | 9153 | 12096 | 9491 | 8215 | 9843 | 7402 | 5739 | 9299 | 9017 | 5808 | 9377 | 102528 | 109193 | 116836
Service charges - refuse revenue |  | 7808 | 10083 | 13325 | 10456 | 9050 | 10844 | 8154 | 6323 | 10244 | 9934 | 6398 | 10329 | 112948 | 120289 | 128709
Service charges - other |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | –
Rental of facilities and equipment |  | 2579 | 3330 | 4401 | 3453 | 2989 | 3581 | 2693 | 2088 | 3383 | 3281 | 2113 | 3406 | 37297 | 39382 | 41584
Interest earned - external investments |  | 3269 | 4221 | 5578 | 4377 | 3789 | 4540 | 3414 | 2647 | 4288 | 4159 | 2679 | 4320 | 47281 | 49882 | 52625
Interest earned - outstanding debtors |  | 5530 | 7142 | 9438 | 7406 | 6410 | 7681 | 5776 | 4478 | 7256 | 7036 | 4532 | 7315 | 80000 | 84400 | 89042
Dividends received |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | –
Fines, penalties and forfeits |  | 1106 | 1429 | 1888 | 1482 | 1282 | 1537 | 1156 | 896 | 1452 | 1408 | 907 | 1457 | 16000 | 16959 | 17979
Licences and permits |  | 1030 | 1330 | 1757 | 1379 | 1194 | 1430 | 1075 | 834 | 1351 | 1310 | 844 | 1356 | 14890 | 15782 | 16728
Agency services |  | 1729 | 2232 | 2950 | 2315 | 2004 | 2401 | 1805 | 1400 | 2268 | 2199 | 1417 | 2280 | 25000 | 26500 | 28090
Transfers and subsidies |  | 69731 | 90054 | 119010 | 93379 | 80828 | 96846 | 72827 | 56467 | 91485 | 88719 | 57143 | 92291 | 1008780 | 1053240 | 1126485
Other revenue |  | 29375 | 37936 | 50134 | 39336 | 34049 | 40797 | 30679 | 23787 | 38539 | 37374 | 24072 | 38874 | 424952 | 442169 | 420119
Gains on disposal of PPE | [12 empty] | – | – | – | –
Total Revenue (excluding capital transfers and contributions) |  | 251241 | 324461 | 428788 | 336442 | 291221 | 348934 | 262394 | 203449 | 329621 | 319653 | 205886 | 332464 | 3634554 | 3885282 | 4148462
Expenditure By Type
Employee related costs |  | 66723 | 69714 | 73476 | 61707 | 60635 | 73736 | 66175 | 62564 | 65201 | 65316 | 66308 | 85868 | 817423 | 869703 | 917117
Remuneration of councillors |  | 3308 | 3456 | 3643 | 3059 | 3006 | 3655 | 3281 | 3102 | 3232 | 3238 | 3287 | 4251 | 40518 | 43149 | 45955
Debt impairment |  | 19183 | 20042 | 21124 | 17740 | 17432 | 21199 | 19025 | 17987 | 18745 | 18778 | 19063 | 24682 | 235000 | 249100 | 300000
Depreciation & asset impairment |  | 15509 | 16205 | 17079 | 14343 | 14094 | 17139 | 15382 | 14543 | 15156 | 15182 | 15413 | 19955 | 190000 | 237000 | 255000
Finance charges |  | 5714 | 5970 | 6293 | 5285 | 5193 | 6315 | 5667 | 5358 | 5584 | 5594 | 5679 | 44848 | 107500 | 111445 | 105000
Bulk purchases |  | 73912 | 77225 | 81393 | 68355 | 67168 | 81681 | 73306 | 69305 | 72226 | 72353 | 73452 | 95121 | 905497 | 970426 | 1028653
Other materials |  | 3075 | 3213 | 3386 | 2844 | 2794 | 3398 | 3050 | 2883 | 3005 | 3010 | 3056 | 3952 | 37666 | 60827 | 64159
Contracted services |  | 65001 | 67915 | 71580 | 60114 | 59070 | 71833 | 64467 | 60949 | 63518 | 63630 | 64596 | 83652 | 796325 | 764936 | 786967
Transfers and subsidies |  | 939 | 981 | 1034 | 869 | 854 | 1038 | 931 | 881 | 918 | 919 | 933 | 1203 | 11500 | 11500 | 11500
Other expenditure |  | 16918 | 17677 | 18630 | 15646 | 15375 | 18696 | 16779 | 15864 | 16532 | 16561 | 16813 | 21769 | 207260 | 235345 | 247889
Loss on disposal of PPE | [12 empty] | – | – | – | –
Total Expenditure |  | 270282 | 282398 | 297638 | 249962 | 245621 | 298690 | 268063 | 253436 | 264117 | 264581 | 268600 | 385301 | 3348689 | 3553431 | 3762240
Surplus/(Deficit) |  | -19041 | 42063 | 131150 | 86480 | 45600 | 50244 | -5669 | -49987 | 65504 | 55072 | -62714 | -52837 | 285865 | 331851 | 386222
Transfers and subsidies - capital (monetary allocations) (National / Provincial and District) |  | 55193 | 71279 | 94198 | 73911 | 63977 | 76655 | 57644 | 44694 | 72412 | 70223 | 45230 | 73049 | 798465 | 1032747 | 1270796
Transfers and subsidies - capital (monetary allocations) (National / Provincial Departmental Agencies, Households, Non-profit Institutions, Private Enterprises, Public Corporatons, Higher Educational Institutions) |  | 996 | 1286 | 1699 | 1333 | 1154 | 1383 | 1040 | 807 | 1306 | 1267 | 816 | 1313 | 14400 | – | –
Transfers and subsidies - capital (in-kind - all) | [12 empty] | – | – | – | –
Surplus/(Deficit) after capital transfers & contributions |  | 37148 | 114628 | 227047 | 161724 | 110731 | 128282 | 53015 | -4486 | 139222 | 126562 | -16668 | 21525 | 1098730 | 1364598 | 1657018
Taxation | [12 empty] | – | – | – | –
Attributable to minorities | [12 empty] | – | – | – | –
Share of surplus/ (deficit) of associate | [12 empty] | – | – | – | –
Surplus/(Deficit) | 1 | 37148 | 114628 | 227047 | 161724 | 110731 | 128282 | 53015 | -4486 | 139222 | 126562 | -16668 | 21525 | 1098730 | 1364598 | 1657018
References
1. Surplus (Deficit) must reconcile with Budgeted Financial Performance
check | [13 empty] | - | - | -
LIM354 Polokwane - Supporting Table SA26 Consolidated budgeted monthly revenue and expenditure (municipal vote)
Description | Ref | Budget Year 2018/19 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2018/19 | Budget Year +1 2019/20 | Budget Year +2 2020/21
Revenue by Vote
Vote 1 - COUNCIL | [12 empty] | – | – | – | –
Vote 2 - Office of the Municipal Manger | [12 empty] | – | – | – | –
Vote 3 - Strategic Planning Monitoring and Evaluation | [12 empty] | – | – | – | –
Vote 4 - Engineering Services |  | 105286 | 135971 | 179693 | 140992 | 122042 | 146227 | 109961 | 85258 | 138133 | 133957 | 86280 | 139352 | 1523152 | 1651620 | 1813480
Vote 5 - Community Services |  | 12728 | 16437 | 21723 | 17044 | 14753 | 17677 | 13293 | 10307 | 16699 | 16194 | 10430 | 16841 | 184126 | 195736 | 208682
Vote 6 - Community Development |  | 798 | 1030 | 1361 | 1068 | 925 | 1108 | 833 | 646 | 1046 | 1015 | 654 | 1049 | 11533 | 12191 | 12889
Vote 7 - Corporate and Shared Services |  | 369 | 477 | 630 | 494 | 428 | 513 | 386 | 299 | 484 | 470 | 303 | 481 | 5334 | 5654 | 5994
Vote 8 - Planning and Economic Development |  | 4065 | 5250 | 6937 | 5443 | 4712 | 5646 | 4245 | 3292 | 5333 | 5172 | 3331 | 5375 | 58801 | 62112 | 65714
Vote 9 - Budget and Treasury |  | 184179 | 237856 | 314339 | 246638 | 213489 | 255796 | 192355 | 149144 | 241637 | 234332 | 150930 | 243778 | 2664473 | 2990715 | 3312497
Vote 10 - Transport Operations | [12 empty] | – | – | – | –
Vote 11 - [NAME OF VOTE 11] | [12 empty] | – | – | – | –
Vote 12 - [NAME OF VOTE 12] | [12 empty] | – | – | – | –
Vote 13 - [NAME OF VOTE 13] | [12 empty] | – | – | – | –
Vote 14 - [NAME OF VOTE 14] | [12 empty] | – | – | – | –
Vote 15 - [NAME OF VOTE 15] | [12 empty] | – | – | – | –
Total Revenue by Vote |  | 307425 | 397021 | 524683 | 411679 | 356349 | 426967 | 321073 | 248946 | 403332 | 391140 | 251928 | 406876 | 4447419 | 4918028 | 5419256
Expenditure by Vote to be appropriated
Vote 1 - COUNCIL |  | 27624 | 28862 | 30420 | 25547 | 25104 | 30527 | 27397 | 25902 | 26994 | 27042 | 27452 | 35548 | 338419 | 361417 | 413747
Vote 2 - Office of the Municipal Manger |  | 3974 | 4152 | 4376 | 3675 | 3611 | 4391 | 3941 | 3726 | 3883 | 3890 | 3949 | 5107 | 48675 | 33879 | 35961
Vote 3 - Strategic Planning Monitoring and Evaluation |  | 5916 | 6181 | 6514 | 5471 | 5376 | 6537 | 5867 | 5547 | 5781 | 5791 | 5879 | 7605 | 72465 | 39740 | 44194
Vote 4 - Engineering Services |  | 116810 | 122046 | 128637 | 108026 | 106152 | 129088 | 115850 | 109531 | 114142 | 114346 | 116084 | 187891 | 1468603 | 1585843 | 1661917
Vote 5 - Community Services |  | 35637 | 37235 | 39244 | 32958 | 32386 | 39383 | 35345 | 33416 | 34825 | 34886 | 35416 | 45859 | 436590 | 458006 | 489658
Vote 6 - Community Development |  | 15227 | 15910 | 16768 | 14082 | 13838 | 16828 | 15102 | 14278 | 14880 | 14906 | 15132 | 19593 | 186544 | 204505 | 216667
Vote 7 - Corporate and Shared Services |  | 17754 | 18550 | 19551 | 16419 | 16134 | 19620 | 17608 | 16647 | 17349 | 17380 | 17643 | 22844 | 217499 | 238456 | 252889
Vote 8 - Planning and Economic Development |  | 5954 | 6221 | 6557 | 5507 | 5411 | 6580 | 5906 | 5583 | 5819 | 5829 | 5917 | 7658 | 72942 | 74046 | 78494
Vote 9 - Budget and Treasury |  | 36711 | 38357 | 40427 | 33951 | 33362 | 40570 | 36410 | 34423 | 35874 | 35937 | 36483 | 47243 | 449748 | 514159 | 527646
Vote 10 - Transport Operations |  | 4670 | 4879 | 5142 | 4319 | 4244 | 5161 | 4632 | 4379 | 4563 | 4571 | 4641 | 6004 | 57205 | 43379 | 41065
Vote 11 - [NAME OF VOTE 11] | [12 empty] | – | – | – | –
Vote 12 - [NAME OF VOTE 12] | [12 empty] | – | – | – | –
Vote 13 - [NAME OF VOTE 13] | [12 empty] | – | – | – | –
Vote 14 - [NAME OF VOTE 14] | [12 empty] | – | – | – | –
Vote 15 - [NAME OF VOTE 15] | [12 empty] | – | – | – | –
Total Expenditure by Vote |  | 270277 | 282393 | 297636 | 249955 | 245618 | 298685 | 268058 | 253432 | 264110 | 264578 | 268596 | 385351 | 3348689 | 3553430 | 3762238
Surplus/(Deficit) before assoc. |  | 37148 | 114628 | 227047 | 161724 | 110731 | 128282 | 53015 | -4486 | 139222 | 126562 | -16668 | 21525 | 1098730 | 1364598 | 1657018
Taxation | [12 empty] | – | – | – | –
Attributable to minorities | [12 empty] | – | – | – | –
Share of surplus/ (deficit) of associate | [12 empty] | – | – | – | –
Surplus/(Deficit) | 1 | 37148 | 114628 | 227047 | 161724 | 110731 | 128282 | 53015 | -4486 | 139222 | 126562 | -16668 | 21525 | 1098730 | 1364598 | 1657018
References
1. Surplus (Deficit) must reconcile with Budgeted Financial Performance
check | [13 empty] | - | - | -

## CAPITAL WORKS PLAN
MULTI YEAR BUDGET | Funding |  | 2018/19 | 2019/20 | 2020/21
Description
Fleet Management |  |  |  | 0 | 0
Clusters - SPME
Thusong Service Centre (TSC) -Mankweng | CRR | R | 1000000 | 4000000 | 5000000
Mobile service sites at Molepo Chuene Maja Cluster (Rampheri Village) | CRR | N | 2100000 | 0 | 1000000
Upgrading of Mohlonong centre (Aganang cluster) | CRR | U | 0 | 0 | 2500000
Renovation of existing Cluster offices in Moletjie, Sebayeng, Molepo/ Chuene /Maja Clusters | CRR | R |  | 1800000 | 1900000
Cluster offices Construction at Seshego | CRR | N | 0 | 2000000 | 3000000
Upgrading of existing Cluster offices in Moletjie ,Sebayeng & Molepo/ Chuene/ Maja clusters | CRR | U | 0 | 1500000 | 1600000
Construction of mobile service sites (Moletjie & Mankweng) | CRR | N | 0 | 7000000 | 7500000
Construction of Municipal Depots in all Clusters | CRR | N | 0 | 3000000 | 5000000
|  | T | 3100000 | 19300000 | 27500000
T
Facility Management- Community Development |  | D
Civic Centre refurbishment | CRR | R | 5000000 | 4500000 | 8000000
Renovation of municipal wide offices | CRR | R | 4000000 | 2000000 | 2500000
Municipal Furniture and Office Equipment | CRR | N | 500000 | 500000 | 1000000
Refurbishment of City Library and Auditorium | CRR | R | 2350000 | 500000 | 1000000
Upgrading of Seshego Library | CRR | R | 500000 | 700000 | 500000
Furniture and Equipment Molepo library | CRR | N | 500000 | 0 | 0
Modular Library Dikgale | CRR | N | 500000 | 0 | 2000000
Modular Library Bloodriver /Perskebult | CRR | N | 300000 | 1300000 | 2000000
Construction of Mankweng Traffic and Licensing Testing Centre | CRR | N | 0 | 3000000 | 4000000
Civic Centre Aircon Upgrade | CRR | N | 1500000 | 0 | 500000
Refurbishment of Municipal Public toilets (municipal wide) | CRR | N | 0 | 750000 | 800000
Renovation for the dilapidated AIDS Centre | CRR | R | 0 | 750000 | 0
Construction of Mankweng Water and Sanitation Centre | CRR | N | 1000000 | 4000000 | 6000000
Refurbishment of Mankweng Library | CRR | R | 0 | 0 | 1500000
Refurbishment of Mankweng Fire Department | CRR | R | 0 | 0 | 3000000
Construction of the integrated Control Center (Traffic Ladanna) | CRR | N | 0 | 0 | 4000000
Extension of the Fire and Traffic Training Facility at Ladanna | CRR | N | 0 | 0 | 3000000
Extension of offices Workshop (Water, Roads and Waste Management) at Ladanna | CRR | N | 0 | 0 | 400000
Construction of new Standby Staff facility at Ladanna | CRR | N | 0 | 0 | 3000000
Refurbishment of Nirvana Hall | CRR | N | 0 | 0 | 3000000
Extension of offices at ladanna electrical workshop | CRR | N | 0 |  | 1500000
|  | T | 16150000 | 18000000 | 47700000
T
T
Control Centre Services - Community Services |  | D
Installation of CCTV cameras in boreholes (Municipal Wide) | CRR | N | 1700000 | 2000000 | 0
Access Control | CRR | N | 227000 | 250000 | 1000000
Hand held radios | CRR | N | 100000 | 100000 | 200000
|  | T | 2027000 | 2350000 | 1200000
Roads & Stormwater - Engineering |  | D
Chebeng to Makweya internal streets | MIG | N | 4000000 | 0 | 0
Sebayeng ring road | MIG | N | 2600000 | 0 | 0
Tarring of Arterial road in SDA1 (Lithuli and Madiba park) | MIG | N | 17900000 | 10000000 | 0
Tarring Ntsime to Sefateng | MIG | N | 10000000 | 11000000 | 14000000
Upgrading Semenya to Matekereng | MIG | U | 11000000 | 8000000 | 0
Tarring of internal streets in Toronto | MIG | N | 10000000 | 11000000 | 0
Upgrading Internal Street in Seshego Zone 8 and zone 2 | MIG | N | 20000000 | 10000000 | 10000000
Upgrading of Ramongoana bus and Taxi roads | MIG | N | 3325000 | 11000000 | 0
Upgrading of Ntshitshane Road | MIG | N | 4000000 | 11000000 | 0
Upgrading of internal streets linked with Excelsior Street in Mankweng unit A | MIG | U | 10000000 | 5000000 | 5000000
Upgrading of Arterial road in Ga Rampheri | MIG | U | 0 | 10000000 | 7000000
Upgrading of access roads to Maja Moshate (Molepo Chuene Maja cluster) | MIG | U | 10000000 | 5000000 | 10000000
Upgrading Makanye Road (Ga-Thoka) | CRR | U | 4000000 | 10000000 | 10000000
Rehabilitation of streets in Seshego Cluster | CRR | R | 0 | 8000000 | 0
upgrading of stormwater system in municipal area (Vuk'uphile) | CRR | U | 1900000 | 6000000 | 0
Upgrading of internal streets in Seshego Zone 1 | CRR | U | 9500000 | 12000000 | 15000000
Upgrading of internal streets in Seshego Zone 2 | CRR | U | 4000000 | 12000000 | 15000000
Upgrading of internal streets in Seshego Zone 2 | MIG | U | 3000000
Upgrading of internal streets in Seshego Zone 3 | CRR | U | 9500000 | 12000000 | 15000000
Upgrading of internal streets in Seshego Zone 4 | CRR | U | 9500000 | 12000000 | 15000000
Upgrading of internal streets in Seshego Zone 5 | MIG | U | 5500000
Upgrading of internal streets in Seshego Zone 5 | CRR |  | 4000000 | 12000000 | 15000000
Upgrading of internal streets in Seshego Zone 6 | CRR
Upgrading of internal streets in Seshego Zone 8 | CRR
Upgrading of internal Streets in Mankweng unit E (Vuk'uphile) | CRR | U | 1140000 | 5000000 | 6000000
Traffic Lights and Signs (Municipal Wide) | CRR | N | 3000000 | 5000000 | 4000000
Installation of road signage (Municipal Wide) | CRR | N | 2690000 | 1200000 | 800000
Upgrading of Storm Water Canal in Seshego Zone 2 | NDPG | U | 12646000
Seshego Hospital link - Upgrading of township road & Bookelo street | NDPG | U | 8566000
Triangle Park - landscapping and street lighting Seshego Zone 2 | NDPG | U | 8788000
Construction of Stormwater culvert and NMT Facilities Skotipola, Kgoro and Dinkwe | NDPG | U | 5000000
NDPG | ndpg |  |  | 35000000 | 35000000
Mohlonong to Kalkspruit upgrading of road from gravel to tar | MIG | U | 7000000 | 0 | 10000000
Lonsdale to Percy clinic via Flora upgrading of road from gravel to tar | MIG | U | 0 | 10000000 | 0
Upgrading of roads in Molepo/Chuene/Maja Cluster | MIG | U | 0 | 0 | 15000000
Upgrading of roads in Sebayeng/Dikgale Cluster | MIG | U | 0 | 0 | 15000000
Upgrading of roads in Mankweng Cluster | MIG | U | 0 | 0 | 15000000
Upgrading of roads in Moletjie Cluster | MIG | U | 0 | 0 | 15000000
Upgrading of roads in Seshego Cluster | MIG | U | 0 | 0 | 15000000
Construction of NMT at Magazyn Street | KWBANK | N | 14400000
Upgrading of roads in Aganang Cluster | MIG | U | 0 | 0 | 15000000
Rehabilitation of streets in city cluster (Concession Program) | CRR | N | 70000000 | 75000000 | 80000000
b
|  | T | 286955000 | 307200000 | 356800000
T
Water Supply and reticulation - Engineering |  | D
Olifantspoort RWS (Mmotong wa Perekisi) | MIG | N | 23000000 | 13509300 | 15000000
Mothapo RWS | MIG | N | 0 | 12000000 | 13000000
Moletjie East RWS | MIG | N | 20000000 | 14000000 | 15000000
Moletjie North RWS | MIG | N | 0 | 10000000 | 10000000
Sebayeng/Dikgale RWS | MIG | N | 17000000 | 10000000 | 15000000
Moletjie South RWS | MIG | N | 0 | 10000000 | 16000000
Houtriver RWS phase 10 | MIG | N | 10000000 | 10000000 | 10000000
Chuene Maja RWS phase 9 | MIG | N | 0 | 7000000 | 14000000
Molepo RWS phase 10 | MIG | N | 10000000 | 5136700 | 5252100
Laastehoop RWS phase 10 | MIG | N | 6000000 | 6000000 | 8000000
Mankweng RWS phase 10 | MIG | N | 15000000 | 11000000 | 1000000
Boyne RWS phase 10 | MIG | N | 9763000 | 13000000 | 10000000
Water Conservation & Water Demand Management (Installation of Smart Meters) at Mankweng | WSIG | N | 20000000 | 29800000 | 10000000
Segwasi RWS Planning | WSIG | N | 1000000 | 8000000 | 19728100
Badimong RWS phase 10 Planning | WSIG | N | 1000000 | 15000000 | 11000000
Extension 78 water reticulation | CRR | N | 665000 | 6000000 | 8000000
Upgrading of laboratory at Polokwane Sewer plant | CRR | U | 475000 | 1000000 | 1500000
Extension 78 sewer reticulation | CRR | N | 665000 | 8000000 | 10000000
Extension 106 sewer & water reticulation | CRR | N | 13300000 | 5000000 | 10000000
Roodeport Reservoir Construction | CRR | N | 0 | 1000000 | 2000000
Aganang RWS 1 Planning | WSIG | N | 1000000 | 25000000 | 30000900
Aganang RWS 2 | MIG | N | 0 | 20000000 | 25000000
Asbestos (AC) Pipes in Seshego, Annadale & CBD | RBIG | N | 83335120 | 110000000 | 200551000
Raise dam wall Dap Naude | CRR | N |  | 0 | 0
Upgrade of Seshego Water works | CRR | U
Upgrade of Mashashane Water works | CRR | U
Upgrading of pipeline from Dap to Menz | RBIG | U | 0 | 110998000 | 283100000
Polokwane Water Network Upgrading (1) | CRR | U | 4750000 | 0 | 0
PolokwanWater Network Upgrading(2) | CRR | U | 4750000 | 0 | 0
Polokwane Central Groundwater development | WSIG | N | 45600000 | 32200000 | 45321000
Asset Renewals of Water Network (CBD) | CRR | R | 4500000 | 0 | 0
Asset Renewals of Waste Water Network (CBD) | CRR | R | 4500000 | 0 | 0
Upgrading of pipeline from Dap to Menz | CRR | U | 950000 | 0 | 0
|  | T | 297253120 | 493644000 | 788453100
T
Sewer Reticulation - Engineering |  | D
bulk outfall sewers | RBIG | N |  | 0 | 0
Regional waste Water treatment plant | RBIG | N | 180519880 | 240000000 | 160840000
Regional waste Water treatment plant | PLEDGE/RBIG | N | 170000000
Refurbishment of Polokwane Waste Water Treatment Works | CRR | R | 41800000 | 0 | 0
Plants and Equipment’s | CRR | N | 0 | 0 | 3000000
b
|  | T | 392319880 | 240000000 | 163840000
Energy Services - Engineering |  | D
Illumination of public areas ( main street into ext40,and75 from Nelson Mandela Voortrekker street , Ext 40 from Matlala road, Ext 71,73 | CRR | N | 2145000 | 2000000 | 3000000
Illumination of public areas ( High Mast lights) various rural areas | CRR | N | 487500 | 5000000 | 8000000
Replacement of oil RMU with SF6/ Vacuum in Industria and Nirvana | CRR | N | 0 | 2500000 | 15000000
SCADA on RTU in Superbia & Epsilon | CRR | N | 2437500 | 3000000 | 5000000
Replacement of overhead lines by underground cables CBD | CRR | N | 0 | 10000000 | 1000000
Replacement of Fiber glass enclosures in Flora, Fauna Park and NIrvana | CRR | N | 9750000 | 5000000 | 15000000
Planning and design New Bakone to IOTA 66KV double circuit GOAT line | CRR | N | 9750000 | 15000000 | 7000000
Build 66KV/Bakone substation | CRR | N | 9500000 | 8000000 | 7000000
Electrification Of Urban Households in Extension 78 and 40 | CRR | N | 5850000 | 5000000 | 5000000
Design and Construct permanent distribution substation at Thornhill | CRR | N | 9750000 | 2000000 | 1000000
Increase NMD from ESKOM at Alpha 11KV Distribution substation | CRR | N | 0 | 0 | 0
Power factor corrections in various Municipal Substations | CRR | N | 682500 | 7000000 | 9000000
Plant and Equipment | CRR | N | 2500000 | 2500000 | 1500000
Installation of 3x 185 mm² cables from Sterpark to Iota sub | CRR | N | 0 | 25000000 | 0
installation of 1 x 185 mm² cable from delta to bendor sub | CRR | N | 0 | 8000000 | 0
Increase license area assets | CRR | N | 1000000 | 8000000 | 9000000
Retrofit 66kV Relays at Gamma, Alpha & Sigma Substations | CRR | N | 0 | 3000000 | 4000000
Replace 66kV Bus Bars & Breakers at Gamma Substation | CRR | R | 3217500 | 5000000 | 3000000
Replacement of Fences at Gamma, Sigma, Alpha, Beta, Sterpark & Florapark Substations (vuk'uphile) | CRR | R | 975000 | 1000000 | 1000000
Upgrade Gamma Substation and install additional 20MVA transformer | CRR | U | 975000 | 10000000 | 10000000
Design and Construction of New Pietersburg 11kv substation | CRR | N | 1000000 | 20000000 | 5000000
Install additional 95MMX11KV cable to complete a ring in Debron to Koppiesfontein | CRR | N |  | 5000000 | 0
Supply power to new Pietersburg substation | CRR | N | 0 | 0 | 10000000
Replacement of undersized XLPE cables with PILCSTAcable in Nirvana & CBD | CRR | R | 0 | 0 | 10000000
Construction of new 66 KV Substations as per master plan in Tweefontein | CRR | N | 0 | 0 | 25000000
Construction of new 66 KV Lines as per master plan in Tweefontein | CRR | N | 0 | 0 | 15000000
Design and Construction of new 11 KV Substations to strengthern capacity in Johnson Park | CRR | N | 0 | 0 | 5800000
Installation of 11KV cables to new substations | CRR | N | 0 | 0 | 2000000
Installation of Check Meters at Main substations | CRR | N | 3200000 | 2000000 | 3200000
Installation of power banks at Main substations | CRR | N | 0 | 10000000 | 10000000
Lowering Pole mount boxes to ground mounted in Westernburg, Zone 1 Zone8, Zone5, Ext 71,73,75,9A, 9L | CRR | N | 5850000 | 8000000 | 10000000
Power Generation (SSEG) at Municipal Buildings | CRR | N | 0 | 0 | 10000000
|  | T | 69070000 | 172000000 | 210500000
b
Disaster and Fire - Community Services |  | D
Acquisition of fire Equipment | CRR | N | 2000000 | 1000000 | 2000000
6 floto pumps | CRR | N | 0 | 250000 | 300000
10 Largee bore hoses with stotz coupling | CRR | N | 350000 | 350000 | 350000
150X 80 Fire hoses with instantaneous couplings | CRR | N | 300000 | 300000 | 350000
Miscellaneous equipment and gear | CRR | N | 800000 | 550000 | 550000
Planning for extension of fire training Centre | CRR |  | 1000000
3 Heavy hydraulic equipment | CRR | N | 0 | 2000000 | 2000000
4 portable pump | CRR | N | 0 | 850000 | 850000
16 x Multipurpose branches Monitors | CRR | N | 300000 | 300000 | 300000
b
|  | T | 4750000 | 5600000 | 6700000
b
Traffic & Licencing - Community Services |  | D
Purchase alcohol testers | CRR | N | 200000 | 0 | 220000
Upgrading of logistics offices | CRR | U | 1000000 | 0 | 0
Upgrading- Traffic Auditorium, parade room and Training Facility | CRR | U | 600000 | 0 | 0
Upgrading of city vehicle test station | CRR | U | 500000 | 600000 | 600000
Procurement of AARTO equipments | CRR | N | 50000 | 50000 | 160000
Procurement of office cleaning equipment’s | CRR | N | 80000 | 100000 | 160000
Computerized Learners license | CRR | N | 0 | 0 | 2000000
Procurement of 2 X Metro counters (law enforcement) | CRR | N | 0 | 0 | 300000
Procurement of 7 X Pro-laser 4 Speed equipment’s | CRR | N | 0 | 0 | 1400000
|  | T | 2430000 | 750000 | 4840000
b
Environmental Health - Community Services |  | D
Vehicle exhaust gas analysis | CRR | N | 140000 | 0 | 0
|  | T | 140000 | 0 | 0
Environmental Management - Community Services |  | D
Grass cutting equipment’s | CRR | N | 900000 | 800000 | 950000
Development of a Botanical garden(Protected area Ster park) | CRR | N | 0 | 1800000 | 2000000
Development of a park at Ext 44 and 76 | CRR | N | 3200000 | 800000 | 900000
Upgrading of Tom Naude Park | CRR | U | 500000 | 800000 | 1000000
Zone 4 Park Expansion Phase 2 | CRR | N | 0 | 800000 | 900000
Upgrading of Security at Game Reserve | CRR | U | 1500000 | 3000000 | 3000000
Upgrading of Environmental Education Centre | CRR | U | 750000 | 1000000 | 1000000
Construction of ablution facilities at Tom Naude Park | CRR | N | 1200000 | 0 | 0
Development of Ablution facilities at Various Municipal Parks | CRR | N | 500000 | 3000000 | 3000000
Animal Pound | CRR |  | 400000
Upgrading of Ga- Kgoroshi community centre | CRR |  | 500000
Development of regional/ cluster parks | CRR | N | 0 | 0 | 2000000
Development of regional/ cluster cemeteries | CRR | N | 0 | 0 | 2000000
|  | T | 9450000 | 12000000 | 16750000
b
Waste Management - Community Services |  | D
30 m3 skip containers | CRR | N | 800000 | 600000 | 1000000
Extension of landfill site(weltevrede) | CRR | N | 4000000 | 0 | 2000000
Extension of offices(Ladanna) | CRR | N | 0 | 500000 | 0
Rural transfer station ( Sengatane) | MIG | N | 4266667 | 0 | 3000900
Rural transfer station (Dikgale) | MIG | N | 4266667 | 3000000 | 0
Rural transfer Station(Makotopong) | MIG | N | 4266666 | 3000000 | 0
770 L Refuse Containers | CRR | N | 0 | 600000 | 1000000
240 litre bins | CRR | N | 0 | 1000000 | 0
6 &9 M3 Skip containers | CRR | N | 0 | 600000 | 1000000
b
|  | T | 17600000 | 9300000 | 8000900
Sport & Recreation - Community Development |  | D
Construction of an RDP Combo Sport Complex at Molepo Area- 2 | MIG | N | 0 | 0 | 0
Construction of Mankweng Sport facility-2 | MIG | N | 11440000 | 0 | 0
Sport stadium in Ga-Maja | MIG | N | 9600000 | 4000000 | 0
EXT 44/77 Sports and Recreation Facility | MIG | N | 1500000 | 10000000 | 8000000
Grass Cutting equipment | CRR | N | 500000 | 1000000 | 1200000
Upgrading of Mankweng Stadium-roadworks | MIG | U | 0 | 6000000 | 0
Upgrading of Tibane Stadium | CRR | U | 475000 | 2000000 | 0
Rehabilitation of Swimming Pool | CRR | R | 1575000
Upgrading of Mohlonong Stadium | MIG | U | 7300000 | 9000000 | 0
b
|  | T | 32390000 | 32000000 | 9200000
T
Security Services - Community Services |  | T
Walk through metal detector | CRR | N | 200000
Upgrading of offices at Itsoseng for Security Services | CRR | N | 600000
Supply and installation of Safes | CRR | N | 80000
Supply and installation of Guard tracking devices | CRR | N | 800000
Supply and delivery of guard houses | CRR | N | 900000
T
|  | T | 2580000 | 0 | 0
Cultural Services - Community Development |  | D
Collection development - Books | CRR | N | 1000000 | 1200000 | 3000000
New Exhibition Irish House | CRR | N | 800000 | 800000 | 900000
|  | T | 1800000 | 2000000 | 3900000
Information Services - Corporate and Shared Services |  | D
Provision of Laptops, PCs and Peripheral Devices | CRR | N | 2000000 | 2000000 | 2000000
Implementation of ICT Strategy | CRR | N | 750000 | 800000 | 1000000
Network Upgrade | CRR | U | 7000000 | 8500000 | 14000000
b
|  | T | 9750000 | 11300000 | 17000000
City Planning - Planning and Economic Development |  | D
Township establishment-Farm Volgestruisfontein 667 LS | CRR | N | 2000000 | 1000000 | 1000000
Township establishment - Nirvana | CRR | N | 0 | 0 | 1000000
Township establishment at portion 151-160 of the Farm Sterkloop 688 LS for PHA mixed land use | CRR | N | 3000000 | 0 | 4500000
Township establishment-Portion 74 and 75 of Ivy Dale Agricultural Holdings | CRR | N | 1000000 | 500000 | 1500000
Integrated feasibility studies for logistics and Industrial hub | CRR | N
Installation of engineering services at Polokwane extension 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 (water, electricity, sewerage network and roads) | CRR | N | 0 | 9000000 | 20000000
Acquisition of land | CRR | N | 0 | 3000000 | 11000000
Upgrading of the R293 area Townships | CRR | U | 0 | 0 | 12000000
T
|  | T | 6000000 | 13500000 | 51000000
GIS - Planning and Economic Development |  | D
Procurement of a drone for aerial imagery | CRR | N | 0 | 0 | 2500000
|  | T | 0 | 0 | 2500000
LED - Planning and Economic Development
Integrated feasibility studies for logistics and Industrial hub | CRR | N | 1000000 | 0 | 2150000
|  | T | 1000000 | 0 | 2150000
T
T
Transport Operations(IPRTS)- Transport and Services |  | D
Implementation of IRPTS Infrastructure | PTISG | R | 0 | 0 | 0
AFC | PTNG | R | 31389000 | 0
PTMS | PTNG | R | 13964000 | 0
Buses | PTNG | R | 37333000 | 0 | 0
Control Centre | PTNG | R | 1500000 | 0 | 0
Infrastructure | PTNG | R | 0 | 77158000 | 81207000
Upgrad & constr of Trunk route 108/2017 | PTNG | R | 6500000 | 0 | 0
Construction of bus depot Civil works 108/2017 | PTNG | R | 5000000 | 0 | 0
Construction of bus station Civil works 108/2017 | PTNG | R | 5000000 | 0 | 0
Daytime lay-over 108/2017 | PTNG | R | 4000000 | 0 | 0
CBD Transit Mall 108/2017 | PTNG | R | 3000000 | 0 | 0
Construction & provision of Depot Upper structures | PTNG | R | 11000000 | 0 | 0
Construction & provision of Station Upperstructures | PTNG | R | 18000000 | 0 | 0
Refurbishment of Daytime Layover Buildings | PTNG | R | 2800000 | 0 | 0
OHS Management | PTNG | R | 1200000 | 0 | 0
Environmental Management Seshego & SDA1 | PTNG | R | 600000 | 0 | 0
Environmental Management in Polokwane City | PTNG | R | 413000 | 0 | 0
Compensation | PTNG | R | 20833000 | 20833000 | 20833000
Acquisition of buses | PTISG Pledge | N | 105000000
|  | T | 267532000 | 97991000 | 102040000
T
Supply Chain Management - Budget and Treasury Services |  | D
Upgrading of stores | CRR | U | 8500000 | 2001000 | 0
|  | T | 8500000 | 2001000 | 0
|  | GT | 1430797000 | 1438936000 | 1820074000
Municipal Infrastructure Grant | MIG |  | 271728000 | 278646000 | 314253000
Public Transport Network Grant | PTIG |  | 162532000 | 97991000 | 102040000
Neighbourhood Development Grant | NDPG |  | 35000000 | 35000000 | 35000000
Water Services Infrastructure Grant | WSIG |  | 68600000 | 110000000 | 116050000
Regional Bulk Infrastructure Grant | RBIG |  | 263855000 | 460998000 | 644491000
Total DoRA Allocations |  |  | 801715000 | 982635000 | 1211834000
PTIG Pledge | PTIG |  | 105000000 | 0 | 0
Donation | KFWbank |  | 14400000 | 0 | 0
RBIG Pledge | RBIG/PLEDGE |  | 170000000 | 0 | 0
CRR | CRR |  | 339682000 | 456301000 | 608240000
TOTAL FUNDING |  |  | 1430797000 | 1438936000 | 1820074000

## BSD
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Total Number of HH/Denominator (CS 2016) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
BSD_TL01 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Energy | Increase electricity capacity by: building substations and install underground cables | Number of new substations built by 30 June 2019 | # | N/A | 1 | 4 | n/a | n/a | n/a | 4 | Progress reports and Completion certificates
BSD_TL02 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Energy | Increase electricity capacity by: - building substations and install underground cables | Kilometre of underground cables installed by 30 June 2019 | km | N/A | New | 4 | n/a | n/a | n/a | 4 | Progress reports and Completion certificates
BSD_TL03 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Energy | Expanding smart metering | Number of new smart meters installed by 30 June 2019 | # | N/A | 6000 | 2000 installation of extra smart meters | 500 | 500 | 500 | 500 | Progress reports and Completion certificates
BSD_TL04 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Energy | Households with access to electricity | Increase percentage of Households with access to electrification from 95.6% (228594 HH) to 96.7% (231261 HH) by 30 June 2019. | % | 239116 | 95.6% (228594 HH) | 96.7% (2667) | n/a | n/a | n/a | 96.7% (2667) | Progress reports and Completion certificates
BSD_TL05 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Energy | number of retrofits done to reduce consumption | Percentage Electricity reduction consumption losses by 30 June 2019. Difference between electricity purchased and electricity sold | % | N/A | 14250 retrofitted street lights | 13200 retrofitted street lights- | 3300 | 3300 | 3300 | 3300 | Electricity reduction assesment report
BSD_TL06 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Sanitation | Upgrade existing Polokwane waste water plant | Increase percentage of Households with access to sanitation from 59.5% (142274 HH) to 60.3% (144074 HH) by 30 June 2019 | % | 239116 | Approximately 2350 VIP toilets. 59.5% (142274 HH) | Approximately 1800 VIP toilets. 60.3% (144074 HH) |  |  |  | Approximately 1800 VIP toilets. 60.3% (144074 HH) | Progress reports and Completion certificates
BSD_TL07 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Water | Replace old existing asbestos cement pipes that is causing water loss | Kilometre of old asbestos cement pipes replaced by 30 June 2019 | km | N/A | Replaced at least 100km asbestos pipes. | 145 | 36.25 | 36.25 | 36.25 | 36.25 | Progress reports and Completion certificates
BSD_TL08 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Water | Replacement of old water meters in the city | Number of old water meters replaced in the city by 30 June 2019 | # | N/A | 22 000 Meters replaced. | 15 000 | 3750 | 3750 | 3750 | 3750 | Progress reports and Completion certificates
BSD_TL09 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Water | Increase existing water sources - Oliphant’s, Ebenezer, Molepo, Seshego, Hout River, Dap Naude (increase water treatment plant). | ML capacity of water treatment plants increased by 30 June 2019 | Ml | N/A | New | 17.8 | n/a | n/a | n/a | 17.8 | Progress reports and Completion certificates
BSD_TL10 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Water | Increase existing boreholes by development of new bore holes. | Number of new boreholes developed (drilled and equipped) by 30 June 2019 | 198 | N/A | New | 66 | n/a | n/a | n/a | 66 | Progress reports and Completion certificates
BSD_TL11 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Water | Increase access to water supply. | Increase percentage of Households with access to Water from 82.3% (196792) to 83.2% (198952 HH) by 30 June 2019 | % | 239116 | Access to water supply. 82.3% (196792 HH) | 83.2% (2160HH) | n/a | n/a | n/a | 83.2% (2160HH) | Progress reports and Completion certificates
BSD_TL12 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transport, Roads and storm water | Implement MIG programme. Increase allocation per financial year to allow quick reduction of backlog | Km of roads upgraded from gravel to tar by 30 June 2019 | km | N/A | 13 | 40 | n/a | n/a | n/a | 40 | Progress reports and Completion certificates
BSD_TL13 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transport, Roads and storm water | Implement MIG programme. Increase allocation per financial year to allow quick reduction of backlog | Km of roads renewed (Asset Renewal Programme/Existing tar roads) by 30 June 2019 | km | N/A | 6.18 | 20 | n/a | n/a | n/a | 20 | Progress reports and Completion certificates
BSD_TL14 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transport, Roads and storm water | Construct storm water in existing towns (Mankweng and Seshego) | Km of Storm water constructed in existing towns (Mankweng and Seshego) by 30 June 2019 | km | N/A | 3 | 1.2 | n/a | n/a | n/a | 1.2 | Progress reports and Completion certificates
BSD_TL15 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Fleet Management | Review fleet contract upon expiry | Percentage availability of municipality service delivery fleet vehicles for operational purpose (fleet availability norm is 75%) by 30 June 2019 | # | N/A | 75% | 85% | 85% | 85% | 85% | 85% | Fleet reports
BSD_TL16 | Service Delivery | Smart Living | Improving sports and recreational facilities and promotion of social cohesion |  | Sports and Recreation | Encourage the formation of clubs and promotion of capacity building of sports administrators (Coaches and referees) | Number of promotion events conducted to build capacity of sport administrators by 30 June 2019 | # | N/A | 4 | 2 |  | 1 |  | 1 | Pictures, Report and minutes
BSD_TL17 | Service Delivery | Smart Environment | Development of municipal capacity to manager disaster risk and protection of environment | To ensure the provision of basic and environmental services in a sustainable way to our communities | Community Health | Obtain authorization from Capricorn District Municipality to render the service on their behalf | Number of Health (Food premises and outlets) Inspections conducted by 30 June 2019 | # | N/A | 1540 | 1540 | 385 | 385 | 385 | 385 | Food premises and outlets) Inspections reports
BSD_TL18 | Service Delivery | Smart Living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Waste Management | Address Waste Management backlog in rural areas. | Number of rural villages supplied with weekly waste removal services by 30 June 2019 | # | N/A | 18 | 18 | n/a | n/a | n/a | 18 | Waste Management Monthly reports, Waste Management Operational Routes, Equipments and Staff employed to collect waste.
BSD_TL19 | Service Delivery | Smart Environment | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way | Waste Management | To promote recycling and ensure that waste generated is managed and disposed of in an environmentally friendly manner | Percent of Households with access to waste removal services from 43.07% (102987) to 43.9% (103035 HH)by 30 June 2019 | % | 239116 | 43.07% (102987) | 43.09% (48 HH) | n/a | n/a | n/a | 43.09% 48 HH) | Waste Management Monthly reports, Waste Management Operational Routes, Equipments and Staff employed to collect waste.
BSD_TL20 | Service Delivery | Smart Environment | Development of municipal capacity to manage disaster risk and protection of environment | To ensure provision of basic and environmental services in a sustainable way | Disaster Management and Fire Services | Conduct Hazard identification and assessment programme. | Review Disaster Management Plan (Annual review) by 30 June 2019 | # | N/A | 1 Disaster Management Plan reviewed by 30 June | 1 Disaster Management Plan reviewed by 30 June | na | n/a | n/a | 1 Disaster Management Plan reviewed by 30 June | Reviewed and approved Disaster Management Plan, Council resolution and minutes
BSD_TL21 | Service Delivery | Smart Environment | Development of municipal capacity to manage disaster risk and protection of environment | To ensure provision of basic and environmental services in a sustainable way | Disaster Management and Fire Services | Conduct reblading programme. | Km fire break reblading conducted by 30 June 2019 | km | N/A | 2600 km | 1800km | n/a | n/a | n/a | 1800km | Progress reports and Completion certificates
BSD_TL22 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transportation (Infrastructure) | Plan and construct infrastructure | Km of Trunk route constructed by 30 June 2019 | km | N/A | 3.85 | 0.65 | n/a | n/a | n/a | 0.65 | Progress reports and Completion certificates
BSD_TL23 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transportation (Infrastructure) | Plan and construct infrastructure | KM of TE constructed at Moletjie by 30 June 2019 | km | N/A | 2.6 | 0.7 | n/a | n/a | n/a | 0.7 | Progress reports and Completion certificates
BSD_TL24 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transportation (Communications and Marketing) | Provide safe, reliable, affordable, sustainable public transport system | Number of affected Taxi and Bus operators integrated into Leeto La Polokwane by 30 June 2019 | # | N/A | New | 4 | n/a | n/a | n/a | 4 | Progress reports

## GGPP
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
GGPP_TL01 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | IDP | Ensure involvement and participation of all stakeholders | Number of IDP, Budget and PMS Rep Forums held by 30 June 2019 | # | 2 | 2 | n/a | 1 | n/a | 1 | IDP Rep Forum Notices, Agenda and Attendance Registers
GGPP_TL02 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure community confidence in the system of local government | IDP | Facilitate and monitor the identified needs falling without the municipality's mandate | Approval of the current financial year IDP, Budget and PMS Schedule (Process Plan) by 30 August 2018 (S21 of the MFMA) | # | 1 | 1 | 1 | n/a | n/a | n/a | Council Resolution on IDP, Budget and PMS Process Plan
GGPP_TL03 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure community confidence in the system of local government | IDP | Ensure involvement and participation of all stakeholders | Number of IDP, Budget and PMS Steering Committee Meeting held by 30 June 2019 | # | 3 | 3 | 1 | n/a | 1 | 1 | IDP, Budget and PMS Steering Committee Notices and Agenda, Minutes and Attendance Registers
GGPP_TL04 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure community confidence in the system of local government | IDP | To ensure budgeting processes are informed by community needs and priorities by 2018 | Submitting the next financial year Final IDP and Budget to Council for adoption by 31 May 2019 (One month before the start of the new financial year) | # | 1 | 1 | n/a | n/a | n/a | 1 | Council Resolution on the 2019/20 Final IDP
GGPP_TL05 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | PMS | Communicate and share performance information | Tabling Draft Annual Report for previous financial year to Council by 31 January 2019. (s121 - 129 MFMA) | Date | 2018-01-31 | 2019-01-31 | n/a | n/a | 2019-01-31 | n/a | Council Resolution on Draft Annual Report for 2017/18 financial year
GGPP_TL06 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | PMS | Communicate and share performance information | Number of Quarterly Performance Reports submitted to Council in line with MFMA S52 (d), by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Council Resolution on Quarterly Performance Reports and Quarterly Reports
GGPP_TL07 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | PMS | Communicate and share performance information | Tabling the Oversight Report on the previous financial year Annual Report to Council by 31 March 2019 (Section 121-129 MFMA) | Date | 2018-03-31 | 2019-03-31 | n/a | n/a | 2019-03-31 | n/a | Council Approved Oversight Report on the 2017/18 Annual Report
GGPP_TL08 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | ICT | Continuous improvement of Corporate Governance of and Governance of ICT | Number ICT Steering Committee meeting held by 30 June 2019 | # | New | 4 | 1 | 1 | 1 | 1 | Invitations, Agend, Minutes and Attendance Registers
GGPP_TL09 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | ICT | Continuous improvement of Corporate Governance of and Governance of ICT | Number of quarterly reports on the performance of ICT Service providers by 30 June 2019 | # | New | 4 | 1 | 1 | 1 | 1 | ICT Assessment reports and Minutes
GGPP_TL10 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Legal | Review and implement delegations of powers to ensure that all managers act and take decisions within their scope | Annual review of the Delegations of powers to ensure effective administration by 31 August 2018 | # | New | Reviewed delegations of powers by 31 Aug 2018 | Reviewed delegations of powers by 31 Aug 2018 | n/a | n/a | n/a | Council Approved Delegation of Powers
GGPP_TL11 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Secretariat Services | Ensuring that Mayoral Committee meetings are convened as per cooperate calendar. | Number of Mayoral Committee meetings scheduled and convened by 30 June 2019 | # | 10 | 10 | 3 | 3 | 2 | 2 | Council Approved Corporate Calendar of meetings. Mayoral Committee notices, Agendas, and Attendance Registers
GGPP_TL12 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Secretariat Services | Ensuring that Council meetings are convened as per cooperate calendar. | Number of Council sittings scheduled and convened by 30 June 2019 (In line with the provisions of MSA) | # | 4 | 4 | 1 | 1 | 1 | 1 | Council Meeting Notices, Agenda and Minutes
GGPP_TL13 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Secretariat Services | Ensuring that Portfolio meetings are convened as per cooperate calendar. | Number of Portfolio Committee meetings scheduled and convened by 30 June 2019 | # | 130 | 130 | 33 | 32 | 33 | 32 | Council Approved Corporate Calendar of meetings. Portfolio Committee Notices, Agendas, Minutes and Attendance Registers
GGPP_TL14 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Human Resources/ Labour Relations | Monitor the corporate calendar. | Number of Local Labour Forum meetings convened and held by 30 June 2019 | # | 10 | 10 | 3 | 2 | 2 | 3 | LLF Notices, Agendas, Minutes and Attendance Registers
GGPP_TL15 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Organisational Development | Develop integrated long term asset management plan | Integrated long term asset management plan developed by 30 June 2019 | # | 1 | 1 | 1 | n/a | n/a | n/a | Council Approved Long Term Asset Plan
GGPP_TL16 | Good Governance and Public Participation | Smart Governance |  |  |  | Develop integrated long term asset management plan | Conduct municipal wide asset register verification in line with GRAP standards by 31 August 2018 | # | 1 | 1 | 1 | n/a | n/a | n/a | GRAP Compliant Asset Register
GGPP_TL17 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure social protection and education outcomes | Special Focus | Liaise with the Department of Health and developmental partners to reduce HIV. Establish Ward AIDS Councils. Implement the 90/90/90/ Fast track Strategy for municipalities to reduce HIV By 2020 | Number of Ward AIDS Councils established by 30 June 2019 | # | 12 | 45 | 45 | n/a | n/a | n/a | Ward AIDS Council Reports and Establishment Notice
GGPP_TL18 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Internal Audit | Cooperating closely with other external oversight bodies to better coordinate oversight activities with a view to providing effective audit coverage and minimising any overlaps | Development of the External and Internal Audit Tracking Register for previous financial year AG Report by 5 February 2019 | # | 1 | 1 | n/a | n/a | 1 | n/a | Approved Internal and External AG Tracking Register
GGPP_TL19 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Internal Audit | Communicate effectively with management to receive effective feedback on the preparation and reporting on the implementation of audit work plans | Adoption of Annual Internal Audit Plan and 3 year rolling strategic plan by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Council Approved Annual Internal Audit Plan for 2018/19
GGPP_TL20 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Internal Audit | Regular review and improving the quality of audit reports by increasing the use of available information technology tool to gather, analyse and present factual data to enhance the accuracy, completeness and tidiness of audit reports | Number of Audit Committee Meetings scheduled and convened in terms of the adopted schedule by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Audit Committee Notices, Agendas and Minutes
GGPP_TL21 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Public Participation | Increase functionality and effectiveness of ward committee structures | Number of Ward Committee meetings scheduled and convened per ward by 30 June 2019 (Functionality of ward committees) | # | 540 | 540 | 135 | 135 | 135 | 135 | Ward Committee Reports, Mihutes and Notices of meetings
GGPP_TL22 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Public Participation | Increase functionality and effectiveness of ward committee structures | Number of Ward Committee Reports developed and submitted to Council by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Council Resolutions on Ward Committee Reports
GGPP_TL23 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Roll-out of risk management services within all levels of the municipalities by identifying potentials risks within the municipality | Number of risk assessments conducted by 30 June 2019 | # | 40 | 45 | n/a | n/a | 45 | n/a | Invitation, Agenda and Minutes
GGPP_TL24 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Creating fraud culture in y and Promote Fraud Hotline in the Municipal area | Number of Fraud awareness Campaign held conducted by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Risk Awareness Campaigns notices and Attendance Registers
GGPP_TL25 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Incorporate Risk Management in the IDP and Budgeting process by identifying strategic risk and budgeting for mitigation action | Reviewal of institutional strategic risk register by 30 June 2019 | # | 1 | 1 | n/a | n/a | 1 | n/a | Reviewed and Approved Risk Register
GGPP_TL26 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Increase functionality, effectiveness and accountability of Risk Management at Directors level | Number of Risk Management Committee scheduled and convened by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Risk Management Notices, Agenda and Minutes

## MTOD
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
MTOD_TL01 | Municipal Transformation and Organisational Development | Smart People |  | To ensure efficiency and effectiveness of municipal administration | Occupational Health and Safety | Expand OHS capacity | Conduct OHS audit by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | OHS Audit Report
MTOD_TL02 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Build capacity of employees through training | Submission of Reviewed of WSP to LGSETA by 30 April 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Signed and Dated WSP
MTOD_TL03 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Targeted recruitment | Submission of Employment Equity Plan to the Department of Labour by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Submission letter and Signed EE Plan
MTOD_TL04 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Targeted awarding of bursary | Number of new External Students awarded study bursaries for the next academic year by 30th June 2019 | # | 40 | 40 | n/a | n/a | n/a | 40 | Register of External Students with the ID numbers and bursaries enrolled for, Bursary Contracts
MTOD_TL05 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Build capacity of municipal officials and the community on skills. | Number of Graduate students awarded Internships/Experimental/Learnership at Polokwane Municipality by the 30 June 2019 | # | 150 | 200 | n/a | n/a | n/a | 200 | List of Students and their details with the names of internships awarded to them
MTOD_TL06 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Build capacity of municipal officials around IR matters | Number of training on application and understanding of code of conduct for all employees by 30 June 2019 | # | 2 | 2 | 1 | n/a | n/a | 1 | Code of Conduct Training Notice, Attendance Register

## LED
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
LED_TL01 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | LED | Sustainable Livelihoods | Number of street traders capacitated through municipal sponsored training by June 2019 | # | 10 | 180 | 30 | 45 | 50 | 55 | List of street traders capacited and program attended. Reports
LED_TL02 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | EPWP | Sustainable Livelihoods | Number of job opportunities created through the EPWP by 30 June 2019 (Temporary Job Opportunities) | # | 3525 | 4249 | 700 (Cummulative) | 2000 (Cummulative) | 3500 (Cummulative) | 4249 (Cummulative) | Copy of EPWP Job Creation report submitted to DPW
LED_TL03 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | LED - SMMEs | Assist SMME to attend exhibitions | Number of exhibition/Flee Markets facilitate the municipality by 30 June 2019 | # | 12 | 12 | 3 | 3 | 3 | 3 | Exhibition reports
LED_TL04 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | Economic Development | Implement Tourism strategy | Number of tourism and investment promotion trade shows by 30 June 2019 | # | 8 | 8 | 3 | 1 | 3 | 1 | List of tourism operators offered support and the programme attended. Reports on SMME
LED_TL05 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | Economic Development | Promote the creation of sustainable jobs | Number of job opportunities created through Municipal sponsored trading | # | 100 | 160 | 30 | 60 | 50 | 40 | Reports and Attandace register
LED_TL06 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | Economic Development | Skills audit and training of SMMEs | Number of Workshops/Trainning organised by the municipality in partnerships with sector partners offered to SMME's by 30 June 2019 | # | 4 | 16 | 4 | 4 | 4 | 4 | List of SMME incubated and the programme attended. Reports on SMME Incubation

## FV
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
FV_TL01 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Budget and Reporting | Improve internal and integrated financial reporting processes to ensure all SBU's are using accurate financial information | Development of the Audit Action Plan for the current financial year AG Report by 31 January 2019 | # | 1 | 1 | n/a | n/a | 1 | n/a | Executive Management Approved AG Audit Action Plan for the 2017/18 AG Report
FV_TL02 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Budget and Reporting | Improve internal and integrated financial reporting processes to ensure all SBU's are using accurate financial information | Municipal compliance to MSCOA by 30 June2019 | % | None | 100% | 100% | 100% | 100% | 100% | Mscoa Compliant Report from National Treasury
FV_TL03 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Expenditure Management | Accurate cash flow planning (SBUs to supply cash flow projections on projects at the beginning of each financial year) | Timeous payment of all the creditors with 30 days upon receipt of invoice | % | 100% | 100% | 100% | 100% | 100% | 100% | Expenditure Report
FV_TL04 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Expenditure Management | To build up reserves (sinking funds) to pay back loans and asset replacement funds | Number of reserve to be established by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | n/a | Invest Report
FV_TL05 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Revenue Management | Develop and enforce business processes and procedures | Number of Households with access to free basic services to all qualifying people in the municipal's area of jurisdiction | # | 30000 | 30500 | 30500 | 30500 | 30500 | 30500 | Indigent Register and details of Indigent Benefiaries
FV_TL06 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Revenue Management | Develop and enforce business processes and procedures | Percentage collection of revenue billed, total billed vs total collected. | % | 85% | 86% | 86% | 86% | 86% | 86% | Revenue Report
FV_TL07 | Financial Viability | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Supply Chain Management | Follow up and adherence to demand management plan | Timeous appointment of service providers within 90 days in line with the National Treasury Norm on appointment of contractors | % | 100% | 100% | 100% | 100% | 100% | 100% | Demand Management Plan and Appointment letters
FV_TL08 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Percentage of municipality capital budget actually spent on capital projects by 30 June 2019 | % | 100% | 100% | 100% | 100% | 100% | 100% | Quarterly Capital Implementatiion Report
FV_TL09 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Municipal debt coverage by 30 June 2019 | % | 17% | 17% | 17% | 17% | 17% | 17% | MFMA S71 Report
FV_TL10 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Municipal outstanding service debtors by 30 June 2019 | % | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | MFMA S71 Report, Debtors Age Analysis Report
FV_TL11 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Municipal cost coverage by 30 June 2019 | % | 200% | 200% | 200% | 200% | 200% | 200% | MFMA S71 Report

## DETAILED CWP
Project Number | Key Performance Area | Polokwane Strategic Objective (IDP Objective) | Municipal Programme | Project Name/Description | Type of Project - New/Renewal | Project Location | Ward No. | Project Owner | Sources of Funding | Implementing Agent | Original Budget | Quarterly Project Implementation Milestones |  |  |  | Annual Project Output (30 June 2019) | PoE (Evidence to verify Performance
[12 empty] | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun)
Clusters - SPME
| Good Governance and Public Participation | Improved efficiency and effectiveness of Municipal administration | Clusters | Thusong Service Centre (TSC) -Mankweng | R | Mankweng | Mankweng Cluster | Director SPME | CRR |  | 1000000 | Preparing of Bid document and finalising of construction estimate. Completion of planning. | None | None | None | Cpmpletion of planning phase. | Bid document. Drawings
| Good Governance and Public Participation | Improved efficiency and effectiveness of Municipal administration | Clusters | Mobile service sites at Molepo Chuene Maja Cluster (Rampheri Village) | N | Rampheri - Maja | Chuene/Maja/Molepo Cluster | Director SPME | CRR |  | 1500000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
Total Clusters - SPME
2500000
Facility Management- Community Development
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Civic Centre refurbishment | R | Polokwane | Pcity Cluster | Director Community development | CRR |  | 4000000 | Installation of new alluminium windows, new mechanical ventilation, new electrical layouts. | Installation of new partitions, floor finishes, new electrical layouts and sanitary fittings. | Completion of Ground floor west wing | None | Refurbishment of Civic Centre ground floor | Payments, progress reports, completion certificates
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Renovation of municipal wide offices | R | Polokwane | Pcity Cluster | Director Community development | CRR |  | 1500000 | Installation of aircons at Libraries | Installation of carports at Traffic Ladanna | None | None | Installation of aircons and carports | Payments, progress reports, completion certificates
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Municipal Furniture and Office Equipment | N | Polokwane | Pcity Cluster | Director Community development | CRR |  | 500000 | Supply office furniture | Supply office furniture | None | None | Delivery of office furniture | Delivery notes, Payments
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Refurbishment of City Library and Auditorium | R | Polokwane | 20 | Director Community development | CRR |  | 500000 | Waterproofing, painting, electrical | None | None | None | Waterproofing, painting, electrical | Job cards, payments
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Upgrading of Seshego Library | R | Seshego | 17 | Director Community development | CRR |  | 500000 | Installation of aircons, aluminium doors | None | None | None | Installation of aircons, aluminium doors | Payments, progress reports, completion certificates
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Library Dikgale | N | Dikgale | 32 | Director Community development | CRR |  | 500000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Library Bloodriver /Perskebult | N | Bloodriver /Perskebult | 10 | Director Community development | CRR |  | 300000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Civic Centre Aircon Upgrade | N | Polokwane | 20 | Director Community development | CRR |  | 1000000 | Installation of aircon plant for Civic Centre North wing | Installation of aircon plant for Civic Centre North wing | None | None | Installation of aircon plant for Civic Centre North wing | Job cards, payments
| Basic Service Delivery | Increased access to municipal services to all households | Infrastructure/Facility Maintenance | Construction of Mankweng Water and Sanitation Centre | N | Mankweng | 25 | Director Community development | CRR |  | 1000000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
Total Facility Management- Community Development
9800000
Control Centre Services - Community Services
| Basic Service Delivery | Improved social protection and education outcomes | Security Services | Installation of CCTV cameras | N |  |  | Director Community Services | CRR |  | 1700000 | Planning and outlining the installation of internal and external cameras | Installation of cameras on biuldings that does not have cameras at all | Installation of cameras in the CBD at the hot spot areas as would be identified | Installation of cameras at biuldings that need to be added | Project completion | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Improved social protection and education outcomes | Security Services | Hand held radios | N |  |  | Director Community Services | CRR |  | 100000 | Planning the installation and purchase of two way radios | Installing base radios | Purchasing two way radios for end users | Purchasing two way radios for end users | Project completion | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Improved social protection and education outcomes | Security Services | Access Control | N |  |  | Director Community Services | CRR |  | 227000 | Planning and outlining the installation of Access control at various biulding | Conducting assessment for the installation access at all Municipal premises | Installation of access (biometric and card readers)40% | Installation of access (biometric and card readers)60% | Project completion | Appointment letter, Project progress report, Payment certificate, Completion certificate
Total Control Centre Services - Community Services
2027000
Roads & Stormwater - Engineering
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Chebeng to Makweya internal streets | N | Makweya | 9 | Director Engineering | MIG | Polokwane Municipality | 4000000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Chebeng to Makweya road | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Sebayeng ring road | N | Sebayeng | 32 | Director Engineering | MIG | Polokwane Municipality | 2600000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Sebayeng road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Tarring of Arterial road in SDA1 (Lithuli and Madiba park) | N | Lithuli | 14 | Director Engineering | MIG | Polokwane Municipality | 13000000 | Appointment of contractor and site establishment | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Finalizing layer works and Surfacin, cleaning of site. | Multiyear project. Completion of phase 1 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Tarring Ntsime to Sefateng | N | Ntsime | 31 | Director Engineering | MIG | Polokwane Municipality | 10000000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | project completion | Completion of Ntsima to Sefateng road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading Semenya to Matekereng | N | Semenya | 38 | Director Engineering | MIG | Polokwane Municipality | 11000000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Semenya to Matekereng road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of roads in Moletjie Cluster | N | Moletjie cluster | 09,10,15,16,18,35,36,38 | Director Engineering | CRR | Polokwane Municipality | 1000000 | Appointmnet of consultant | Scoping report | Prelimenary report and Detailed design report | Tender advert | Tender advert of project | Tender advert
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading Internal Street in Seshego Zone 8 | N | Zone 8 | 11 | Director Engineering | MIG | Polokwane Municipality | 9225000 | Appointment of a Contractor,Site establishment and road bed preparartions | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 8 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of Ramongoana bus and Taxi roads | N | Ramongwana | 38 | Director Engineering | MIG | Polokwane Municipality | 3500000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Ramongwana road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of Ntshitshane Road | N | Ntshitshane | 6, 31 | Director Engineering | MIG | Polokwane Municipality | 7000000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Ntshitshane road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Tarring of internal streets in Toronto | N | Toronto | 25 | Director Engineering | MIG | Polokwane Municipality | 10000000 | Appointment of a Contractor,Site establishment and road bed preparartions | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Toronto road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal Streets in Mankweng unit E (Vuk'uphile) | N | unit E | 25 | Director Engineering | CRR | Polokwane Municipality | 1140000 | Handover of site to Learner contractors, site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Mankweng | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets linked with Excelsior Street in Mankweng unit A | N | Mankweng | 25,26 | Director Engineering | MIG | Polokwane Municipality | 10000000 | Appointment of a Contractor,Site establishment and road bed preparartions | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street linked to Excelsior Strret | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading Makanye Road (Ga-Thoka) | N | Makanye | 27 | Director Engineering | CRR | Polokwane Municipality | 9000000 | Construction of Layer works and drainage system | construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of road in Makanye | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of Arterial road in Ga Rampheri | N | Rampheri | 4 | Director Engineering | MIG | Polokwane Municipality | 6500000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of road in Rampheri | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of access roads to Maja Moshate (Molepo Chuene Maja cluster) | N | Chuene | 2 | Director Engineering | MIG | Polokwane Municipality | 9000000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of road in Maja Moshate | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | upgrading of stormwater system in municipal area (Vuk'uphile) | N | municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 1900000 | Handover of site to Learner contractors, site establishment and excavations | Excavations and pipe laying of stormwater units | Finalising of concrete works and cleaning | Project completion | Completion of stormwater culverts | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Rehabilitation of streets in Seshego Cluster | R | Seshego Cluster | 11,12,13,14,17,37 | Director Engineering | CRR | Polokwane Municipality | 4500000 | Handover of site to Learner contractors, site establishment and setting out | Removal and excavation of existing pavement material | Repair base failure and surface failure and new asphalt surfacing | Project completion | Completion of identified street | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 1 | N | Zone 1 | 13 | Director Engineering | CRR | Polokwane Municipality | 8000000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 1 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading Internal Streets in Seshego Zone2 | N | Zone 2 | 17 | Director Engineering | MIG | Polokwane Municipality | 10000000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 2 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 2 | N | Zone 2 | 17 | Director Engineering | CRR | Polokwane Municipality | 4000000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 2 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Triangle Park- land scaping and street lighting Seshego Zone 2 | N | Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 7003000 | Appointment of contractor and site establishment and clearing of site | Construction of fence, installation of lighting, walkways and grassing. | Installation of jungle gyms, outdoor gym and lanscaping. | Project completion | Completion of the triangle park | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 3 | U | Zone 3 | 37 | Director Engineering | CRR | Polokwane Municipality | 8000000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 4 | U | Zone 4 | 12 | Director Engineering | CRR | Polokwane Municipality | 8000000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 4 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 5 | U | Zone 5 | 11 | Director Engineering | CRR | Polokwane Municipality | 1800000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 5 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 5 | U | Zone 5 | 11 | Director Engineering | MIG | Polokwane Municipality | 5500000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 5 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 8 | U | Seshego zone 8 | 11 | Director Engineering | CRR | Polokwane Municipality | 1200000 | Appointmnet of consultant | Scoping report | Prelimenary report and Detailed design report | Tender advert | Tender advert of project | Tender advert
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Seshego Hospital link-Upgrading of township road & Bookelo street | U | Seshego Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 8740000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Seshego Hospital Link | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Construction of stormwater culvert and NMT facilities between skotipola, kgoro and dinkwe | N | Seshego Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 8703000 | Trench excavations for electrical works, cabling, streetlighting, block paving | Landscaping and finishing off and clearing | Project completion | Project completion | Completion of Construction of stormwater culvert and NMT facilities between skotipola, kgoro and dinkwe | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Traffic Lights and Signs (Municipal Wide) | N | municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 3000000 | Detailed design stage and tender advert | Appointment of contractor, Site establishment and exposing exising services | Erection of 1 new signalised traffic lights, and Concret footings for traffic lights and road signs | Project completion | Erection of 1 new signalised traffic lights, and Concret footings for traffic lights and road signs | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Installation of road signage (Municipal Wide) | N | municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 2190000 | Installation of road signage as and when required | Installation of road signage as and when required | Installation of road signage as and when required | Installation of road signage as and when required | Installation of road signage as and when required | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Mohlonong to Kalkspruit upgrading of road from gravel to tar | U | Mohlonong | 40,42 | Director Engineering | MIG | Polokwane Municipality | 7000000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Mohlonong to Kalkspruit upgrading of road from gravel to tar | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Rehabilitation of streets in Municipal Wide(Concession Program) | N | municipal wide | Municipal wide | Director Engineering | LOAN | Polokwane Municipality | 80000000 | Detailed design and appointment of contractor | Site establishment and identification of existing services | Removal and excavation of existing pavement material | Repair base failure and surface failure and new asphalt surfacing | Multiyear project. Completion of phase 1 | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Polokwane Drive- upgrade from single to dual carriage way | U | Lithuli | 12, 13, 14,17 | Director Engineering | NDPG | Polokwane Municipality | 8050000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Continuation of Construction of Layer works and drainage system | Installation of electrical works | Project is a multiyear | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Construction of NMT at Ditlou Str, Freedom Str. Zondi Str, Kgoro, Realeboga and Braam | N | Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 2504000 | Finalising the Construction of layerworks and block paving | Finalising the Construction of layerworks and block paving | Finalising the Construction of layerworks and block paving | Project completion | Completion of NMT at Ditlou Str, Freedom Str. Zondi Str, Kgoro, Realeboga and Braam | Appointment letter, Project progress report, Payment certificate, Completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Roads and Stormwater | Construction of NMT at Magazyn Street and Vermekuwet | N | CBD | City Cluster | Director Engineering | KFWBANK | Polokwane Municipality | 14400000 | Preliminary and detailed design stage | Appointment of contractor, Site establishment and exposing exising services | Construction of layerworks and block paving | Finalising the Construction of layerworks and block paving . Project completion | completion of NMT at Magazyn Street | Appointment letter, Project progress report, Payment certificate, Completion certificate
Total Roads & Stormwater - Engineering
301455000
Water Supply and reticulation - Engineering
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Olifantspoort RWS (Mmotong wa Perekisi) | N | 10, 16,36,37 | 10, 16,36,37 | Director Engineering | MIG |  | 23000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Moletjie East RWS | N | 15, 36, 38 | 15, 36, 38 | Director Engineering | MIG |  | 20000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Sebayeng/Dikgale RWS | N | 29,31,32,33 | 29,31,32,33 | Director Engineering | MIG |  | 17000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Houtriver RWS phase 10 | N | 18,35 | 18,35 | Director Engineering | MIG |  | 10000000 | Approval of technical report and tender advert | Appointment of Contractor, site handover and establishment | excavations and pipe laying, equipping of boreholes. | Finalisation of excavation and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Chuene Maja RWS phase 9 | N | 1,2 | 1,2 | Director Engineering | CRR |  | 2500000 | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Boreholes equipped, pump house, bulk line and distribution line. | project completion | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Molepo RWS phase 10 | N | 1,2 | 1,2 | Director Engineering | MIG |  | 10000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Laastehoop RWS phase 10 | N | 5 | 5 | Director Engineering | MIG |  | 6000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Mankweng RWS phase 10 | N | 27, 25, 31, 7, 26 | 27, 25, 31, 7, 26 | Director Engineering | MIG |  | 15000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Boyne RWS phase 10 | N | 4 | 4 | Director Engineering | MIG |  | 9763000 | Approval of technical report and tender advert | Appointment of Contractor, site handover and establishment | excavations and pipe laying, equipping of boreholes. | Finalisation of excavation and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Water Conservation & Water Demand Management (Installation of Smart Meters) at Mankweng | N | 26 | 26 | Director Engineering | WSIG |  | 10000000 | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Progress report
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Segwasi RWS Planning | N | 28 | 28 | Director Engineering | WSIG |  | 1000000 | Appointment of consultant | Preparation of design reports | Preparation of design reports | Tender advert for appointment of contractor | Tender advert for appointment of contractor | Tender advert
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Badimong RWS phase 10 Planning | N | 28,30, 31, 34 | 28,30, 31, 34 | Director Engineering | WSIG |  | 1000000 | Appointment of consultant | Preparation of design reports | Preparation of design reports | Tender advert for appointment of contractor | Tender advert for appointment of contractor | Tender advert
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Extension 78 water reticulation | N | 8 | 8 | Director Engineering | CRR |  | 665000 | Detailed design presentation | n/a budget insufficient | n/a budget insufficient | Tender advert after confirmation of 19/20 FY budget | Tender advert after confirmation of 19/20 FY budget | Tender advert
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Extension 78 sewer reticulation | N | 8 | 8 | Director Engineering | CRR |  | 665000 | Detailed design presentation | n/a budget insufficient | n/a budget insufficient | Tender advert after confirmation of 19/20 FY budget | Tender advert after confirmation of 19/20 FY budget | Tender advert
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Extension 106 sewer & water reticulation | N | 8 | 8 | Director Engineering | CRR |  | 8500000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. all other water connection. | Continue with excavations and pipe laying. Construction of pump house. all other water connection.Commissioning and issuing completion certificate. | Completion of sewer and water reticulation | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Aganang RWS 1 Planning | N | 40,41,42,43,44 & 45 | 40,41,42,43,44 & 45 | Director Engineering | WSIG |  | 11000000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Aganang RWS 2 | N | 40,41,42,43,44 & 45 | 40,41,42,43,44 & 45 | Director Engineering | CRR |  | 9525000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Asbestos (AC) Pipes in Seshego, Annadale & CBD | N | City and Seshego Cluster | City and Seshego Cluster | Director Engineering | RBIG |  | 83335120 | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections. Installations of PRV | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections. Installations of PRV | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections. Installations of PRV | progress reports, minutes, payment certificates,
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Polokwane Water Network Upgrading (1) | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 4600000 | Appointment of consultant for scoping, designs and procurement | Raplacing inlets control system and refurbishment of outlet pipe manifold in Krugersburg. | Finalisation of Raplacing inlets control system and refurbishment of outlet pipe manifold | Project complete | Refurbished inlets at Krugersburg | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | PolokwanWater Network Upgrading(2) | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 4600000 | Appointment of consultant for scoping, designs and procurement | Refurbishment of pumpstations and pressure control systems in Polokwane | Continuation of Refurbishment of pumpstations and pressure control systems in Polokwane | Phase 1 of project completed | Refurbished pumpstations and pressure control systems in Polokwane | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Polokwane Groundwater development | N | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | WSIG |  | 45600000 | Drilling, testing and equiping of boreholes | N/A | N/A | N/A | N/A | Test certificates and project reports
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Asset Renewals of Water Network (CBD) | R | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 4000000 | Renewals of pipeworks( eg pressure control valves) | Renewals of pipeworks( eg pressure control valves) | Renewals of pipeworks( eg pressure control valves) | Renewals of pipeworks( eg pressure control valves) | Renewals of pipeworks( eg pressure control valves) | Progress report, List of components renewed
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Asset Renewals of Waste Water Network (CBD) | R | 9 19,20,21,22,23 & 39 | 9 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 4000000 | renewal of pump station mechanical and electrical componenets | renewal of pump station mechanical and electrical componenets | renewal of pump station mechanical and electrical componenets | renewal of pump station mechanical and electrical componenets | renewal of pump station mechanical and electrical componenets | Progress report, List of components renewed
| Basic Service Delivery | Increased access to municipal services to all households | Water Supply and Reticulation Programme | Upgrading of pipeline from Dap to Menz | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 950000 | Renewals of pipeworks( eg air valves) | Renewals of pipeworks( eg air valves) | Renewals of pipeworks( eg air valves) | Renewals of pipeworks( eg air valves) | Renewals of pipeworks( eg air valves) | Progress report, List of components renewed
Total Water Supply and reticulation - Engineering
302703120
Sewer Reticulation - Engineering
| Basic Service Delivery | Increased access to municipal services to all households | Sanitation | Regional waste Water treatment plant | N | 9 | 9 | Director Engineering | RBIG |  | 180519880 | Preliminary design stage | Detailed design stage | Tender advert | Appointment of contractor | Project is a multiyear (24 months) | Design reports, tender advert, appointment letter
| Basic Service Delivery | Increased access to municipal services to all households | Sanitation | Regional waste Water treatment plant | N | 11,12,13,14,17,37,08,19,20,21,22,23,39 | 11,12,13,14,17,37,08,19,20,21,22,23,39 | Director Engineering | PLEDGE/RBIG |  | 170000000 | Preliminary design stage | Detailed design stage | Tender advert | Appointment of contractor | Project is a multiyear (24 months) | Design reports, tender advert, appointment letter
| Basic Service Delivery | Increased access to municipal services to all households | Sanitation | Refurbishment of Polokwane Waste Water Treatment Works | R | 11,12,13,14,17,37,08,19,20,21,22,23,39 | 11,12,13,14,17,37,08,19,20,21,22,23,39 | Director Engineering | CRR |  | 41800000 | Continue with the replacement and repair of mechanical and electrical equipment as well as structural repairs to return the WWTW to a functional condition | Continue with the replacement and repair of mechanical and electrical equipment as well as structural repairs to return the WWTW to a functional condition | Continue with the replacement and repair of mechanical and electrical equipment as well as structural repairs to return the WWTW to a functional condition | Conclude project, reports, as-built plans and Operations manual | All elements (inlet, sedimentation tanks, aeration basin, biofilters, and pump stations refurbished. | Progress reports, Site meetings, design reports, quotations as built plans and Maintenance and Operation Plan
Total Sewer Reticulation - Engineering
392319880
Energy Services - Engineering
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Illumination of public areas ( main street into ext40,and75 from Nelson Mandela Voortrekker street , Ext 40 from Matlala road, Ext 71,73 | N | Ext 40 and 75 | 8,14 | Director Engineering | CRR | Polokwane Municipality | 2145000 | Advertise bid, evaluate and appoint contractor | oreder material | plant poles and install cables and lights | Test, commissioning and switching on | 50 street lights installed in the area | Adverts, appointment letters, SLAs, payment certificate
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Illumination of public areas ( High Mast lights) various rural areas | N | Municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 9487500 | Advertise bid, evaluate and appoint contractor | order poles, lights and dig foundations | install poles and lights | Test, commissioning and switching on | 11 High Mast lights installed | Adverts, appointment letters, SLAs, payment certificate
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | SCADA on RTU in Superbia & Epsilon | N | Superbia | 11,12,13, 14,17,37 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 2437500 | Appointment of Contractor, site handover and site establishment. | order materials | install RTUs | Test, commissioning and switching on | 66KV substation connected to SCADA t | Appointment letters, adverts, payment certificate, completion certificate
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Replacement of Fiber glass enclosures in Flora, Fauna Park and NIrvana | N | Flora, Fauna and Nirvana | 19,20,21,22,23, 39 | Director Engineering | CRR | Polokwane Municipality | 9750000 | Advertise bid, evaluate and appoint contractor | order materials, prepare boxes at training centre | replace the fibre enclosures | Test, commissioning and switching on | 300 meter box enclosures replaced | Requisitions, invoices, job cards
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Planning and design New Bakone to IOTA 66KV double circuit GOAT line | N | Bakone SS | 11,12,13, 14,17,37 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 9750000 | Advertise bid, evaluate and appoint contractor | Order materialr | Installation of poles | Poles installed | Poles installed | Quotations for servitudes, minutes, payment certificates
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Build 66KV/Bakone substation | N | Bakone SS | 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 9500000 | Appointment of Contractor, site handover and site establishment. | Prepare civil works and grounds | Build the substation | Test, commissioning and switching on | Install switch gears | Minutes of meetings, Progress report, payment certificates,
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Electrification Of Urban Households in Extension 78 and 40 | N | Ext 78 and 40 | 8 | Director Engineering | CRR | Polokwane Municipality | 5850000 | Advertise bid, evaluate and appoint contractor | Order materialr and plant poles | Stringing and transformer installat | Test, commissioning and switching on | electrified households | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Design and Construct permanent distribution substation at Thornhill | N | Thornhill | 23 | Director Engineering | CRR | Polokwane Municipality | 9750000 | Execute the work | order material | build structure and | install switch gear | completed 11 kv switching substation | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Power factor corrections in various Municipal Substations | N | Municipal wide | 11,12,13, 14,17,37 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 682500 | Consultant appointment, development of bid document and advertise | Evaluate and appoint contractor, site handover and site establishment. | N/A | N/A | N/A | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Plant and Equipment | N | Municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 2500000 | Execute the work | get quotations and orders | purchase | receive items | receive items | Requisitions, invoices, job cards
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Increase license area assets | N | Municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 1000000 | Meetings to negotiate | meetings to negotiate | cost the transfers | report agreements | Execute the work | Requisitions, invoices, job cards
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Replace 66kV Bus Bars & Breakers at Gamma Substation | R | Gamma SS | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 3217500 | Advertise bid, evaluate and appoint contractor | Designs | Designs | Prepare tender documents | Advertise bids | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Replacement of Fences at Gamma, Sigma, Alpha, Beta, Sterpark & Florapark Substations (vuk'uphile) | R | Various Sub Stations | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 975000 | Designs | Appoint contractors | Replace the fences | Test, commissioning and switching on | Evaluate and prepare the following bids | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Upgrade Gamma Substation and install additional 20MVA transformer | U | Gamma SS | 20, 21, 19 | Director Engineering | CRR | Polokwane Municipality | 975000 | Advertise bid, evaluate and appoint contractor | Designs | Advertise tender | Evaluate and award | Build substation | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Design and Construction of New Pietersburg 11kv substation | N | New Pietersburg | 8, 14,19 | Director Engineering | CRR | Polokwane Municipality | 1000000 | Advertise bid, evaluate and appoint contractor | Designs | Construct civil works | Measure and order switch gears | Install switch gears | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Installation of Check Meters at Main substations | N | Various Sub Stations | 8,11,12,13,14,37,37,19,20,21,22,23,39 | Director Engineering | CRR | Polokwane Municipality | 3200000 | Advertise bid, evaluate and appoint contractor | order meters | install meters | Test, commissioning and switching on | report on operations and | Appointment letters, minutes, payment certificates.
| Basic Service Delivery | Increased access to municipal services to all households | Electrification/Energy Programme | Lowering Pole mount boxes to ground mounted in Westernburg, Zone 1 Zone8, Zone5, Ext 71,73,75,9A, 9L | N | Westernburg, Zone 1 Zone8, Zone5, Ext 71,73,75,9A, 9L | 8,11,12,13,14,37,37 | Director Engineering | CRR | Polokwane Municipality | 5850000 | Consultant appointment, development of bid document and advertise | Evaluate and appoint contractor, site handover and site establishment. | order materials | install meters mobexes and transfer meters | test and commission | Appointment letters, minutes, payment certificates.
Total Energy Services - Engineering
78070000
Disaster and Fire - Community Services
| Basic Service Delivery | Improved social protection and education outcomes | Disaster and Fire Programme | Planning for extension of fire training Centre | N | 23 | 23 | Director Community Services | CRR |  | 1000000 | Appoint the consultant to prepare the design report and approval of the design scope | Consultant to submit the drawings for approval by Housing and Building Inspection section. Preparation of bid document and of cost estimate | Advertise tender and appoint contractors | Site handover to the contractor and implementation | Approved drawings
Total Disaster and Fire - Community Services
1000000
Traffic & Licencing - Community Services
| Basic Service Delivery | Improved social protection and education outcomes | Traffic and Licensing | Upgrading of logistics offices | U | Polokwane | City Cluster | Director Community Services | CRR |  | 1000000 | Contractor already on site ( Phase 2 to continue- progress report | Contractor on site | Contractor on site | Project completion and handing over | Conjusive working environment. | Completion certificate
| Basic Service Delivery | Improved social protection and education outcomes | Traffic and Licensing | Upgrading- Traffic Auditorium, parade room and Training Facility | U | Polokwane | City Cluster | Director Community Services | CRR |  | 600000 | Contractor on site | Contractor on site | Contractor on site | Project completion and handing over | Conjusive working environment. | Completion certificate
| Basic Service Delivery | Improved social protection and education outcomes | Traffic and Licensing | Upgrading of city vehicle test station | U | Polokwane | City Cluster | Director Community Services | CRR |  | 500000 | Project specification and bid advertisement. | Awarding processes | Imstallation and renewal of equipments | Payment and Closure | Compliance with Road Traffic Regulations | Completion certificate and Invoice
Total Traffic & Licencing - Community Services
2100000
Environmental Management - Community Services
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Development of a park at Ext 44 and 76 | N | City | 8 | Director Community Services | CRR |  | 600000 | Planting of 30 trees, establishment of 3 flowerbeds. | Drilling and equipping of borehole. Procuring paving bricks and kerbs | Paving and kebing of 3 shade houses each measuring 48 square metres | Complete and usable recreational park | Works orders, Invoices, Delivery notes.
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Upgrading of Security at Game Reserve | U | City | 20 | Director Community Services | CRR |  | 1000000 | Submission of specification for the supply and delivery of (Bonox) game fence .400m perimeter. | Appointment of service provider for the supply and delivery of (Bonox) Game fence | Procurement of material (Bonox) Game fencing) | Implementation of the project ( Fencing) of approximately
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Upgrading of Environmental Education Centre | U | City | 23 | Director Community Services | CRR |  | 750000 | Completion of paving for vehicle parking area. | Provision of the shopping list for teaching aids and educational displays. | Purchasing of teaching aids and educational displays. | Receiving and placing of educational displays and teaching aids | Updated and effective Environmental Education Centre | Invoices, Works orders and educational material
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Construction of ablution facilities at Tom Naude Park | N | City | 22 | Director Community Services | CRR |  | 800000 | Prepare and submit a report to BAC for the appointment of the architect to design Ablution facility | Appointment of the architect to plan, design and determine the Project specification and BOQ for Ablution Facility. | Submission of Layout plans and Design | Appointment of the contractor | Submission of Approved designs and appointment of a contractor | BAC Reports, Appointment letters, Plans and designs, payment certificates
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Development of Ablution facilities at Various Municipal Parks | N |  | 22, 19, 20, 39, 25, 26, 32, 31 | Director Community Services | CRR |  | 500000 | Plans and designs | Plans and designs | Plans and designs | Plans and designs | Plans and designs | ReportsDesigns
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Animal Pound | N |  | Municipal Wide | Director Community Services | CRR |  | 900000 | Submit the report for the establishment of the animal pound to Council | Repair the available sites through annual contractors | Invite proposals from bidders | Operate and manage the animal pound. | An operational animal pound. Lesser roaming animals | Report. Invoices. Appointment letter. SLA
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Upgrading of Ga- Kgoroshi community centre | N |  | 42 | Director Community Services | CRR |  | 500000 | Planting of 20 additional trees, procurement of 90 kerbs | Electrification and kerbing of childrens play area | Drilling and equipping of a borehole. | Connecting electricity to the borehole. | Electrified facility | Invoices, Works orders
Total Environmental Management - Community Services
5050000
Waste Management - Community Services
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Waste Management | Extension of landfill site(weltevrede) | N | Municipal wide | Municipal wide | Director Community Services | CRR |  | 3000000 | Bid specification, approval and advertisement | Bid evaluation, adjudication and awarding | implementatation | implementatation | completed fence | Invoices
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer station ( Sengatane) | N |  | 9 | Director Community Services | MIG |  | 4266667 | construction of the transfer station. Site hand over done on 14 may 2018 | construction of the transfer station | construction of the transfer station | construction and completion | complaeted transfer station | completion certificate and invoices
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer station (Dikgale) | N |  | 24 | Director Community Services | MIG |  | 4266667 | Site hand over and establishment to be done on 28 June 2018. contractor appointed on 25 May 2018 | construction of te transfer station | construction of the transfer station | construction and completion | completed transfer station | completion certificate and invoices
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer Station(Makotopong) | N |  | 28 | Director Community Services | MIG |  | 4266666 | evaluation and awarding | construction | construction | construction | Constructed transfere station | completion and invoices
| Basic Service Delivery | Improved provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer Station Planning (Molepo) | N |  | 1,2,3,4,5 | Director Community Services | CRR |  | 1000000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
Total Waste Management - Community Services
16800000
Sport & Recreation - Community Development
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Construction of Mankweng Sport facility-2 | N | Mankweng | 25 | Director Community Development | MIG |  | 11440000 | Appointment of Service provider,Bulk civil works for roads and parking,finishes for the main pavilion | External buildings,Bulk services installation viz:water,sewerage,external lights and stormwater drainage | Building finishes,seats,soccer pitch and baseball drainage | Refurbishment of old courts(Basketball,netball | Completed roads and parking area;pavilion;completely refurbished basket and netball and netball courts | Appointment letters,Project reports, certificates;pictures
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Sport stadium in Ga-Maja | N | Ga-Maja | 2 | Director Community Development | MIG |  | 9600000 | Fencing;Bulk earthworks for all structures;Combi couts,ablution block;connection of water services | Borehole and septic tank;parking | Start with the construction of the community hall,excavation of the foundation;Construction of the concrete footing;construction of the floor | Construction of a community hall-;construction of the superstructure;Erection of the trusses,laying the roof cover;lighting,painting ;finishing off | Complete combi courts,ablution facility;borehole;septic tank;connection os services;community hall;lighting | Appointment letters,Project reports, certificates;pictures
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | EXT 44/77 Sports and Recreation Facility | N | Ext 44/77 | 8 | Director Community Development | MIG |  | 1500000 | Appointment of consultant, Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Upgrading of Tibane Stadium | U | Tibane | 44 | Director Community Development | CRR |  | 475000 | Procurement of contractor (Tender documents have been prepared) | Upgrading water supply system and providing additional ablution facilities | Project completion and finalisation | NA | Water supply system, tank and ablutions completed | Contract/ SLA/ progress reports, site meeting minutes as-built documents
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Sebayeng/Dikgale Sports Complex (Planning) |  | Sebayeng/Dikgale |  | Director Community Development | CRR |  | 1000000 | Appointment of consultant, Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Rehabilitation of Swimming Pool to be commercialized | R | City | City | Director Community Development | CRR |  | 1575000 | Plant room maintenance and Pumps instalation | Filtration system and completion | N/A | N/A | Rehabilitated swimming pools | Project progress report and pictures
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Upgrading of Mohlonong Stadium | U | Aganang | Aganang | Director Community Development | MIG |  | 7300000 | Construction of Retaining structure, lawns (artificial grass), augmentation of water system and gravel athletics track | Construction of Retaining structure, lawns (artificial grass), augmentation of water system and gravel athletics track | Concluding reporting and documentation, close out report and as-built plans | NA | Functioning water supply system, lawns and athletics track | Contract/ SLA/ progress reports, site meeting minutes as-built documents
Total Sport & Recreation - Community Development
32890000
Security Services - Community Services
| Basic Service Delivery | Improved social protection and education outcomes | Sport & Recreation | Upgrading of offices at Itsoseng for Security Services | N | City | City | Director Community Development | CRR |  | 600000 | specification and advertisement | Evaluate and appoint contractor and site handover . | project implementation | completion of the project | upgraded offices | invoices
Total Security Services - Community Services
600000
#REF!
Information Services - Corporate and Shared Services
| Good Governance and Public Participation | Improved efficiency and effectiveness of Municipal administration | ICT Programme | Implementation of ICT Strategy | N | Municipal wide | Municipal Wide | Director Corporate and Shared Services | CRR |  | 750000 | Finalization of Specification | Service Provider apointment | 50% Implementation of ITIL processes | 100% Implementation ITIL processes | Proper IT Service Management | Project Handover Report
| Good Governance and Public Participation | Improved efficiency and effectiveness of Municipal administration | ICT Programme | Network Upgrade | U | Municipal wide | Municipal Wide | Director Corporate and Shared Services | CRR |  | 7000000 | Appoinment of Service Provider | 30% Implementation | 70% Implementation | 100% Implementation | Reliable connectivity to cluster offices | Project Handover Report
Total Information Services - Corporate and Shared Services
7750000
City Planning - Planning and Economic Development
| Spatial Rationale | Increased economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Township establishment-Farm Volgestruisfontein 667 LS | N | Municipal wide | Municipal wide | Director Planning and Economic Development | CRR |  | 2000000 | Lum Resolution ROD General Plan approval | Lum Resolution ROD General Plan approval | Township Regsiter | Proclamation | Proclaimed Township Serviced Township | LUM Resolution Final Layout ROD Approved General Plan Township Register Proclamation Notice
| Spatial Rationale | Increased economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Township establishment at portion 151-160 of the Farm Sterkloop 688 LS for PHA mixed land use | N | Municipal wide | Municipal wide | Director Planning and Economic Development | CRR |  | 3000000 | Bid Specification approval | Project Advertisement, Evaluation, Adjudication and Appointment letter | Draft Layout CoE Environmental Management Plan Township Application | LUM Resolution Township Layout | Proclaimed Township Serviced Township | LUM Resolution Final Layout ROD Approved General Plan Township Register Proclamation Notice
| Spatial Rationale | Increased economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Township establishment-Portion 74 and 75 of Ivy Dale Agricultural Holdings | N | Municipal wide | Municipal wide | Director Planning and Economic Development | CRR |  | 1000000 | LUM Resolution ROD Approved General Plan | Township Regsiter | Proclamation | Serviced Township | Proclaimed Township Serviced Township | LUM Resolution Final Layout ROD Approved General Plan Township Register Proclamation Notice
| Spatial Rationale | Increased economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Integrated feasibility studies for logistics and Industrial hub | N | Municipal wide | Municipal wide | Director Planning and Economic Development | CRR |  |  | Registration of Notarial Lease | Township Appilcation Advertisements | Draft Layout CoE Environmental Management Plan Township Application | LUM Resolution Township Layout | General Plan approval Township Regsiter | Registered Notarial Lease ROD General Plan Township Register Proclamation Logistic Hub Truck Inn
| Spatial Rationale | Increased economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Planning for Installation of engineering services at Polokwane extension 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 (water, electricity, sewerage network and roads) | N | 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 34 | 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 | Director Planning and Economic Development | CRR |  | 1000000 | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | Township Regsiter
Total City Planning - Planning and Economic Development
7000000
Transport Operations(IPRTS)- Transport and Services
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | AFC | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG |  | 35499000 | Advertisement of tender to procure AFC to be installed in busses | Appointment of service provider | N/A | Operations of leeto la Polokwane system | Appointment letter , SLA of the fare collection service provider | Appointment letter for the service provider, Bid Document, SLA, Advertisement of the Fare Collection Service Provider
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | PTMS | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG |  | 25499000 | Advertisement of tender to procure (PTMS) monitoring system to be installed in busses and control centre | Appointment of Service provider | N/A | Operations of leeto la Polokwane system | Appointment letter , SLA of the fare collection service provider | Appointment letter for the service provider, Bid Document, SLA, Advertisement of the Fare Collection Service Provider
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Control Centre | N | Municipal wide | 20 | Director Transportation Services | PTNG |  | 1500000 | Advertisement of tender to procure (PTMS) monitoring system to be installed in busses and control centre | Install PTMS elements: Server, Video walls | N/A | Operations of leeto la Polokwane system | Appointment letter , SLA of the fare collection service provider | Appointment letter for the service provider, Bid Document, SLA, Advertisement of the Fare Collection Service Provider
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Compensation | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG |  | 62500000 | Engage Industry on Compensation survey results and sign off Compensation Survey Results | Sign off Compensation Offers | Witdrawal of 125 minibus taxis and settle compensation (payment of compensation on withdrawal of Operating Licences) | Not applicable for Quarter 4, as Compensation process is planned to be completed by end of Third Quarter. | Signed Compensation Offers, Settle Compensation and removal of 125 minibus taxis from Phas1 A footprint | Attendance Register, signed Compensation Survey Results, signed Compensation Offers, cancelled Operating Licences and the vehicles or scrapping certificate
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | PT facility upgrade | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG |  | 5750000 | Designs of Taxi Facility upgrades | Appointment of contractor | Construction | Operations | Operations | Operations
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Upgrad & constr of Trunk route 108/2017 WP1 | N |  | 8, 13, 14, 17, 19 | Director Transportation Services | PTNG Pledge |  | 16844000 | Establishment, excavations, mass earthworks, Road layers | Road layer, BT Base, patching and milling on existing lanes, surfacing, kerbing and storm water drainage. | Road markings, Rumble blocks, road signs and finishing | n/a | 0.6km New BRT lanes & rehabilitation of mixed traffic lanes | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Construction of bus depot Civil works 108/2017 WP3 | N |  | 11 | Director Transportation Services | PTNG Pledge |  | 5767000 | Establishment, excavations, mass earthworks, pavement layers, fencing | Installation of stormwater systems, construction of pavement layers and platforms for buildings, concrete paving & kerbing, fencing | n/a | n/a | Fenced Depot site, paved bus parking area with, fueling and washbay facility areas, with stormwater drainage systems | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Construction of bus station Civil works 108/2017 WP4 | N |  | 22 | Director Transportation Services | PTNG Pledge |  | 20476000 | Establishment, excavations, mass earthworks, demolishing of public toilets, pavement layers | Pavement layers, rehabilitation and upgrading of roadways, construction of paving and kerbing | n/a | n/a | Bus lanes, rehabilitated road ways, busstation platforms, paved station precinct | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Construction of bus station Civil works 108/2017 WP4 | N | Municipal wide | Municipal Wide | Director Transportation Services | PTNG |  | 7700000 | Establishment, excavations, mass earthworks, demolishing of public toilets, pavement layers | Pavement layers, rehabilitation and upgrading of roadways, construction of paving and kerbing | n/a | n/a | Bus lanes, rehabilitated road ways, busstation platforms, paved station precinct | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Daytime lay-over 108/2017 WP2 | N | City | City | Director Transportation Services | PTNG Pledge |  | 7792000 | Site establishment, demolishing of existing parking area, excavations, mass earthworks and layerworks, installation of stormwater systems, | Construction of concrete paving and kerbing, perimeter fencing. | n/A | n/a | Provision of secured (fenced) paved parking area. (holding area) with stormwater drainage systems | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | CBD Transit Mall 108/2017 WP4 | N | City | City | Director Transportation Services | PTNG Pledge |  | 10925000 | n/a | Rehabilitation of mixed traffic lanes, construction of que jump lanes at intersections | Rehabilitation of mixed traffic lanes, construction of que jump lanes at intersections. Provision of UTC traffic signals, roadmarkings | n/a | Que jump lanes and UTC systems at intersections, rehabilitated road ways | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Construction & provision of Depot Upper structures |  | City | City | Director Transportation Services | PTNG Pledge |  | 14950000 | n/a | n/a | Foundation Excavations, construction of Maintenance building with service pits, storeroom, fueling and washby floors | Construction of Maintenance building with service pits, storeroom, fueling and washby facilities, temporary offices, restsrooms and guardhouse | Fenced Depot site, paved bus- and staff parking area with Maintenance and storeroom buildings, offices, restrooms, guardhouse, fueling and washbay facilities | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Construction & provision of Station Upperstructures |  | City | City | Director Transportation Services | PTNG |  | 20834000 | n/a | n/a | Construction of 2 module stations structers and roofing | Installation of kiosk, ticket vending machine, server room, turnstiles, office, ablution AFC & APTMS equipment, paving and landscaping. | 2 equiped station modules with office, ablution, fare gates, server room, ticket vending machine, APTMS & AFC equipment, paved station precinct, hawkers facilities, signage & landscaping | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Construction & provision of Station Upperstructures |  | City | City | Director Transportation Services | PTNG Pledge |  | 7916000 | n/a | n/a | Construction of 2 module stations structers and roofing | Installation of kiosk, ticket vending machine, server room, turnstiles, office, ablution AFC & APTMS equipment, paving and landscaping. | 2 equiped station modules with office, ablution, fare gates, server room, ticket vending machine, APTMS & AFC equipment, paved station precinct, hawkers facilities, signage & landscaping | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Refurbishment of Daytime Layover Buildings |  | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 4025000 | n/a | Removal of old interior finishing and equipment. Repaint and tile ablution and admin building, internal walls and drywalling, | Partitioning & Fitment of ablution equipment and furniture. (store room & wash bay) | n/a | Ablution facility, rest rooms, offices, canteen, server room, store room and washbay, parking areas | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | OHS Management Rev2Light | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 1000000 | OHS management - complaince and monitoring | OHS management, complaince and monitoring | OHS management, complaince and monitoring | OHS management, complaince and monitoring | OHS Compliance | Monthly audit reports, close-out report
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Environmental Management Seshego & SDA1 | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 400000 | Environmental Management - compliance and monitoring | Environmental Management - compliance and monitoring | Environmental Management - compliance and monitoring | Environmental Management - compliance and monitoring | Environmental Compliance | Monthly audit reports, close-out report
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Environmental Management in Polokwane City | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 300000 | Environmental Management - compliance and monitoring | Environmental Management - compliance and monitoring | Environmental Management - compliance and monitoring | Environmental Management - compliance and monitoring | Environmental Compliance | Monthly audit reports, close-out report
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Upgrade & rehab of Trunk Ext in Seshego & SDA1 109/2017 | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 8855000 | Establishment, excavations and relocation of services, mass earthworks, installation of stormwater pipe systems | Construction of pavement layers, stormwater drainage, milling of existing road prism, concrete kerbing, surfacing, road markings and road signs & finishing | n/a | n/a | 1.25 km upgraded and widened street section. | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Rehabilitation of Feeder Routes in Polokwane 110/2017 | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 5750000 | Establishment, relocation of services, deep milling of road layers | Completion of road structural layers, prime, surfacing and road markings | n/a | n/a | 1km rehabilitated mixed traffic lanes | Appointment letter, site meeting minutes, progress reports
| Basic Service Delivery | Increased access to municipal services to all households | Transportation Services | Acquisition of buses | N | Municipal wide | Municipal wide | Director Transportation Services | PTISG Pledge |  | 165000000 | Appointment of the Service provider | Testing of the bus operations through station,laybuys | Implementation of the bus schedule operations | Operation of the bus schedule operations by Vehicle Operating Company (VOC) | Leeto la Polokwane operating from CBD to Seshego, Flora Park and Westerburg | Bus Schedule, Approved Routes, VOC Contract, SLA for the supply and delivery of the busses
Total Transport Operations(IPRTS)- Transport and Services
429282000
Supply Chain Management - Budget and Treasury Services
| Financial Viability | Improved efficiency and effectiveness of Municipal administration | Supply chain management | Upgrading of stores | U | City | City | Chief Financial Officer | CRR |  | 8500000 | Site handover to contractor, Site establishment. | Upgrading of Building 2 main entrance and offices. | Construction of Boundary wall and Guard house, Construction of new Warehouse | Completion of works | Upgrading of Building 2 main entrance and offices.Construction of Boundary wall and Guard house, Construction of new Warehouse. | Appointment letter, site meeting minutes, progress reports
Total Supply Chain Management - Budget and Treasury Services
|  |  |  | Total Capital Expenditure | GT | [5 empty] | 8500000

## APPROVAL
SDBIP APPROVAL