## COVER
REVISED TOP-LAYER SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP) 2018/19

## INTRODUCTION
INTRODUCTION | Polokwane Municipality Council approved that the Budget can be adjusted downward after considering the 2018-19 Mid-Year Budget and Performance Assessment. Council will use the Revised 2018/19 SDBIP performance indicators and targets, as a monitoring tool for the implementation of the IDP objectives and Adjustment Budget. The Revised SDBIP will be effective from the Third Quarter until the Fourth Quarter of the 2018/2019 financial year.
LEGISLATION FRAMEWORK | Section 54 (1) (c) of the MFMA states that the Mayor may consider and if necessary, make any revisions to the Service Delivery and Budget Implementation Plan, provided the revisions to the Service Delivery targets and performance indicators in the Plan may only be made with the approval of the Council following approval of an Adjustment Budget.
SDBIP METHODOLOGY | The IDP objectives need to be quantified and translated into key performance indicators. The budget is then aligned to the objectives, projects and activities to enable the SDBIP to serve as a monitoring tool for service delivery. The SDBIP is a layered plan that comprises the top layer as well as the lower layer SDBIP. The top layer deals with consolidated service delivery targets and time frames for top management, whereas the lower layer consists of detailed outputs that are broken down into smaller outputs and then linked and assigned to middle and lower managers. The following are the minimum required components of a top-layer SDBIP: (a) Monthly projections of revenue to be collected for each source (b) Monthly projections of expenditure (operating and capital) and revenue for each vote (c) Quarterly projections of service delivery targets and performance indicators for each vote (d) Ward information for expenditure and service delivery (e) Detailed capital works plan broken down by ward over three years The diagram below shows the process for approving the SDBIP including how the departmental SDBIPs roll up into the draft SDBIP:
POLOKWANE MUNICIPALITY STRATEGIC INTENT AND OBJECTIVES | Vision “The Ultimate in Innovation and Sustainable Development” Mission “Provide cost effective services which promote sustainable livelihood through socio economic development and good governance” Value Statement "Sustainable Development through Responsive Innovation" Values • Sustainable Development • Innovation • Responsiveness
POLOKWANE MUNICIPALITY SERVICE DELIVERY PRIORITIES | • Provision of basic services, which include electricity provision, water and sanitation and refuse removal • Strengthen the local economic development structures and expansion of expanded public works programme • Upgrading of informal settlements and promotion of sustainable human settlements • Overhaul of ageing service delivery infrastructure and maintenance of municipal facilities • Improving transport, roads and bridges • Improving sports and recreational facilities and promotion of social cohesion • Development of municipal capacity to manage disaster risk and protection of environment • Ensure long-term planning capacity, monitoring and evaluation • Promotion of sound financial management to ensure financial sustainability • Promotion of good governance and the participation of local communities in the municipal affairs
POLOKWANE MUNICIPALITY’S IDP STRATEGIC OBJECTIVES | • To ensure efficiency and effectiveness of Municipal administration • To ensure the provision of basic and environmental services in a sustainable way to our communities • To ensure social protection and education outcomes • Promotion of economic growth ,job creation and Sustainable human settlement • To ensure community confidence in the system of local government • To enhance Financial Viability and Financial Management
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN REPORTING CYCLE | The Service Delivery and Budget Implementation Plan is a management tool that will be used by the Executive Management Committee to monitor institutional performance, departmental performance, SBU performance and individual performance of employees. The Service Delivery and Budget Implementation Plan will be used by Mayoral Committee and Council to play oversight on the performance of the municipality and will be used as the basis of reporting municipal performance to the community of Polokwane and all interested stakeholders. It will serve as a early warning system for poor performance and will allow for timeous intervention to correct poor performance. The reporting cycle of this Service Delivery and Budget Implementation Plan is aligned to the Council approved PMS Framework and the PMS Policy. Reporting will be done:

## FINANCIAL PROJECTIONS
LIM354 Polokwane - Supporting Table SB12 Adjustments Budget - monthly revenue and expenditure (municipal vote) - feb 2018
Description | Ref | Budget Year 2018/19 | [12 empty] | Medium Term Revenue and Expenditure Framework
|  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Full year budget | Budget Year 2018/19 | Budget Year +1 2019/20 | Budget Year +2 2020/21
R thousands |  | Outcome | Outcome | Outcome | Outcome | Outcome | Outcome | Adjusted Budget | Adjusted Budget | Adjusted Budget | Adjusted Budget | Adjusted Budget | Adjusted Budget |  | Adjusted Budget | Adjusted Budget | Adjusted Budget
R thousands
Revenue by Vote |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 1 - Council |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 2 - Office of the Municipal Manger |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 3 - Strategic Planning Monitoring and Evaluation |  | 65708359.73 | 124298882.14 | 103596554.08 | 93926845.48 | 114094602.8 | 106479422.44 | 89557542.63 | 85258000 | 138133000 | 133957000 | 86280000 | -1141290209.3 | 0 | 0 | 0 | 0
Vote 4 - Engineering Services |  | 17494277.96 | 22257286.79 | 19405580.06 | 18639676.58 | 18393741.01 | 11835982.87 | 20485159.19 | 10307000 | 16699000 | 16194000 | 10430000 | 1365835791.54 | 1547977496 | 1547977496 | 1651620000 | 1813480000
Vote 5 - Community Services |  | 128075.47 | 1570323.41 | 401149.31 | 161566.93 | 566912.81 | 791340.92 | 307823.67 | 646000 | 1046000 | 1015000 | 654000 | 182525807.48 | 189814000 | 189814000 | 195736000 | 208682000
Vote 6 - Community Development |  | 0 | 0 | 0 | 0 | 590898.14 | 0 | 3217391.32 | 299000 | 484000 | 470000 | 203000 | 6268710.54 | 11533000 | 11533000 | 12191000 | 12889000
Vote 7 - Corporate and Shared Services |  | 1563934.37 | 2093998.52 | 1097713.81 | 790430.44 | 2160773.9 | 3920378.26 | 2132173.62 | 3292000 | 5333000 | 5172000 | 3331000 | -25553402.92 | 5334000 | 5334000 | 5654000 | 5994000
Vote 8 - Planning and Economic Development |  | 135559909.1833 | 275253215.724 | 187894558.208 | 203504808.074 | 213184544.8745 | 277471707.9803 | 205735860.4547 | 229702659 | 239253659 | 278027659 | 273678659 | -2460466240.4988 | 58801000 | 58801000 | 62112000 | 65714000
Vote 9 - Budget and Treasury | [12 empty] | 2683231504 |  | 2683231504 | 2990715000 | 3312497000
Vote 10 - Transport Operations | [12 empty] | 0 |  | 0 | 0 | 0
Vote 11 - [NAME OF VOTE 11] | [12 empty] | 0 |  | 0 | 0 | 0
Vote 12 - [NAME OF VOTE 12] | [12 empty] | 0 |  | 0 | 0 | 0
Vote 13 - [NAME OF VOTE 13] | [12 empty] | 0 |  | 0 | 0 | 0
Vote 14 - [NAME OF VOTE 14] | [12 empty] | 0 | 0 | 0 | 0 | 0
Vote 15 - [NAME OF VOTE 15] |  | 220454556.7133 | 425473706.584 | 312395555.468 | 317023327.504 | 348991473.5345 | 400498832.4703 | 321435950.8847 | 329504659 | 400948659 | 434835659 | 374576659 | 610551960.8412 | 1813459496 | 4496691000 | 4918028000 | 5419256000
0
Expenditure by Vote |  | 24696732.8622 | 26199924.5336 | 26931385.847 | 25837792.4338 | 26965864.6869 | 27155887.5164 | 27397000 | 25902000 | 26994000 | 27042000 | 27452000 | -292574587.88 | 0 | 0 | 0 | 0
Vote 1 - Council |  | 1381299.5524 | 2331674.8692 | 1918428.1472 | 6501439.6847 | 3879548.041 | 1834975.5154 | 3941000 | 3726000 | 3883000 | 3890000 | 3949000 | 267312334.19 | 304548700 | 304548700 | 361417000 | 413746600
Vote 2 - Office of the Municipal Manger |  | 2032669.6457 | 5279034.134 | 5137725.7187 | 6017883.3421 | 5540683.5173 | 5358021.7122 | 5867000 | 5547000 | 5781000 | 5791000 | 5879000 | -12192718.07 | 46038300 | 46038300 | 33879200 | 35960600
Vote 3 - Strategic Planning Monitoring and Evaluation |  | 101401680.7236 | 141261232.9854 | 123430050.2367 | 124468804.5765 | 116198519.5973 | 114034374.1606 | 87802843.5862 | 166699658.0048 | 160632658.0048 | 160368658.0048 | 158088658.0048 | -1376313707.8853 | 78073430 | 78073430 | 39740400 | 44194300
Vote 4 - Engineering Services |  | 23388849.3352 | 37332487.07 | 34398045.4852 | 37775769.4982 | 34832306.8479 | 42016652.1734 | 35345000 | 33416000 | 34825000 | 34886000 | 35416000 | 1072040089.59 | 1455672200 | 1455672200 | 1585843300 | 1661916500
Vote 5 - Community Services |  | 10018754.3985 | 19742554.1673 | 15576664.1785 | 19881388.3778 | 11584570.6796 | 12795885.0882 | 15102000 | 14278000 | 14880000 | 14906000 | 15132000 | 287154840.11 | 451052657 | 451052657 | 458005600 | 489658300
Vote 6 - Community Development |  | 8573855.1124 | 16407846.3445 | 14867228.493 | 16922385.7925 | 20225990.9246 | 15079097.693 | 17608000 | 16647000 | 17349000 | 17380000 | 17643000 | 18134395.64 | 196837800 | 196837800 | 204505300 | 216666900
Vote 7 - Corporate and Shared Services |  | 4271170.6966 | 4791644.401 | 4535609.5299 | 5381797.4414 | 4747536.0813 | 4806760.5298 | 5906000 | 5583000 | 5819000 | 5829000 | 5917000 | 178835981.32 | 236424500 | 236424500 | 238456100 | 252889300
Vote 8 - Planning and Economic Development |  | 13646508.4038 | 45735475.5843 | 35408264.3656 | 63415665.0011 | 26214302.0615 | 64922330.4638 | 36410000 | 34423000 | 35874000 | 35937000 | 36483000 | -355549845.88 | 72919700 | 72919700 | 74045800 | 78494400
Vote 9 - Budget and Treasury |  | 789784.1363 | 827956.4673 | 990331.1848 | 6459992.7785 | 3788715.0893 | 5385120.4738 | 4632000 | 4379000 | 4563000 | 4571000 | 4641000 | 466948876.87 | 507976777 | 507976777 | 514158500 | 527646200
Vote 10 - Transport Operations | [12 empty] | 56804900 | 56804900 | 56804900 | 0 | 0
Vote 11 - [NAME OF VOTE 11] | [12 empty] | 0 | 0 | 0 | 43379200 | 41064900
Vote 12 - [NAME OF VOTE 12] | [12 empty] | 0 | 0 | 0 | 0 | 0
Vote 13 - [NAME OF VOTE 13] | [12 empty] | 0 | 0 | 0 | 0 | 0
Vote 14 - [NAME OF VOTE 14] | [12 empty] | 0 | 0 | 0 | 0 | 0
Total Expenditure by Vote |  | 190201304.8667 | 299909830.5567 | 263193733.1867 | 312662918.9267 | 253978037.5267 | 293389105.3267 | 240010843.5862 | 310600658.0048 | 310600658.0048 | 310600658.0048 | 310600658.0048 | 310600558.0048 | 3406348964 | 3406348964 | 3553430400 | 3762238000
Surplus/ (Deficit) |  | 30253251.8467 | 125563876.0273 | 49201822.2813 | 4360408.5773 | 95013436.0079 | 107109727.1436 | 81425107.2984 | 18904000.9952 | 90348000.9952 | 124235000.9952 | 63976000.9952 | 299951402.8365 | -1592889468 | 1090342036 | 1364597600 | 1657018000
References
1. Surplus (Deficit) must reconcile with budget table A2 and monthly budget statement table C2
LIM354 Polokwane - Supporting Table SB14 Adjustments Budget - monthly revenue and expenditure - feb 2018
Description | Ref | Budget Year 2018/19 | [12 empty] | Medium Term Revenue and Expenditure Framework
|  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Full year budget | Budget Year 2018/19 | Budget Year +1 2019/20 | Budget Year +2 2020/21
R thousands |  | Outcome | Outcome | Outcome | Outcome | Outcome | Outcome | Adjusted Budget | Adjusted Budget | Adjusted Budget | Adjusted Budget | Adjusted Budget | Adjusted Budget |  | Adjusted Budget | Adjusted Budget | Adjusted Budget
Revenue By Source
Property rates |  | 34892785.82 | 34296636.5 | 34285040.85 | 34288761.81 | 34295774.6 | 35678825.51 | 34514874.92 | 25832000 | 41852000 | 35586000 | 46141000 | 698678235.99 | 1090341936 | 1090341936 | 1364597600 | 1657018000
Service charges - electricity revenue |  | 70756682.11 | 93656307.26 | 72431047.88 | 62578614.99 | 45271425.52 | 109077293.47 | 98937688.79 | 99051000 | 95672000 | 92779000 | 99758000 | -939969060.02 | 0 | 0 | 0 | 0
Service charges - water revenue |  | 20443153.07 | 20251836.39 | 18584516.82 | 20830176.83 | 21751332.43 | 22935059.88 | 23007764.73 | 13907000 | 22532000 | 21851000 | 14074000 | -220167840.15 | 0 | 0 | 0 | 0
Service charges - sanitation revenue |  | 8380776.28 | 9382888.37 | 9510809.94 | 9381145.4 | 9355704.18 | 9359303.85 | 10395842.78 | 5739000 | 9299000 | 9017000 | 5808000 | -95629470.8 | 0 | 0 | 0 | 0
Service charges - refuse |  | 9305210.34 | 9291214.13 | 9434628.73 | 10789047.72 | 10424721.35 | 10422673.42 | 9257276.92 | 8323000 | 10244000 | 10934000 | 10398000 | -108823772.61 | 0 | 0 | 0 | 0
Service charges - other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment |  | 19770.79 | 2368782.42 | 2015211.47 | 1066669.36 | 1126572.54 | 755902.68 | 1136248 | 2088000 | 3383000 | 3281000 | 2113000 | -19354157.26 | 0 | 0 | 0 | 0
Interest earned - external investments |  | 863786.7 | 1834645.45 | 1819028.08 | 1267454.72 | 0 | 0 | 0 | 2647000 | 4288000 | 4159000 | 2679000 | -19557914.95 | 0 | 0 | 0 | 0
Interest earned - outstanding debtors |  | 1798685.12 | 1496824.87 | 2092543.27 | 2261732.74 | 7796224.75 | 3589098 | 6673776 | 4478000 | 7256000 | 7036000 | 4532000 | -49010884.75 | 0 | 0 | 0 | 0
Dividends received |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines, penalties and forfeits |  | 491762.35 | 272787.57 | 6244318.9 | 1355250 | 433257.33 | 5364331.21 | 268000 | 257659 | 367659 | 367659 | 367659 | -15790343.36 | 0 | 0 | 0 | 0
Licences and permits |  | 759175.34 | 859233.25 | 782855.6 | 906472.99 | 2174452 | 1879080 | 2479934 | 834000 | 1351000 | 1310000 | 844000 | -14180203.18 | 0 | 0 | 0 | 0
Agency services |  | 1519873.69 | 2045113.574 | 1499596.308 | 1846154.844 | 6201679 | 5575341 | 8245907 | 1400000 | 2268000 | 2199000 | 1417000 | -34217665.416 | 0 | 0 | 0 | 0
Transfers and subsidies |  | 69712733.5433 | 75458945 | 82960656.58 | 79447089.22 | 86790255.2973 | 76935827.0899 | 78820576.4648 | 96467000 | 91485000 | 88719000 | 57143000 | 3612750916.8047 | 4496691000 | 4496691000 | 4918029000 | 5419258000
Other revenue |  | 1510161.56 | 70433744.8 | 7472425.2 | 9066165.72 | 3312437 | 4061059 | 7359135.47 | 23787000 | 38539000 | 87374000 | 84072000 | -336987128.75 | 0 | 0 | 0 | 0
Gains on disposal of PPE |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue |  | 220454556.7133 | 321648959.584 | 249132679.628 | 235084736.344 | 228933835.9973 | 285633795.1099 | 281097025.0748 | 284810659 | 328536659 | 364612659 | 329346659 | 2457740711.5487 | 5587032936 | 5587032936 | 6282626600 | 7076276000
Expenditure By Type
Employee related costs |  | 58263528.56 | 58425100.18 | 58891068.28 | 74717907.63 | 62976360.89 | 61894810.54 | 65301580.93 | 82439259.998 | 82439259.998 | 82439259.998 | 82439259.998 | -770227397.002 | 0 | 0 | 0 | 0
Remuneration of councillors |  | 3052953.18 | 3053737.84 | 3073758.99 | 3053719.56 | 3151973.97 | 3053008.95 | 3121615.32 | 3791446.438 | 3791446.438 | 3791446.438 | 3791446.438 | -36726553.562 | 0 | 0 | 0 | 0
Debt impairment |  | 19583333.3333 | 19583333.3333 | 19583333.3333 | 19583333.3333 | 19583333.3333 | 19583333.3333 | 19583333.3333 | 12583333.3333 | 12583333.3333 | 12583333.3333 | 12583333.3333 | -187416666.6667 | 0 | 0 | 0 | 0
Depreciation & asset impairment |  | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | 15833333.3333 | -174166666.6667 | 0 | 0 | 0 | 0
Finance charges |  | 2146779.73 | 0 | 0 | 0 | 0 | 0 | 6023000 | 14866044.054 | 14866044.054 | 14866044.054 | 14866044.054 | -67633955.946 | 0 | 0 | 0 | 0
Bulk purchases |  | 74756416.8 | 91638548.82 | 67688448.18 | 63479988.5 | 63984433 | 71819989.17 | 57254415.6696 | 77974951.9721 | 77974951.9721 | 77974951.9721 | 77974951.9721 | -802522048.0279 | 0 | 0 | 0 | 0
Other materials |  | 0 | 12430523.41 | 2674327.05 | 5526579.18 | 2551062 | 2400603 | 2539370 | 2228688.472 | 2228688.472 | 2228688.472 | 2228688.472 | -37037218.528 | 0 | 0 | 0 | 0
Contracted services |  | 11804396.4 | 67452985.96 | 81693055.94 | 118114995.87 | 68230551 | 103468630 | 54333766 | 77236923.766 | 77236923.766 | 77236923.766 | 77236923.766 | -814046076.234 | 0 | 0 | 0 | 0
Grants and subsidies |  | 0 | 1070000 | 1030000 | 40000 | 1030000 | 990000 | 480000 | 1372000 | 1372000 | 1372000 | 1372000 | -10128000 | 0 | 0 | 0 | 0
Other expenditure |  | 4760563.53 | 30422267.68 | 12726408.08 | 12313061.52 | 16636990 | 14345397 | 15540429 | 22274676.638 | 22274676.638 | 22274676.638 | 22274676.638 | -195843823.362 | 0 | 0 | 0 | 0
Loss on disposal of PPE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenditure |  | 190201304.8667 | 299909830.5567 | 263193733.1867 | 312662918.9267 | 253978037.5267 | 293389105.3267 | 240010843.5862 | 310600658.0048 | 310600658.0048 | 310600658.0048 | 310600658.0048 | -3095748405.9953 | 0 | 0 | 0 | 0
Surplus/(Deficit) |  | 30253251.8467 | 21739129.0273 | -14061053.5587 | -77578182.5827 | -25044201.5294 | -7755310.2168 | 41086181.4885 | -25789999.0048 | 17936000.9952 | 54012000.9952 | 18746000.9952 | 5553489117.544 | 5587032936 | 5587032936 | 6282626600 | 7076276000
Transfers and subsidies - capital (monetary allocations) (National / Provincial and District) |  | 0 | 103824747 | 63262875.84 | 81938591.16 | 120057637.5373 | 114865037.3603 | 40338925.8099 | 44694000 | 72412000 | 70223000 | 45230000 | -756846814.7075 |  | 0 | 0 | 0
Transfers and subsidies - capital (monetary allocations) (National / Provincial Departmental Agencies, Households, Non-profit Institutions, Private Enterprises, Public Corporatons, Higher Educational Institutions) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Transfers and subsidies - capital (in-kind - all) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Surplus/(Deficit) after capital transfers & contributions |  | 30253251.8467 | 125563876.0273 | 49201822.2813 | 4360408.5773 | 95013436.0079 | 107109727.1436 | 81425107.2984 | 18904000.9952 | 90348000.9952 | 124235000.9952 | 63976000.9952 | 4796642302.8365 | 5587032936 | 5587032936 | 6282626600 | 7076276000
References
1. Surplus (Deficit) must reconcile with budget table A4 and monthly budget statement table C4
[15 empty] | 5587032936 | 6282626600 | 7076276000

## CAPITAL WORKS PLAN
Project Number | Project Name/Description | Type of Project - New/Renewal | Project Location | Ward No. | Sources of Funding | Implementing Agent | Original Budget | Revised Budget
Clusters - SPME
CWP_01 | Thusong Service Centre (TSC) -Mankweng (Acquisition of land in Mankweng for the construction of TSC) | R | Mankweng | Mankweng Cluster | CRR | Polokwane Municipality | 1000000 | 1000000
Total Clusters - SPME
1000000
Facility Management- Community Development
CWP_03 | Civic Centre refurbishment | R | Polokwane | Pcity Cluster | CRR | Polokwane Municipality | 4000000 | 6 000 000
CWP_04 | Renovation of municipal wide offices | R | Polokwane | Pcity Cluster | CRR | Polokwane Municipality | 1500000 | 2 800 000
CWP_05 | Municipal Furniture and Office Equipment | N | Polokwane | Pcity Cluster | CRR | Polokwane Municipality | 500000 | 1 000 000
CWP_06 | Refurbishment of City Library and Auditorium | R | Polokwane | 20 | CRR | Polokwane Municipality | 500000 | 484 996
CWP_07 | Upgrading of Seshego Library | R | Seshego | 17 | CRR | Polokwane Municipality | 500000 | 500 000
CWP_08 | Library Dikgale | N | Dikgale | 32 | CRR | Polokwane Municipality | 500000 | 300 000
CWP_09 | Library Bloodriver /Perskebult | N | Bloodriver /Perskebult | 10 | CRR | Polokwane Municipality | 300000 | 300 000
CWP_10 | Civic Centre Aircon Upgrade | N | Polokwane | 20 | CRR | Polokwane Municipality | 1000000 | 985 837
CWP_11 | Construction of Mankweng Water and Sanitation Centre | N | Mankweng | 25 | CRR | Polokwane Municipality | 1000000 | _
Total Facility Management- Community Development
9800000
Control Centre Services - Community Services
CWP_12 | Installation of CCTV cameras | N |  |  | CRR | Polokwane Municipality | 1700000 | 1 700 000
CWP_13 | Hand held radios | N |  |  | CRR | Polokwane Municipality | 100000 | 99 202
CWP_14 | Access Control | N |  |  | CRR | Polokwane Municipality | 227000 | 227 000
Total Control Centre Services - Community Services
2027000
Roads & Stormwater - Engineering
CWP_15 | Chebeng to Makweya internal streets | N | Makweya | 9 | MIG | Polokwane Municipality | 4000000 | 6 200 000
CWP_16 | Sebayeng ring road (Upgrading from gravel to Asphalt) | N | Sebayeng | 32 | MIG | Polokwane Municipality | 2600000 | 4 330 000
CWP_17 | Tarring of Arterial road in SDA1 (Lithuli and Madiba park) | N | Lithuli | 14 | MIG | Polokwane Municipality | 13000000 | 15 000 000
CWP_18 | Tarring Ntsime to Sefateng (Phase 2 and 3) | N | Ntsime | 31 | MIG | Polokwane Municipality | 10000000 | 10 137 000
CWP_19 | Upgrading Semenya to Matekereng | N | Semenya | 38 | MIG | Polokwane Municipality | 11000000 | 4 553 422
CWP_22 | Upgrading of Ramongoana bus and Taxi roads | N | Ramongwana | 38 | MIG | Polokwane Municipality | 3500000 | 3 500 000
CWP_23 | Upgrading of Ntshitshane Road | N | Ntshitshane | 6, 31 | MIG | Polokwane Municipality | 7000000 | 10 681 000
CWP_24 | Tarring of internal streets in Toronto | N | Toronto | 25 | MIG | Polokwane Municipality | 10000000 | 15 400 000
CWP_25 | Upgrading of internal Streets in Mankweng unit E (Vuk'uphile) | N | unit E | 25 | CRR | Polokwane Municipality | 1140000 | 1 140 000
CWP_26 | Upgrading of internal streets linked with Excelsior Street in Mankweng unit A | N | Mankweng | 25,26 | MIG | Polokwane Municipality | 10000000 | 16 500 000
CWP_27 | Upgrading Makanye Road (Ga-Thoka) | N | Makanye | 27 | CRR | Polokwane Municipality | 9000000 | 9 000 000
CWP_28 | Upgrading of Arterial road in Ga Rampheri | N | Rampheri | 4 | MIG | Polokwane Municipality | 6500000 | 6 500 000
CWP_29 | Upgrading of access roads to Maja Moshate (Molepo Chuene Maja cluster) | N | Chuene | 2 | MIG | Polokwane Municipality | 9000000 | 10 970 000
CWP_30 | upgrading of stormwater system in municipal area (Vuk'uphile) | N | municipal wide | Municipal wide | CRR | Polokwane Municipality | 1900000 | 1 900 000
CWP_31 | Rehabilitation of streets in Seshego Cluster | R | Seshego Cluster | 11,12,13,14,17,37 | CRR | Polokwane Municipality | 4500000 | 4 500 000
CWP_32 | Upgrading of internal streets in Seshego Zone 1 | N | Zone 1 | 13 | CRR | Polokwane Municipality | 8000000 | 8 000 000
CWP_33 | Upgrading Internal Streets in Seshego Zone2 | N | Zone 2 | 17 | MIG | Polokwane Municipality | 10000000 | 10 000 000
CWP_34 | Upgrading of internal streets in Seshego Zone 2 | N | Zone 2 | 17 | CRR | Polokwane Municipality | 4000000 | 4 000 000
CWP_35 | Triangle Park- land scaping and street lighting Seshego Zone 2 | N | Zone 2 | 17 | NDPG | Polokwane Municipality | 7003000 | 8 431 700
CWP_36 | Upgrading of internal streets in Seshego Zone 3 | U | Zone 3 | 37 | CRR | Polokwane Municipality | 8000000 | 5 000 000
CWP_37 | Upgrading of internal streets in Seshego Zone 4 | U | Zone 4 | 12 | CRR | Polokwane Municipality | 8000000 | 8 000 000
CWP_39 | Upgrading of internal streets in Seshego Zone 5 | U | Zone 5 | 11 | MIG | Polokwane Municipality | 5500000 | 5 500 000
CWP_40 | Upgrading of internal streets in Seshego Zone 8 (Planning) | U | Seshego zone 8 | 11 | CRR | Polokwane Municipality | 1200000 | 1 200 000
CWP_41 | Seshego Hospital link-Upgrading of township road & Bookelo street | U | Seshego Zone 2 | 17 | NDPG | Polokwane Municipality | 8740000 | 6 742 683
CWP_42 | Construction of stormwater culvert and NMT facilities between skotipola, kgoro and dinkwe | N | Seshego Zone 2 | 17 | NDPG | Polokwane Municipality | 8703000 | 9 136 717
CWP_43 | Traffic Lights and Signs (Municipal Wide) | N | municipal wide | Municipal wide | CRR | Polokwane Municipality | 3000000 | 3 000 000
CWP_45 | Mohlonong to Kalkspruit upgrading of road from gravel to tar | U | Mohlonong | 40,42 | MIG | Polokwane Municipality | 7000000 | 5 000 000
CWP_46 | Rehabilitation of streets in Municipal Wide (Concession Program) | N | municipal wide | Municipal wide | LOAN | Polokwane Municipality | 80000000 | 20 000 000
CWP_47 | Polokwane Drive- upgrade from single to dual carriage way | U | Lithuli | 12, 13, 14,17 | NDPG | Polokwane Municipality | 8050000 | 10 222 420
CWP_49 | Construction of NMT at Magazyn Street and Vermekuwet (Planning and design) | N | CBD | City Cluster | KFWBANK | Polokwane Municipality | 14400000 | 2 504 000
Total Roads & Stormwater - Engineering
284736000
Water Supply and reticulation - Engineering
CWP_50 | Olifantspoort RWS (Mmotong wa Perekisi) | N | 10, 16,36,37 | 10, 16,36,37 | MIG | Polokwane Municipality | 23000000 | 23 000 000
CWP_51 | Moletjie East RWS | N | 15, 36, 38 | 15, 36, 38 | MIG | Polokwane Municipality | 20000000 | 20 000 000
CWP_52 | Sebayeng/Dikgale RWS | N | 29,31,32,33 | 29,31,32,33 | MIG | Polokwane Municipality | 17000000 | 22 900 000
CWP_53 | Houtriver RWS phase 10 | N | 18,35 | 18,35 | MIG | Polokwane Municipality | 10000000 | 10 000 000
CWP_54 | Chuene Maja RWS phase 9 | N | 1,2 | 1,2 | CRR | Polokwane Municipality | 2500000 | 3 250 000
CWP_55 | Molepo RWS phase 10 | N | 1,2 | 1,2 | MIG | Polokwane Municipality | 10000000 | 14 000 000
CWP_56 | Laastehoop RWS phase 10 | N | 5 | 5 | MIG | Polokwane Municipality | 6000000 | 8 500 000
CWP_57 | Mankweng RWS phase 10 | N | 27, 25, 31, 7, 26 | 27, 25, 31, 7, 26 | MIG | Polokwane Municipality | 15000000 | 18 300 000
CWP_58 | Boyne RWS phase 10 | N | 4 | 4 | MIG | Polokwane Municipality | 9763000 | 6 763 000
CWP_59 | Water Conservation & Water Demand Management (Installation of Smart Meters) at Mankweng | N | 26 | 26 | WSIG | Polokwane Municipality | 10000000 | 10 000 000
CWP_60 | Segwasi RWS Planning | N | 28 | 28 | WSIG | Polokwane Municipality | 1000000 | 1 000 000
CWP_61 | Badimong RWS phase 10 Planning | N | 28,30, 31, 34 | 28,30, 31, 34 | WSIG | Polokwane Municipality | 1000000 | 1 000 000
CWP_63 | Extension 78 sewer reticulation | N | 8 | 8 | CRR | Polokwane Municipality | 665000 | _
CWP_64 | Extension 106 sewer & water reticulation | N | 8 | 8 | CRR | Polokwane Municipality | 8500000 | 1 100 000
CWP_65 | Aganang RWS 1 Planning (Juno, Kordon and Farlie) | N | 40,41,42,43,44 & 45 | 40,41,42,43,44 & 45 | WSIG | Polokwane Municipality | 11000000 | 11 000 000
CWP_66 | Aganang RWS 2 (Mahoai and Ceres) | N | 40,41,42,43,44 & 45 | 40,41,42,43,44 & 45 | CRR | Polokwane Municipality | 9525000 | 9 525 000
CWP_67 | Asbestos (AC) Pipes in Seshego, Annadale & CBD | N | City and Seshego Cluster | City and Seshego Cluster | RBIG | Polokwane Municipality | 83335120 | 210 159 624
CWP_68 | Polokwane Water Network Upgrading (1) | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | CRR | Polokwane Municipality | 4600000 | 4 600 000
CWP_69 | PolokwanWater Network Upgrading(2) | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | CRR | Polokwane Municipality | 4600000 | 4 600 000
CWP_70 | Polokwane Groundwater development | N | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | WSIG | Polokwane Municipality | 45600000 | 45 600 000
Total Water Supply and reticulation - Engineering
293088120
Sewer Reticulation - Engineering
CWP_74 | Regional waste Water treatment plant | N | 9 | 9 | RBIG | Polokwane Municipality | 180519880 | 133 842 880
CWP_75 | Regional waste Water treatment plant | N | 11,12,13,14,17,37,08,19,20,21,22,23,39 | 11,12,13,14,17,37,08,19,20,21,22,23,39 | PLEDGE/RBIG | Polokwane Municipality | 170000000 | 170 000 000
CWP_76 | Refurbishment of Polokwane Waste Water Treatment Works | R | 11,12,13,14,17,37,08,19,20,21,22,23,39 | 11,12,13,14,17,37,08,19,20,21,22,23,39 | CRR | Polokwane Municipality | 41800000 | 41 800 000
Total Sewer Reticulation - Engineering
392319880
Energy Services - Engineering
CWP_77 | Illumination of public areas ( main street into ext40,and75 from Nelson Mandela Voortrekker street , Ext 40 from Matlala road, Ext 71,73 | N | Ext 40 and 75 | 8,14 | CRR | Polokwane Municipality | 2145000 | 2 145 000
CWP_78 | Illumination of public areas ( High Mast lights) various rural areas | N | Municipal wide | Municipal wide | CRR | Polokwane Municipality | 9487500 | 9 487 500
CWP_79 | SCADA on RTU in Superbia & Epsilon | N | Superbia | 11,12,13, 14,17,37 19,20,21,22,23 | CRR | Polokwane Municipality | 2437500 | 2 437 500
CWP_80 | Replacement of Fiber glass enclosures in Flora, Fauna Park and NIrvana | N | Flora, Fauna and Nirvana | 19,20,21,22,23, 39 | CRR | Polokwane Municipality | 9750000 | 6 750 000
CWP_81 | Planning and design New Bakone to IOTA 66KV double circuit GOAT line | N | Bakone SS | 11,12,13, 14,17,37 19,20,21,22,23 | CRR | Polokwane Municipality | 9750000 | 2 750 000
CWP_82 | Build 66KV/Bakone substation | N | Bakone SS | 19,20,21,22,23 | CRR | Polokwane Municipality | 9500000 | 3 000 000
CWP_83 | Electrification Of Urban Households in Extension 78 and 40 | N | Ext 78 and 40 | 8 | CRR | Polokwane Municipality | 5850000 | 1 000 000
CWP_84 | Design and Construct permanent distribution substation at Thornhill | N | Thornhill | 23 | CRR | Polokwane Municipality | 9750000 | 9 750 000
CWP_85 | Power factor corrections in various Municipal Substations | N | Municipal wide | 11,12,13, 14,17,37 19,20,21,22,23 | CRR | Polokwane Municipality | 682500 | _
CWP_86 | Plant and Equipment | N | Municipal wide | Municipal wide | CRR | Polokwane Municipality | 2500000 | 2 500 000
CWP_87 | Increase license area assets (Feasibility study to increase license area) | N | Municipal wide | Municipal wide | CRR | Polokwane Municipality | 1000000 | 1 000 000
CWP_88 | Replace 66kV Bus Bars & Breakers at Gamma Substation | R | Gamma SS | Municipal wide | CRR | Polokwane Municipality | 3217500 | 3 217 500
CWP_89 | Replacement of Fences at Sterpark & Florapark Substations (vuk'uphile) | R | Various Sub Stations | Municipal wide | CRR | Polokwane Municipality | 975000 | 975 000
CWP_90 | Upgrade Gamma Substation and install additional 20MVA transformer (Design) | U | Gamma SS | 20, 21, 19 | CRR | Polokwane Municipality | 975000 | 975 000
CWP_91 | Design and Construction of New Pietersburg 11kv substation | N | New Pietersburg | 8, 14,19 | CRR | Polokwane Municipality | 1000000 | 1 000 000
CWP_92 | Installation of Check Meters at Main substations (Beta, Alpha and Three wheeling points) | N | Various Sub Stations | 8,11,12,13,14,37,37,19,20,21,22,23,39 | CRR | Polokwane Municipality | 3200000 | 2 000 000
CWP_93 | Lowering Pole mount boxes to ground mounted in Westernburg and Zone 1 Ext | N | Westernburg and Zone 1 Ext | 8,11,12,13,14,37,37 | CRR | Polokwane Municipality | 5850000 | 1 850 000
Total Energy Services - Engineering
78070000
Disaster and Fire - Community Services
CWP_94 | Planning for extension of fire training Centre | N | 23 | 23 | CRR | Polokwane Municipality | 1000000 | 1 000 000
Total Disaster and Fire - Community Services
1000000
Traffic & Licencing - Community Services
CWP_95 | Upgrading of logistics offices | U | Polokwane | City Cluster | CRR | Polokwane Municipality | 1000000 | _
CWP_96 | Upgrading- Traffic Auditorium, parade room and Training Facility | U | Polokwane | City Cluster | CRR | Polokwane Municipality | 600000 | 600 000
CWP_97 | Upgrading of city vehicle test station (Installation of play detector) | U | Polokwane | City Cluster | CRR | Polokwane Municipality | 500000 | 500 000
Total Traffic & Licencing - Community Services
2100000
Environmental Management - Community Services
CWP_98 | Development of a park at Ext 44 and 76 | N | City | 8 | CRR | Polokwane Municipality | 600000 | 600 000
CWP_99 | Upgrading of Security at Game Reserve | U | City | 20 | CRR | Polokwane Municipality | 1000000 | 1 000 000
CWP_100 | Upgrading of Environmental Education Centre | U | City | 23 | CRR | Polokwane Municipality | 750000 | 750 000
CWP_101 | Construction of ablution facilities at Tom Naude Park | N | City | 22 | CRR | Polokwane Municipality | 800000 | 400 000
CWP_102 | Development of Ablution facilities at Various Municipal Parks | N |  | 22, 19, 20, 39, 25, 26, 32, 31 | CRR | Polokwane Municipality | 500000 | 500 000
CWP_103 | Animal Pound ( Ga-Kgoroshi and Laboria) | N |  | Municipal Wide | CRR | Polokwane Municipality | 900000 | 900 000
CWP_104 | Upgrading of Ga- Kgoroshi community centre | N |  | 42 | CRR | Polokwane Municipality | 500000 | 500 000
Total Environmental Management - Community Services
5050000
Waste Management - Community Services
CWP_105 | Extension of landfill site(weltevrede) - (Feasibility study to extend the Landfill site) | N | Municipal wide | Municipal wide | CRR | Polokwane Municipality | 3000000 | 3 000 000
CWP_106 | Rural transfer station ( Sengatane) | N |  | 9 | MIG | Polokwane Municipality | 4266667 | 3 800 091
CWP_107 | Rural transfer station (Dikgale) | N |  | 24 | MIG | Polokwane Municipality | 4266667 | 4 999 719
CWP_108 | Rural transfer Station(Makotopong) | N |  | 28 | MIG | Polokwane Municipality | 4266666 | 3 000 000
CWP_109 | Rural transfer Station Planning (Molepo) | N |  | 1,2,3,4,5 | CRR | Polokwane Municipality | 1000000 | 1 000 000
Total Waste Management - Community Services
16800000
Sport & Recreation - Community Development
CWP_110 | Construction of Mankweng Sport facility-2 | N | Mankweng | 25 | MIG | Polokwane Municipality | 11440000 | 3 000 000
CWP_111 | Sport stadium in Ga-Maja | N | Ga-Maja | 2 | MIG | Polokwane Municipality | 9600000 | 8 000 000
CWP_112 | EXT 44/77 Sports and Recreation Facility | N | Ext 44/77 | 8 | MIG | Polokwane Municipality | 1500000 | 1 000 000
CWP_113 | Upgrading of Tibane Stadium | U | Tibane | 44 | CRR | Polokwane Municipality | 475000 | 475 000
CWP_114 | Sebayeng/Dikgale Sports Complex (Planning) |  | Sebayeng/Dikgale |  | CRR | Polokwane Municipality | 1000000 | 1 000 000
CWP_115 | Rehabilitation of Swimming Pool to be commercialized | R | City | City | CRR | Polokwane Municipality | 1575000 | 1 575 000
CWP_116 | Upgrading of Mohlonong Stadium | U | Aganang | Aganang | MIG | Polokwane Municipality | 7300000 | 6 400 000
Total Sport & Recreation - Community Development | [5 empty] | Polokwane Municipality
[6 empty] | Polokwane Municipality | 32890000
Security Services - Community Services | [5 empty] | Polokwane Municipality
CWP_117 | Upgrading of offices at Itsoseng for Security Services | N | City | City | CRR | Polokwane Municipality | 600000
Total Security Services - Community Services | [5 empty] | Polokwane Municipality
[6 empty] | Polokwane Municipality | 600000
Information Services - Corporate and Shared Services | [5 empty] | Polokwane Municipality
CWP_118 | Implementation of ICT Strategy (Upgrading of Council Chambers by installing translation devices) | N | Municipal wide | Municipal Wide | CRR | Polokwane Municipality | 2700000 | 2 700 000
CWP_119 | Network Upgrade (Reliable network connectivity to cluster offices) | U | Municipal wide | Municipal Wide | CRR | Polokwane Municipality | 4000000 | 4 000 000
Total Information Services - Corporate and Shared Services | [5 empty] | Polokwane Municipality
[6 empty] | Polokwane Municipality | 6700000
City Planning - Planning and Economic Development | [5 empty] | Polokwane Municipality
CWP_120 | Township establishment-Farm Volgestruisfontein 667 LS | N | Municipal wide | Municipal wide | CRR | Polokwane Municipality | 2000000 | 2 000 000
CWP_122 | Township establishment-Portion 74 and 75 of Ivy Dale Agricultural Holdings | N | Municipal wide | Municipal wide | CRR | Polokwane Municipality | 1000000 | 1 000 000
CWP_124 | Planning for Installation of engineering services at Polokwane extension 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 (water, electricity, sewerage network and roads) | N | 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 34 | 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 | CRR | Polokwane Municipality | 1000000 | 1 000 000
Total City Planning - Planning and Economic Development | [5 empty] | Polokwane Municipality
[6 empty] | Polokwane Municipality | 4000000
Transport Operations(IPRTS)- Transport and Services | [5 empty] | Polokwane Municipality
CWP_127 | Control Centre | N | Municipal wide | 20 | PTNG | Polokwane Municipality | 1500000 | 1 500 000
CWP_129 | Public Transport facility upgrade (Pick n Pay and City Center facility) | N | Municipal wide | Municipal wide | PTNG | Polokwane Municipality | 5750000 | 5 750 000
CWP_130 | Upgrad & constr of Trunk route 108/2017 WP1 (Nelson Mandela Road) | N |  | 8, 13, 14, 17, 19 | PTNG Pledge | Polokwane Municipality | 16844000 | 16 844 000
CWP_131 | Construction of bus depot Civil works 108/2017 WP3 (Seshego Zone 8) Upgrad & constr of Trunk route 108/2017 WP1 (Nelso+E180 |  |  | 11 | PTNG Pledge | Polokwane Municipality | 5767000 | 5 767 000
CWP_132 | Construction of bus station Civil works 108/2017 WP4 (General Joubert) | N |  | 22 | PTNG Pledge | Polokwane Municipality | 20476000 | 20 476 000
CWP_133 | Construction of bus station Civil works 108/2017 WP4 | N | Municipal wide | Municipal Wide | PTNG | Polokwane Municipality | 7700000 | 7 700 000
CWP_134 | Daytime lay-over 108/2017 WP2 (Itsoseng) | N | City | City | PTNG Pledge | Polokwane Municipality | 7792000 | 7 792 000
CWP_135 | CBD Transit Mall 108/2017 WP4 | N | City | City | PTNG Pledge | Polokwane Municipality | 10925000 | 10 925 000
CWP_136 | Construction & provision of Depot Upper structuresm |  | City | City | PTNG Pledge | Polokwane Municipality | 14950000 | 14 950 000
CWP_137 | Construction & provision of Station Upperstructures |  | City | City | PTNG | Polokwane Municipality | 20834000 | 20 834 000
CWP_138 | Construction & provision of Station Upperstructures |  | City | City | PTNG Pledge | Polokwane Municipality | 7916000 | 7 916 000
CWP_139 | Refurbishment of Daytime Layover Buildings |  | Municipal wide | Municipal wide | PTNG Pledge | Polokwane Municipality | 4025000 | 4 025 000
CWP_143 | Upgrade & rehab of Trunk Ext in Seshego & SDA1 109/2017 | N | Municipal wide | Municipal wide | PTNG Pledge (Seshego Zone 1) | Polokwane Municipality | 8855000 | 8 855 000
CWP_144 | Rehabilitation of Feeder Routes in Polokwane 110/2017 | N | Municipal wide | Municipal wide | PTNG Pledge (Thabo Mbeki) | Polokwane Municipality | 5750000 | 5 750 000
Total Transport Operations(IPRTS)- Transport and Services | [5 empty] | Polokwane Municipality
[6 empty] | Polokwane Municipality | 139084000
Supply Chain Management - Budget and Treasury Services
CWP_146 | Upgrading of stores | U | City | City | CRR | Polokwane Municipality | 8500000 | 8 500 000

## BSD
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Total Number of HH/Denominator (CS 2016) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
BSD_TL01 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Energy | Increase electricity capacity by: building substations and install underground cables | Number of new substations built by 30 June 2019 | # | N/A | 1 | 2 | n/a | n/a | n/a | 2 | Progress reports and Completion certificates
BSD_TL02 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Energy | Increase electricity capacity by: - building substations and install underground cables | Kilometre of underground cables installed by 30 June 2019 | km | N/A | New | 4 | n/a | n/a | n/a | 4 | Progress reports and Completion certificates
BSD_TL03 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Energy (BTO) | Expanding smart metering | Number of new smart meters installed by 30 June 2019 | # | N/A | 6000 | 2000 installation of extra smart meters | 500 | 500 | 500 | 500 | Progress reports and Completion certificates
BSD_TL04 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Energy | Households with access to electricity | Increase percentage of Households with access to electrification by 0.99% (2367) by 30 June 2019. | % | 239116 | 95.6% (1419 HH) | 0.99% (2367) | n/a | n/a | n/a | 0.99% (2367) | Progress reports and Completion certificates
BSD_TL05 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Energy | number of retrofits done to reduce consumption | Percentage Electricity reduction consumption losses by 30 June 2019. Difference between electricity purchased and electricity sold | % | N/A | 950 retrofitted street lights | 1300 retrofitted street lights- | 0 | 200 | 500 | 600 | Electricity reduction assesment report
BSD_TL06 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Sanitation | Upgrade existing Polokwane waste water plant | Increase percentage of Households with access to sanitation by 1.15% (2745) by 30 June 2019 | % | 239116 | Approximately 2350 VIP toilets. 59.5% (142274 HH) | 1.15% (2745) [510 & 490 - Sebayeng; 617 - Chuene/Maja; 600 - Mankweng; 528 Moletjie] |  |  |  | 1.15% (2745) [510 & 490 - Sebayeng; 617 - Chuene/Maja; 600 - Mankweng; 528 Moletjie] | Progress reports and Completion certificates
BSD_TL07 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Water | Replace old existing asbestos cement pipes that is causing water loss | Kilometre of old asbestos cement pipes replaced by 30 June 2019 | km | N/A | Replaced at least 100km asbestos pipes. | 46 | 36.25 | 36.25 | 8 | 14 | Progress reports and Completion certificates
BSD_TL08 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Water | Replacement of old water meters in the city | Number of old water meters replaced in the city by 30 June 2019 | # | N/A | 22 000 Meters replaced. | 15 000 | 3750 | 3750 | 3750 | 3750 | Progress reports and Completion certificates
BSD_TL09 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Water | Increase existing water sources - Oliphant’s, Ebenezer, Molepo, Seshego, Hout River, Dap Naude (increase water treatment plant). | Planning for ML capacity of water treatment plants increased by 30 June 2019 | Ml | N/A | New | Planning and approved designs | n/a | n/a | n/a | Planning and approved designs | Planning and approved designs
BSD_TL10 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Water | Increase existing boreholes by development of new bore holes. | Number of new boreholes developed (drilled and equipped) by 30 June 2019 | 198 | N/A | New | 66 | n/a | n/a | n/a | 66 | Progress reports and Completion certificates
BSD_TL11 | Service Delivery | Smart living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Water | Increase access to water supply. | Increase percentage of Households with access to Water by 0.75% (1800HH) by 30 June 2019 | % | 239116 | Access to water supply. 82.3% (196792 HH) | 0.75% (1800HH) | n/a | n/a | n/a | 0.75% (1800HH) | Progress reports and Completion certificates
BSD_TL12 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transport, Roads and storm water | Implement MIG programme. Increase allocation per financial year to allow quick reduction of backlog | Km of roads upgraded from gravel to tar by 30 June 2019 | km | N/A | 13 | 40 | n/a | n/a | n/a | 40 | Progress reports and Completion certificates
BSD_TL15 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Fleet Management | Review fleet contract upon expiry | Percentage availability of municipality service delivery fleet vehicles for operational purpose (fleet availability norm is 75%) by 30 June 2019 | # | N/A | 75% | 85% | 85% | 85% | 85% | 85% | Fleet reports
BSD_TL17 | Service Delivery | Smart Environment | Development of municipal capacity to manager disaster risk and protection of environment | To ensure provision of basic and environmental services in a sustainable way to our communities | Community Health | Obtain authorization from Capricorn District Municipality to render the service on their behalf | Number of Health (Food premises and outlets) Inspections conducted by 30 June 2019 | # | N/A | 1540 | 1540 | 385 | 385 | 385 | 385 | Food premises and outlets) Inspections reports
BSD_TL18 | Service Delivery | Smart Living | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Waste Management | Address Waste Management backlog in rural areas. | Number of rural villages provided with once a week waste removal services by 30 June 2019 | # | N/A | 18 | 18 | n/a | n/a | n/a | 18 | Waste Management Monthly reports, Waste Management Operational Routes.
BSD_TL19 | Service Delivery | Smart Environment | Provision of basic services, which include electricity, water, sanitation and refuse removal | To ensure provision of basic and environmental services in a sustainable way to our communities | Waste Management | To promote recycling and ensure that waste generated is managed and disposed of in an environmentally friendly manner | Percent of Households with access to waste removal services by 0.08% (200 HH) by 30 June 2019 | % | 239116 | 43.07% (102987) | 0.08% (200 HH) | n/a | n/a | n/a | 0.08% (200 HH) | Waste Management Monthly reports, Waste Management Operational Routes.
BSD_TL20 | Service Delivery | Smart Environment | Development of municipal capacity to manage disaster risk and protection of environment | To ensure provision of basic and environmental services in a sustainable way | Disaster Management and Fire Services | Conduct Hazard identification and assessment programme. | Review Disaster Management Plan (Annual review) by 30 June 2019 | # | N/A | 1 Disaster Management Plan reviewed by 30 June | 1 Disaster Management Plan reviewed by 30 June | na | n/a | n/a | 1 Disaster Management Plan reviewed by 30 June | Reviewed and approved Disaster Management Plan, Council resolution and minutes
BSD_TL21 | Service Delivery | Smart Environment | Development of municipal capacity to manage disaster risk and protection of environment | To ensure provision of basic and environmental services in a sustainable way to our communities | Disaster Management and Fire Services | Conduct reblading programme. | Km fire break reblading conducted by 30 June 2019 | km | N/A | 2600 km | 1100km (244 farms) | n/a | n/a | n/a | 1100km (244 farms) | Progress reports and Completion certificates
BSD_TL22 | Service Delivery | Smart Mobility | Improving transport, roads and bridges | Promotion of economic growth, job creation and sustainable human settlements | Transportation (Infrastructure) | Plan and construct infrastructure | Km of Trunk route constructed by 30 June 2019 | km | N/A | 3.85 | 0.65 | n/a | n/a | n/a | 0.65 | Progress reports and Completion certificates

## GGPP
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
GGPP_TL01 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | IDP | Ensure involvement and participation of all stakeholders | Number of IDP, Budget and PMS Rep Forums held by 30 June 2019 | # | 2 | 2 | n/a | 1 | 1 | n/a | IDP Rep Forum Notices, Agenda and Attendance Registers
GGPP_TL02 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure community confidence in the system of local government | IDP | Facilitate and monitor the identified needs falling without the municipality's mandate | Approval of the current financial year IDP, Budget and PMS Schedule (Process Plan) by 30 August 2018 (S21 of the MFMA) | # | 1 | 1 | 1 | n/a | n/a | n/a | Council Resolution on IDP, Budget and PMS Process Plan
GGPP_TL03 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure community confidence in the system of local government | IDP | Ensure involvement and participation of all stakeholders | Number of IDP, Budget and PMS Steering Committee Meeting held by 30 June 2019 | # | 3 | 3 | 1 | n/a | 1 | 1 | IDP, Budget and PMS Steering Committee Notices and Agenda, Minutes and Attendance Registers
GGPP_TL04 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure community confidence in the system of local government | IDP | To ensure budgeting processes are informed by community needs and priorities by 2018 | Submitting the next financial year Final IDP and Budget to Council for adoption by 31 May 2019 (One month before the start of the new financial year) | # | 1 | 1 | n/a | n/a | n/a | 1 | Council Resolution on the 2019/20 Final IDP
GGPP_TL05 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | PMS | Communicate and share performance information | Tabling Draft Annual Report for previous financial year to Council by 31 January 2019. (s121 - 129 MFMA) | Date | 2018-01-31 | 2019-01-31 | n/a | n/a | 2019-01-31 | n/a | Council Resolution on Draft Annual Report for 2017/18 financial year
GGPP_TL06 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | PMS | Communicate and share performance information | Number of Quarterly Performance Reports submitted to Council in line with MFMA S52 (d), by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Council Resolution on Quarterly Performance Reports and Quarterly Reports
GGPP_TL07 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | PMS | Communicate and share performance information | Tabling the Oversight Report on the previous financial year Annual Report to Council by 31 March 2019 (Section 121-129 MFMA) | Date | 2018-03-31 | 2019-03-31 | n/a | n/a | 2019-03-31 | n/a | Council Approved Oversight Report on the 2017/18 Annual Report
GGPP_TL08 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | ICT | Continuous improvement of Corporate Governance of and Governance of ICT | Number ICT Steering Committee meeting held by 30 June 2019 | # | New | 3 | 1 | 1 | 0 | 1 | Invitations, Agenda, Minutes and Attendance Registers
GGPP_TL09 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure community confidence in the system of local government | ICT | Continuous improvement of Corporate Governance of and Governance of ICT | Number of quarterly reports on the performance of ICT Service providers by 30 June 2019 | # | New | 3 | 1 | 1 | 0 | 1 | ICT Assessment reports and Minutes
GGPP_TL10 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Legal | Review and implement delegations of powers to ensure that all managers act and take decisions within their scope | Annual review of the Delegations of powers to ensure effective administration by 30 June 2019 | # | New | Reviewed delegations of powers by 31 Aug 2018 | Reviewed delegations of powers by 31 Aug 2018 | n/a | n/a | Reviewed delegations of powers by 30 June 2019 | Council Approved Delegation of Powers
GGPP_TL11 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Secretariat Services | Ensuring that Mayoral Committee meetings are convened as per cooperate calendar. | Number of Mayoral Committee meetings scheduled and convened by 30 June 2019 | # | 10 | 10 | 3 | 3 | 2 | 2 | Council Approved Corporate Calendar of meetings. Mayoral Committee notices, Agendas, and Attendance Registers
GGPP_TL12 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Secretariat Services | Ensuring that Council meetings are convened as per cooperate calendar. | Number of Council sittings scheduled and convened by 30 June 2019 (In line with the provisions of MSA) | # | 4 | 4 | 1 | 1 | 1 | 1 | Council Meeting Notices, Agenda and Minutes
GGPP_TL13 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Secretariat Services | Ensuring that Portfolio meetings are convened as per cooperate calendar. | Number of Portfolio Committee meetings scheduled and convened by 30 June 2019 | # | 130 | 130 | 33 | 32 | 33 | 32 | Council Approved Corporate Calendar of meetings. Portfolio Committee Notices, Agendas, Minutes and Attendance Registers
GGPP_TL14 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Human Resources/ Labour Relations | Monitor the corporate calendar. | Number of Local Labour Forum meetings convened and held by 30 June 2019 | # | 10 | 10 | 3 | 2 | 2 | 3 | LLF Notices, Agendas, Minutes and Attendance Registers
GGPP_TL15 | Good Governance and Public Participation | Smart Governance | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Assest Management | Develop integrated long term asset management plan | Integrated long term asset management plan developed by 30 June 2019 | # | 1 | 1 | 1 | n/a | n/a | n/a | Council Approved Long Term Asset Plan
GGPP_TL16 | Good Governance and Public Participation | Smart Governance |  |  | Assest Management | Develop integrated long term asset management plan | Conduct municipal wide asset register verification in line with GRAP standards by 31 August 2018 | # | 1 | 1 | 1 | n/a | n/a | n/a | GRAP Compliant Asset Register
GGPP_TL17 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure social protection and education outcomes | Special Focus | Liaise with the Department of Health and developmental partners to reduce HIV. Establish Ward AIDS Councils. Implement the 90/90/90/ Fast track Strategy for municipalities to reduce HIV By 2020 | Number of Ward AIDS Councils established by 30 June 2019 | # | 12 | 45 | 45 | n/a | n/a | n/a | Ward AIDS Council Reports and Establishment Notice
GGPP_TL18 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Internal Audit | Cooperating closely with other external oversight bodies to better coordinate oversight activities with a view to providing effective audit coverage and minimising any overlaps | Development of the External and Internal Audit Tracking Register for previous financial year AG Report by 5 February 2019 | # | 1 | 1 | n/a | n/a | 1 | n/a | Approved Internal and External AG Tracking Register
GGPP_TL19 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Internal Audit | Communicate effectively with management to receive effective feedback on the preparation and reporting on the implementation of audit work plans | Adoption of Annual Internal Audit Plan and 3 year rolling strategic plan by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Council Approved Annual Internal Audit Plan for 2018/19
GGPP_TL20 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Internal Audit | Regular review and improving the quality of audit reports by increasing the use of available information technology tool to gather, analyse and present factual data to enhance the accuracy, completeness and tidiness of audit reports | Number of Audit Committee Meetings scheduled and convened in terms of the adopted schedule by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Audit Committee Notices, Agendas and Minutes
GGPP_TL21 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Public Participation | Increase functionality and effectiveness of ward committee structures | Number of Ward Committee meetings scheduled and convened per ward by 30 June 2019 (Functionality of ward committees) | # | 540 | 540 | 135 | 135 | 135 | 135 | Ward Committee Reports, Mihutes and Notices of meetings
GGPP_TL22 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Public Participation | Increase functionality and effectiveness of ward committee structures | Number of Ward Committee Reports developed and submitted to Council by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Council Resolutions on Ward Committee Reports
GGPP_TL23 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Roll-out of risk management services within all levels of the municipalities by identifying potentials risks within the municipality | Number of risk assessments conducted by 30 June 2019 | # | 40 | 45 | n/a | n/a | 45 | n/a | Invitation, Agenda and Minutes
GGPP_TL24 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Creating fraud culture in y and Promote Fraud Hotline in the Municipal area | Number of Fraud awareness Campaign held conducted by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Risk Awareness Campaigns notices and Attendance Registers
GGPP_TL25 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Incorporate Risk Management in the IDP and Budgeting process by identifying strategic risk and budgeting for mitigation action | Reviewal of institutional strategic risk register by 30 June 2019 | # | 1 | 1 | n/a | n/a | 1 | n/a | Reviewed and Approved Risk Register
GGPP_TL26 | Good Governance and Public Participation | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Risk Management | Increase functionality, effectiveness and accountability of Risk Management at Directors level | Number of Risk Management Committee scheduled and convened by 30 June 2019 | # | 4 | 4 | 1 | 1 | 1 | 1 | Risk Management Notices, Agenda and Minutes

## MTOD
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
MTOD_TL01 | Municipal Transformation and Organisational Development | Smart People |  | To ensure efficiency and effectiveness of municipal administration | Occupational Health and Safety | Expand OHS capacity | Conduct OHS audit by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | OHS Audit Report
MTOD_TL02 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Build capacity of employees through training | Submission of Reviewed of WSP to LGSETA by 30 April 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Signed and Dated WSP
MTOD_TL03 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Targeted recruitment | Submission of Employment Equity Plan to the Department of Labour by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Submission letter and Signed EE Plan
MTOD_TL04 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Targeted awarding of bursary | Number of new External Students awarded study bursaries for the next academic year by 30th June 2019 (Mayors Bursary) | # | 40 | 10 | n/a | n/a | n/a | 10 | Register of External Students with the ID numbers and bursaries enrolled for, Bursary Contracts
MTOD_TL05 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Build capacity of municipal officials and the community on skills. | Number of Graduate students awarded Internships/Experimental/Learnership at Polokwane Municipality by the 30 June 2019 | # | 150 | 60 | n/a | n/a | n/a | 60 | List of Students and their details with the names of internships awarded to them
MTOD_TL06 | Municipal Transformation and Organisational Development | Smart People | Ensure long-term planning capacity, monitoring and evaluation | To ensure efficiency and effectiveness of municipal administration | Human Resources Management | Build capacity of municipal officials around IR matters | Number of training on application and understanding of code of conduct for all employees by 30 June 2019 | # | 2 | 2 | 1 | n/a | n/a | 1 | Code of Conduct Training Notice, Attendance Register

## LED
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
LED_TL01 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | LED | Sustainable Livelihoods | Number of street traders capacitated through municipal sponsored training by June 2019 | # | New | 180 | 30 | 45 | 50 | 55 | List of street traders capacited and program attended. Reports, Pictures, ID Copies
LED_TL02 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | EPWP | Sustainable Livelihoods | Number of job opportunities created through the EPWP by 30 June 2019 (Temporary Job Opportunities) | # | 3525 | 4249 | 700 (Cummulative) | 2000 (Cummulative) | 3500 (Cummulative) | 4249 (Cummulative) | Copy of EPWP Job Creation report submitted to DPW
LED_TL03 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | LED - SMMEs | Assist SMME to attend exhibitions | Number of exhibition/Flee Markets facilitated by the municipality 30 June 2019 | # | New | 12 | 3 | 3 | 3 | 3 | Exhibition reports Attendance Registers and pictures
LED_TL04 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | Economic Development | Implement Tourism strategy | Number of tourism and investment promotion trade shows attended by 30 June 2019 | # | New | 8 | 3 | 1 | 3 | 1 | List of trade shows attend. Reports on events
LED_TL05 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | Economic Development | Promote the creation of sustainable jobs | Number of job opportunities created through Municipal sponsored trading | # | New | 160 | 30 | 60 | 50 | 40 | Reports and Attendance register, ID Copies
LED_TL06 | Local Economic Development | Smart Economy | Strengthen the local economic development structures and expansion of expanded public works programme | Promotion of economic growth, job creation and sustainable human settlements | Economic Development | Skills audit and training of SMMEs | Number of Workshops/Trainning organised by the municipality in partnerships with sector partners offered to SMME's by 30 June 2019 | # | New | 16 | 4 | 4 | 4 | 4 | Number of workshops and trainings attended. Incubation:- (List of SMME incubated and the programme attended. Reports on SMME Incubation, Lease agreements, Pictures) Start Ups: (Reports Attendance register,ID copies and Pictures ) SMME: (Data base, Reports,Pictures, Proof of Business Registration)

## FV
KPI No | KPA | Pillar | Municipal IDP Priority | IDP Strategic Objective | Municipal Programme | Operating Strategy | Key Performance Indicator (KPI) | Unit of Measure (UoM) | Performance Baseline 2017/18 | Annual Target 2018/19 | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun) | Portfolio of Evidence
FV_TL01 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Budget and Reporting | Improve internal and integrated financial reporting processes to ensure all SBU's are using accurate financial information | Development of the Audit Action Plan for the current financial year AG Report by 31 January 2019 | # | 1 | 1 | n/a | n/a | 1 | n/a | Executive Management Approved AG Audit Action Plan for the 2017/18 AG Report
FV_TL02 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Budget and Reporting | Improve internal and integrated financial reporting processes to ensure all SBU's are using accurate financial information | Municipal compliance to MSCOA budget by 30 June2019 | % | None | 100% | 100% | 100% | 100% | 100% | MSCOA Budget Compliant Report
FV_TL03 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Expenditure Management | Accurate cash flow planning (SBUs to supply cash flow projections on projects at the beginning of each financial year) | Timeous payment of all the creditors with 30 days upon receipt of invoice | % | 100% | 100% | 100% | 100% | 100% | 100% | Section 71 Report (Creditors Age Analysis)
FV_TL04 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Budget and Reporting | To build up reserves (sinking funds) to pay back loans and asset replacement funds | Number of reserve to be established by 30 June 2019 | # | 1 | 1 | n/a | n/a | n/a | 1 | Invest Report
FV_TL05 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Revenue Management | Develop and enforce business processes and procedures | Percentage of Households with access to free basic services to all qualifying households in the municipal's area of jurisdiction | # | 30000 | 100% | 100% | 100% | 100% | 100% | Indigent Register and details of Indigent Benefiaries
FV_TL06 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Revenue Management | Develop and enforce business processes and procedures | Percentage collection of current revenue billed vs total collected. | % | 85% | 86% | 86% | 86% | 86% | 86% | Revenue Report
FV_TL07 | Financial Viability | Smart Governance | Promotion of good governance and the participation of local communities in the municipal affairs | To ensure efficiency and effectiveness of municipal administration | Supply Chain Management | Follow up and adherence to demand management plan | Timeous appointment of service providers within 90 days in line with the National Treasury Norm on appointment of contractors | % | 100% | 100% | 100% | 100% | 100% | 100% | Demand Management Plan and Appointment letters
FV_TL08 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Programme Management Unit | Bankable projects for implementation on alternative funding model | Percentage of municipality capital budget actually spent on capital projects by 30 June 2019 | % | 100% | 100% | 100% | 100% | 100% | 100% | Quarterly Capital Implementatiion Report
FV_TL09 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Municipal debt coverage by 30 June 2019 (Total Operating Revenue Recieved -minus Operating Grants/Interest plus Redemption) | # | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | MFMA S71 Report
FV_TL10 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Municipal outstanding service debtors by 30 June 2019 {(Total outstanding debtors-less impairment/Total revenue billed for services) * 365] | # | 30 | 30 | 30 | 30 | 30 | 30 | MFMA S71 Report, Debtors Age Analysis Report
FV_TL11 | Financial Viability | Smart Governance | Promotion of sound financial management to ensure financial sustainability | To ensure efficiency and effectiveness of municipal administration | Financial Viability | Bankable projects for implementation on alternative funding model | Municipal cost coverage by 30 June 2019 (Available cash plus investments/fixed costs) Fixed costs = Bulk purchases plus salaries | # | 1 | 1 | 1 | 1 | 1 | 1 | MFMA S71 Report

## DETAILED CWP
Project Number | Key Performance Area | Polokwane Strategic Objective (IDP Objective) | Municipal Programme | Project Name/Description | Type of Project - New/Renewal | Project Location | Ward No. | Project Owner | Sources of Funding | Implementing Agent | Original Budget | Revised Budget | Quarterly Project Implementation Milestones |  |  |  | Annual Project Output (30 June 2019) | PoE (Evidence to verify Performance
[13 empty] | Quarter 1 (Jul-Sep) | Quarter 2 (Oct-Dec) | Quarter 3 (Jan-Mar) | Quarter 4 (Apr-Jun)
Clusters - SPME
CWP_01 | Good Governance and Public Participation | To ensure efficiency and effectiveness of municipal administration | Clusters | Thusong Service Centre (TSC) -Mankweng (Acquisition of land in Mankweng for the construction of TSC) | R | Mankweng | Mankweng Cluster | Director SPME | CRR |  | 1000000 | 1000000 | Preparing of Bid document and finalising of construction estimate. Completion of planning. | None | Advertisement of expression of interest by land owners | Procurement of land and registration process to the deeds office for the transfer of land to Polokwane Municipality | Procured and registered land | Advert and deeds registration
Total Clusters - SPME
1000000
Facility Management- Community Development
CWP_03 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Civic Centre refurbishment | R | Polokwane | Pcity Cluster | Director Community development | CRR |  | 4000000 | 6 000 000 | Installation of new alluminium windows, new mechanical ventilation, new electrical layouts. | Installation of new partitions, floor finishes, new electrical layouts and sanitary fittings. | None | None | Installation of new alluminium windows, new mechanical ventilation, new electrical layouts, new partitions, floor finishes, new electrical layouts | Payments, progress reports, completion certificates
CWP_04 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Renovation of municipal wide offices | R | Polokwane | Pcity Cluster | Director Community development | CRR |  | 1500000 | 2 800 000 | Installation of aircons at Libraries | Installation of carports at Traffic Ladanna | Payment of invoices for consultants | None | Payment of outstanding consultants and contractors invoices | Payments, progress reports, completion certificates
CWP_05 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Municipal Furniture and Office Equipment | N | Polokwane | Pcity Cluster | Director Community development | CRR |  | 500000 | 1 000 000 | Supply office furniture | Supply office furniture | Request for quotations to supply furniture | Supply office furniture | Delivery of office furniture | Delivery notes, Payments
CWP_06 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Refurbishment of City Library and Auditorium | R | Polokwane | 20 | Director Community development | CRR |  | 500000 | 484 996 | Waterproofing, painting, electrical | None | None | None | Waterproofing, painting, electrical | Job cards, payments
CWP_07 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Upgrading of Seshego Library | R | Seshego | 17 | Director Community development | CRR |  | 500000 | 500 000 | Installation of aircons, aluminium doors | None | None | None | Installation of aircons | Payments, progress reports, completion certificates
CWP_08 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Library Dikgale | N | Dikgale | 32 | Director Community development | CRR |  | 500000 | 300 000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
CWP_09 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Library Bloodriver /Perskebult | N | Bloodriver /Perskebult | 10 | Director Community development | CRR |  | 300000 | 300 000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
CWP_10 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Civic Centre Aircon Upgrade | N | Polokwane | 20 | Director Community development | CRR |  | 1000000 | 985 837 | Installation of aircon plant for Civic Centre North wing | Installation of aircon plant for Civic Centre North wing | None | None | Installation of aircon plant for Civic Centre North wing | Job cards, payments
CWP_11 | Basic Service Delivery | To ensure provision of basic and environmental services in a sustainable way to our communities | Infrastructure/Facility Maintenance | Construction of Mankweng Water and Sanitation Centre | N | Mankweng | 25 | Director Community development | CRR |  | 1000000 | _ | Identification of site, Design development | Approval of designs | None | None | Appointment of consultant | Bid document. Drawings
Total Facility Management- Community Development
9800000
Control Centre Services - Community Services
CWP_12 | Basic Service Delivery | To ensure social protection and education outcomes | Security Services | Installation of CCTV cameras | N |  |  | Director Community Services | CRR |  | 1700000 | 1 700 000 | Planning and outlining the installation of internal and external cameras | Installation of cameras on biuldings that does not have cameras at all | Installation of cameras in the CBD at the hot spot areas as would be identified | Installation of cameras at biuldings that need to be added | Project completion | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_13 | Basic Service Delivery | To ensure social protection and education outcomes | Security Services | Hand held radios | N |  |  | Director Community Services | CRR |  | 100000 | 99 202 | Planning the installation and purchase of two way radios | Installing base radios | Purchasing two way radios for end users | Purchasing two way radios for end users | Project completion | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_14 | Basic Service Delivery | To ensure social protection and education outcomes | Security Services | Access Control | N |  |  | Director Community Services | CRR |  | 227000 | 227 000 | Planning and outlining the installation of Access control at various biulding | Conducting assessment for the installation access at all Municipal premises | Installation of access (biometric and card readers)40% | Installation of access (biometric and card readers)60% | Project completion | Appointment letter, Project progress report, Payment certificate, Completion certificate
Total Control Centre Services - Community Services
2027000
Roads & Stormwater - Engineering
CWP_15 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Chebeng to Makweya internal streets | N | Makweya | 9 | Director Engineering | MIG | Polokwane Municipality | 4000000 | 6 200 000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Chebeng to Makweya road | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_16 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Sebayeng ring road (Upgrading from gravel to Asphalt) | N | Sebayeng | 32 | Director Engineering | MIG | Polokwane Municipality | 2600000 | 4 330 000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Sebayeng road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_17 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Tarring of Arterial road in SDA1 (Lithuli and Madiba park) | N | Lithuli | 14 | Director Engineering | MIG | Polokwane Municipality | 13000000 | 15 000 000 | Appointment of contractor and site establishment | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Finalizing layer works and Surfacin, cleaning of site. | Multiyear project. Completion of phase 1 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_18 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Tarring Ntsime to Sefateng (Phase 2 and 3) | N | Ntsime | 31 | Director Engineering | MIG | Polokwane Municipality | 10000000 | 10 137 000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | project completion | Completion of Ntsima to Sefateng road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_19 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading Semenya to Matekereng | N | Semenya | 38 | Director Engineering | MIG | Polokwane Municipality | 11000000 | 4 553 422 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Semenya to Matekereng road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_22 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of Ramongoana bus and Taxi roads | N | Ramongwana | 38 | Director Engineering | MIG | Polokwane Municipality | 3500000 | 3 500 000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Ramongwana road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_23 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of Ntshitshane Road | N | Ntshitshane | 6, 31 | Director Engineering | MIG | Polokwane Municipality | 7000000 | 10 681 000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacin, cleaning of site. | Project completion | Completion of Ntshitshane road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_24 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Tarring of internal streets in Toronto | N | Toronto | 25 | Director Engineering | MIG | Polokwane Municipality | 10000000 | 15 400 000 | Appointment of a Contractor,Site establishment and road bed preparartions | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Toronto road phase 3 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_25 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal Streets in Mankweng unit E (Vuk'uphile) | N | unit E | 25 | Director Engineering | CRR | Polokwane Municipality | 1140000 | 1 140 000 | Handover of site to Learner contractors, site establishment and roadbed preparations | Construction of Layer works and drainage system | Handover of site to Learner contractors, site establishment and roadbed preparations | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_26 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets linked with Excelsior Street in Mankweng unit A | N | Mankweng | 25,26 | Director Engineering | MIG | Polokwane Municipality | 10000000 | 16 500 000 | Appointment of a Contractor,Site establishment and road bed preparartions | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street linked to Excelsior Strret | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_27 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading Makanye Road (Ga-Thoka) | N | Makanye | 27 | Director Engineering | CRR | Polokwane Municipality | 9000000 | 9 000 000 | Construction of Layer works and drainage system | construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of road in Makanye | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_28 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of Arterial road in Ga Rampheri | N | Rampheri | 4 | Director Engineering | MIG | Polokwane Municipality | 6500000 | 6 500 000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of road in Rampheri | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_29 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of access roads to Maja Moshate (Molepo Chuene Maja cluster) | N | Chuene | 2 | Director Engineering | MIG | Polokwane Municipality | 9000000 | 10 970 000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of road in Maja Moshate | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_30 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | upgrading of stormwater system in municipal area (Vuk'uphile) | N | municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 1900000 | 1 900 000 | Handover of site to Learner contractors, site establishment and excavations | Excavations and pipe laying of stormwater units | Handover of site to Learner contractors, site establishment and excavations | Excavations and pipe laying of stormwater units | Excavations and pipe laying of stormwater units | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_31 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Rehabilitation of streets in Seshego Cluster | R | Seshego Cluster | 11,12,13,14,17,37 | Director Engineering | CRR | Polokwane Municipality | 4500000 | 4 500 000 | Handover of site to Learner contractors, site establishment and setting out | Removal and excavation of existing pavement material | Handover of site to Learner contractors, site establishment and setting out | Removal and excavation of existing pavement material | Removal and excavation of existing pavement material | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_32 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 1 | N | Zone 1 | 13 | Director Engineering | CRR | Polokwane Municipality | 8000000 | 8 000 000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 1 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_33 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading Internal Streets in Seshego Zone2 | N | Zone 2 | 17 | Director Engineering | MIG | Polokwane Municipality | 10000000 | 10 000 000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 2 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_34 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 2 | N | Zone 2 | 17 | Director Engineering | CRR | Polokwane Municipality | 4000000 | 4 000 000 | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Street in Zone 2 | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_35 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Triangle Park- land scaping and street lighting Seshego Zone 2 | N | Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 7003000 | 8 431 700 | Appointment of contractor and site establishment and clearing of site | Construction of fence, installation of lighting, walkways and grassing. | Installation of jungle gyms, irrigation system | Installation of electrical works, lanscaping and project completion | Completion of the triangle park | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_36 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 3 | U | Zone 3 | 37 | Director Engineering | CRR | Polokwane Municipality | 8000000 | 5 000 000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Finalizing layer works and Surfacing, cleaning of site. | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_37 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 4 | U | Zone 4 | 12 | Director Engineering | CRR | Polokwane Municipality | 8000000 | 8 000 000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Finalizing layer works and Surfacing, cleaning of site. | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_39 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 5 | U | Zone 5 | 11 | Director Engineering | MIG | Polokwane Municipality | 5500000 | 5 500 000 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Appointment of contractor and site establishment | Construction of Layer works and drainage system | Construction of Layer works and drainage system | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_40 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Upgrading of internal streets in Seshego Zone 8 (Planning) | U | Seshego zone 8 | 11 | Director Engineering | CRR | Polokwane Municipality | 1200000 | 1 200 000 | Appointmnet of consultant | Scoping report | Prelimenary report and Detailed design report | Tender advert | Tender advert of project | Tender advert
CWP_41 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Seshego Hospital link-Upgrading of township road & Bookelo street | U | Seshego Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 8740000 | 6 742 683 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Setting out of earthworks, surfacing of Bookelo street and layerworks for NMT | Finalizing layer works, cleaning of site, Surfacing and Project completion | Completion of Seshego Hospital Link | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_42 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Construction of stormwater culvert and NMT facilities between skotipola, kgoro and dinkwe | N | Seshego Zone 2 | 17 | Director Engineering | NDPG | Polokwane Municipality | 8703000 | 9 136 717 | Trench excavations for electrical works, cabling, streetlighting, block paving | Landscaping and finishing off and clearing | Project completion |  | Completion of Construction of stormwater culvert and NMT facilities between skotipola, kgoro and dinkwe | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_43 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Traffic Lights and Signs (Municipal Wide) | N | municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 3000000 | 3 000 000 | Detailed design stage and tender advert | Appointment of contractor, Site establishment and exposing exising services | Appointment of contractor. | Site establishment and exposing exising services and installation of traffic light | Erection of 1 new signalised traffic lights, and Concret footings for traffic lights and road signs | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_45 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Mohlonong to Kalkspruit upgrading of road from gravel to tar | U | Mohlonong | 40,42 | Director Engineering | MIG | Polokwane Municipality | 7000000 | 5 000 000 | Construction of Layer works and drainage system | Finalizing layer works and Surfacing, cleaning of site. | Finalizing layer works and Surfacing, cleaning of site. | Project completion | Completion of Mohlonong to Kalkspruit upgrading of road from gravel to tar | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_46 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Rehabilitation of streets in Municipal Wide (Concession Program) | N | municipal wide | Municipal wide | Director Engineering | LOAN | Polokwane Municipality | 80000000 | 20 000 000 | Detailed design and appointment of contractor | Site establishment and identification of existing services | Scoping of additional rural roads | Detailed design stage (Final design) | Detailed design stage (Final design) | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_47 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Polokwane Drive- upgrade from single to dual carriage way | U | Lithuli | 12, 13, 14,17 | Director Engineering | NDPG | Polokwane Municipality | 8050000 | 10 222 420 | Appointment of contractor and site establishment and roadbed preparations | Construction of Layer works and drainage system | Construction of Earthworks | Construction of Layer works and drainage system | Project is a multiyear | Appointment letter, Project progress report, Payment certificate, Completion certificate
CWP_49 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Roads and Stormwater | Construction of NMT at Magazyn Street and Vermekuwet (Planning and design) | N | CBD | City Cluster | Director Engineering | KFWBANK | Polokwane Municipality | 14400000 | 2 504 000 | Preliminary and detailed design stage | Appointment of contractor, Site establishment and exposing exising services | Preliminary design stage | Detailed design stage (Final design) | Detailed design stage (Final design) | Appointment letter, Project progress report, Payment certificate, Completion certificate
Total Roads & Stormwater - Engineering
284736000
Water Supply and reticulation - Engineering
CWP_50 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Olifantspoort RWS (Mmotong wa Perekisi) | N | 10, 16,36,37 | 10, 16,36,37 | Director Engineering | MIG |  | 23000000 | 23 000 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_51 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Moletjie East RWS | N | 15, 36, 38 | 15, 36, 38 | Director Engineering | MIG |  | 20000000 | 20 000 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of booster pump station. | Continue with excavations and pipe laying. connection. Eskom connection and all other water connection. | Continue with excavations and pipe laying. connection. Eskom connection and all other water connection. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_52 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Sebayeng/Dikgale RWS | N | 29,31,32,33 | 29,31,32,33 | Director Engineering | MIG |  | 17000000 | 22 900 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of reservoir and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_53 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Houtriver RWS phase 10 | N | 18,35 | 18,35 | Director Engineering | MIG |  | 10000000 | 10 000 000 | Approval of technical report and tender advert | Appointment of Contractor, site handover and establishment | Detailed design report and to serve at BSC | Tender advert, appointment of Contractor, site handover and establishment | Tender advert, appointment of Contractor, site handover and establishment | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_54 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Chuene Maja RWS phase 9 | N | 1,2 | 1,2 | Director Engineering | CRR |  | 2500000 | 3 250 000 | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | project completion | N/A | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_55 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Molepo RWS phase 10 | N | 1,2 | 1,2 | Director Engineering | MIG |  | 10000000 | 14 000 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house and all other water connection. | Continue with excavations and pipe laying. Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | Boreholes equipped, pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_56 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Laastehoop RWS phase 10 | N | 5 | 5 | Director Engineering | MIG |  | 6000000 | 8 500 000 | Appointment of Contractor, site handover. |  | Appointment of Contractor, site handover, Site establishment and excavations | Continue with excavations and pipe laying. Construction of pump house and all other water connection. | Continue with excavations and pipe laying. Construction of pump house and all other water connection. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_57 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Mankweng RWS phase 10 | N | 27, 25, 31, 7, 26 | 27, 25, 31, 7, 26 | Director Engineering | MIG |  | 15000000 | 18 300 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Continue with excavations and pipe laying. Construction of pump house. all other water connection. | Construction of pump house. Eskom connection and all other water connection.Commissioning and issuing completion certificate. | pump house, bulk line and distribution line. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_58 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Boyne RWS phase 10 | N | 4 | 4 | Director Engineering | MIG |  | 9763000 | 6 763 000 | Approval of technical report and tender advert | Appointment of Contractor, site handover and establishment | Detailed design report and to serve at BSC | Tender advert, appointment of Contractor, site handover and establishment | Tender advert, appointment of Contractor, site handover and establishment | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_59 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Water Conservation & Water Demand Management (Installation of Smart Meters) at Mankweng | N | 26 | 26 | Director Engineering | WSIG |  | 10000000 | 10 000 000 | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Installation of smart meters municipal wide | Progress report
CWP_60 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Segwasi RWS Planning | N | 28 | 28 | Director Engineering | WSIG |  | 1000000 | 1 000 000 | Appointment of consultant | Preparation of design reports | Preparation of design reports | Tender advert for appointment of contractor | Tender advert for appointment of contractor | Tender advert
CWP_61 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Badimong RWS phase 10 Planning | N | 28,30, 31, 34 | 28,30, 31, 34 | Director Engineering | WSIG |  | 1000000 | 1 000 000 | Appointment of consultant | Preparation of design reports | Preparation of design reports | Tender advert for appointment of contractor | Tender advert for appointment of contractor | Tender advert
CWP_63 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Extension 78 sewer reticulation | N | 8 | 8 | Director Engineering | CRR |  | 665000 | _ | Detailed design presentation | n/a budget insufficient | N/A | Tender advert after confirmation of 19/20 FY budget | Tender advert after confirmation of 19/20 FY budget | Tender advert
CWP_64 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Extension 106 sewer & water reticulation | N | 8 | 8 | Director Engineering | CRR |  | 8500000 | 1 100 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | N/A | N/A | Completion of sewer and water reticulation | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_65 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Aganang RWS 1 Planning (Juno, Kordon and Farlie) | N | 40,41,42,43,44 & 45 | 40,41,42,43,44 & 45 | Director Engineering | WSIG |  | 11000000 | 11 000 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Site establishment, excavations and pipe laying, equipping of boreholes. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_66 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Aganang RWS 2 (Mahoai and Ceres) | N | 40,41,42,43,44 & 45 | 40,41,42,43,44 & 45 | Director Engineering | CRR |  | 9525000 | 9 525 000 | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Appointment of Contractor, site handover. | Site establishment, excavations and pipe laying, equipping of boreholes. | Site establishment, excavations and pipe laying, equipping of boreholes. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_67 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Asbestos (AC) Pipes in Seshego, Annadale & CBD | N | City and Seshego Cluster | City and Seshego Cluster | Director Engineering | RBIG |  | 83335120 | 210 159 624 | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections. Installations of PRV | Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections. Installations of PRV and project completion | 46 km Asbestos pipes replacements, installation of fire hydrants and reinstatements. House connections. Installations of PRV | progress reports, minutes, payment certificates,
CWP_68 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Polokwane Water Network Upgrading (1) | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 4600000 | 4 600 000 | Appointment of consultant for scoping, designs and procurement | Raplacing inlets control system and refurbishment of outlet pipe manifold in Krugersburg. | Refurbishment of pumps at mashinini, installattion water and sewer in ext 133 | Refurbishment of sandriver south pumpstation | Refurbishment of pumps at mashinini, installattion water and sewer in ext 133.Refurbishment of sandriver south pumpstation | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_69 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | PolokwanWater Network Upgrading(2) | U | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | CRR |  | 4600000 | 4 600 000 | Appointment of consultant for scoping, designs and procurement | Refurbishment of pumpstations and pressure control systems in Polokwane | Extention of sewer network in Sterpark east of Coronna Street. Relocation of sewere in Mankweng. | Extention of Sewer service in Bendor. | Extention of sewer network in Sterpark east of Coronna Street. Relocation of sewere in Mankweng. Extention of Sewer service in Bendor. | Appointment letter, progress reports, minutes, payment certificates, completion certificate.
CWP_70 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Water Supply and Reticulation Programme | Polokwane Groundwater development | N | 08 19,20,21,22,23 & 39 | 08 19,20,21,22,23 & 39 | Director Engineering | WSIG |  | 45600000 | 45 600 000 | Drilling, testing and equiping of boreholes | N/A | Detailed design report and to serve at BSC | Tender advert, appointment and site establishment | Tender advert, appointment and site establishment | Test certificates and project reports
Total Water Supply and reticulation - Engineering
293088120
Sewer Reticulation - Engineering
CWP_74 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Sanitation | Regional waste Water treatment plant | N | 9 | 9 | Director Engineering | RBIG |  | 180519880 | 133 842 880 | Preliminary design stage | Detailed design stage | Construction of outfall sewers and design of the RWWTW plant | Continuation of outfall sewers construction and Tender advert of RWWTW plant | Continuation of outfall sewers construction and Tender advert of RWWTW plant | Design reports, tender advert, appointment letter
CWP_75 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Sanitation | Regional waste Water treatment plant | N | 11,12,13,14,17,37,08,19,20,21,22,23,39 | 11,12,13,14,17,37,08,19,20,21,22,23,39 | Director Engineering | PLEDGE/RBIG |  | 170000000 | 170 000 000 | Preliminary design stage | Detailed design stage | Construction of outfall sewers and design of the RWWTW plant | Continuation of outfall sewers construction and Tender advert of RWWTW plant | Continuation of outfall sewers construction and Tender advert of RWWTW plant | Design reports, tender advert, appointment letter
CWP_76 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Sanitation | Refurbishment of Polokwane Waste Water Treatment Works | R | 11,12,13,14,17,37,08,19,20,21,22,23,39 | 11,12,13,14,17,37,08,19,20,21,22,23,39 | Director Engineering | CRR |  | 41800000 | 41 800 000 | Continue with the replacement and repair of mechanical and electrical equipment as well as structural repairs to return the WWTW to a functional condition | Continue with the replacement and repair of mechanical and electrical equipment as well as structural repairs to return the WWTW to a functional condition | Continue with the replacement and repair of mechanical and electrical equipment as well as structural repairs to return the WWTW to a functional condition | Phase 1 completion | Replaced and repaired mechanical and electrical equipment as well as structural repairs | Progress reports, Site meetings, design reports, quotations as built plans and Maintenance and Operation Plan
Total Sewer Reticulation - Engineering
392319880
Energy Services - Engineering
CWP_77 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Illumination of public areas ( main street into ext40,and75 from Nelson Mandela Voortrekker street , Ext 40 from Matlala road, Ext 71,73 | N | Ext 40 and 75 | 8,14 | Director Engineering | CRR | Polokwane Municipality | 2145000 | 2 145 000 | Advertise bid, evaluate and appoint contractor | oreder material | plant poles and install cables and lights | Test, commissioning and switching on | 50 street lights installed in the area | Adverts, appointment letters, SLAs, payment certificate
CWP_78 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Illumination of public areas ( High Mast lights) various rural areas | N | Municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 9487500 | 9 487 500 | Advertise bid, evaluate and appoint contractor | order poles, lights and dig foundations | install poles and lights | Test, commissioning and switching on | 11 High Mast lights installed | Adverts, appointment letters, SLAs, payment certificate
CWP_79 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | SCADA on RTU in Superbia & Epsilon | N | Superbia | 11,12,13, 14,17,37 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 2437500 | 2 437 500 | Appointment of Contractor, site handover and site establishment. | order materials | install RTUs | Test, commissioning and switching on | 66KV substation connected to SCADA t | Appointment letters, adverts, payment certificate, completion certificate
CWP_80 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Replacement of Fiber glass enclosures in Flora, Fauna Park and NIrvana | N | Flora, Fauna and Nirvana | 19,20,21,22,23, 39 | Director Engineering | CRR | Polokwane Municipality | 9750000 | 6 750 000 | Advertise bid, evaluate and appoint contractor | order materials, prepare boxes at training centre | replace the fibre enclosures | Test, commissioning and switching on | 300 meter box enclosures replaced | Requisitions, invoices, job cards
CWP_81 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Planning and design New Bakone to IOTA 66KV double circuit GOAT line | N | Bakone SS | 11,12,13, 14,17,37 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 9750000 | 2 750 000 | Advertise bid, evaluate and appoint contractor | Order materialr | Installation of poles | Poles installed | Poles installed | Quotations for servitudes, minutes, payment certificates
CWP_82 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Build 66KV/Bakone substation | N | Bakone SS | 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 9500000 | 3 000 000 | Appointment of Contractor, site handover and site establishment. | Prepare civil works and grounds | Build the substation | Test, commissioning and switching on | Install switch gears | Minutes of meetings, Progress report, payment certificates,
CWP_83 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Electrification Of Urban Households in Extension 78 and 40 | N | Ext 78 and 40 | 8 | Director Engineering | CRR | Polokwane Municipality | 5850000 | 1 000 000 | Advertise bid, evaluate and appoint contractor | Order materialr and plant poles | Stringing and transformer installat | Test, commissioning and switching on | electrified households | Appointment letters, minutes, payment certificates.
CWP_84 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Design and Construct permanent distribution substation at Thornhill | N | Thornhill | 23 | Director Engineering | CRR | Polokwane Municipality | 9750000 | 9 750 000 | Execute the work | order material | build structure and | install switch gear | completed 11 kv switching substation | Appointment letters, minutes, payment certificates.
CWP_85 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Power factor corrections in various Municipal Substations | N | Municipal wide | 11,12,13, 14,17,37 19,20,21,22,23 | Director Engineering | CRR | Polokwane Municipality | 682500 | _ | Consultant appointment, development of bid document and advertise | Evaluate and appoint contractor, site handover and site establishment. | N/A | N/A | N/A | Appointment letters, minutes, payment certificates.
CWP_86 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Plant and Equipment | N | Municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 2500000 | 2 500 000 | Execute the work | get quotations and orders | purchase | receive items | receive items | Requisitions, invoices, job cards
CWP_87 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Increase license area assets (Feasibility study to increase license area) | N | Municipal wide | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 1000000 | 1 000 000 | Meetings to negotiate | meetings to negotiate | cost the transfers | report agreements | Execute the work | Requisitions, invoices, job cards
CWP_88 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Replace 66kV Bus Bars & Breakers at Gamma Substation | R | Gamma SS | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 3217500 | 3 217 500 | Advertise bid, evaluate and appoint contractor | Designs | Designs | Prepare tender documents | Advertise bids | Appointment letters, minutes, payment certificates.
CWP_89 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Replacement of Fences at Sterpark & Florapark Substations (vuk'uphile) | R | Various Sub Stations | Municipal wide | Director Engineering | CRR | Polokwane Municipality | 975000 | 975 000 | Designs | Appoint contractors | Replace the fences | Test, commissioning and switching on | Evaluate and prepare the following bids | Appointment letters, minutes, payment certificates.
CWP_90 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Upgrade Gamma Substation and install additional 20MVA transformer (Design) | U | Gamma SS | 20, 21, 19 | Director Engineering | CRR | Polokwane Municipality | 975000 | 975 000 | Advertise bid, evaluate and appoint contractor | Designs | Advertise tender | Evaluate and award | Build substation | Appointment letters, minutes, payment certificates.
CWP_91 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Design and Construction of New Pietersburg 11kv substation | N | New Pietersburg | 8, 14,19 | Director Engineering | CRR | Polokwane Municipality | 1000000 | 1 000 000 | Advertise bid, evaluate and appoint contractor | Designs | Construct civil works | Measure and order switch gears | Install switch gears | Appointment letters, minutes, payment certificates.
CWP_92 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Installation of Check Meters at Main substations (Beta, Alpha and Three wheeling points) | N | Various Sub Stations | 8,11,12,13,14,37,37,19,20,21,22,23,39 | Director Engineering | CRR | Polokwane Municipality | 3200000 | 2 000 000 | Advertise bid, evaluate and appoint contractor | order meters | install meters | Test, commissioning and switching on | report on operations and | Appointment letters, minutes, payment certificates.
CWP_93 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Electrification/Energy Programme | Lowering Pole mount boxes to ground mounted in Westernburg and Zone 1 Ext | N | Westernburg and Zone 1 Ext | 8,11,12,13,14,37,37 | Director Engineering | CRR | Polokwane Municipality | 5850000 | 1 850 000 | Consultant appointment, development of bid document and advertise | Evaluate and appoint contractor, site handover and site establishment. | order materials | install meters mobexes and transfer meters | test and commission | Appointment letters, minutes, payment certificates.
Total Energy Services - Engineering
78070000
Disaster and Fire - Community Services
CWP_94 | Basic Service Delivery | To ensure social protection and education outcomes | Disaster and Fire Programme | Planning for extension of fire training Centre | N | 23 | 23 | Director Community Services | CRR |  | 1000000 | 1 000 000 | Appoint the consultant to prepare the design report and approval of the design scope | Consultant to submit the drawings for approval by Housing and Building Inspection section. Preparation of bid document and of cost estimate | Appontment of consultant | Approved drawings | Approved drawings | Appointment letter and approved drawings
Total Disaster and Fire - Community Services
1000000
Traffic & Licencing - Community Services
CWP_95 | Basic Service Delivery | To ensure social protection and education outcomes | Traffic and Licensing | Upgrading of logistics offices | U | Polokwane | City Cluster | Director Community Services | CRR |  | 1000000 | _ | Contractor already on site ( Phase 2 to continue- progress report | Contractor on site | Contractor on site | None | None | None
CWP_96 | Basic Service Delivery | To ensure social protection and education outcomes | Traffic and Licensing | Upgrading- Traffic Auditorium, parade room and Training Facility | U | Polokwane | City Cluster | Director Community Services | CRR |  | 600000 | 600 000 | Contractor on site | Contractor on site | Contractor on site | Project completion and handing over | Conjusive working environment. | Completion certificate
CWP_97 | Basic Service Delivery | To ensure social protection and education outcomes | Traffic and Licensing | Upgrading of city vehicle test station (Installation of play detector) | U | Polokwane | City Cluster | Director Community Services | CRR |  | 500000 | 500 000 | Project specification and bid advertisement. | Awarding processes | Supply and Installation of play detector equipment | Payment and Closure | Compliance with Road Traffic Regulations | Completion certificate and Invoice
Total Traffic & Licencing - Community Services
2100000
Environmental Management - Community Services
CWP_98 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Development of a park at Ext 44 and 76 | N | City | 8 | Director Community Services | CRR |  | 600000 | 600 000 | Planting of 30 trees, establishment of 3 flowerbeds. | Drilling and equipping of borehole. Procuring paving bricks and kerbs | Paving and kebing of 3 shade houses each measuring 48 square metres | Complete and usable recreational park | Complete and usable recreational park | Works orders, Invoices, Delivery notes.
CWP_99 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Upgrading of Security at Game Reserve | U | City | 20 | Director Community Services | CRR |  | 1000000 | 1 000 000 | Submission of specification for the supply and delivery of (Bonox) game fence .400m perimeter. | Appointment of service provider for the supply and delivery of (Bonox) Game fence | Procurement of material (Bonox) Game fencing) | Implementation of the project ( Fencing) of approximately | Reinforced security fence | Appointment letter and Security fence
CWP_100 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Upgrading of Environmental Education Centre | U | City | 23 | Director Community Services | CRR |  | 750000 | 750 000 | Completion of paving for vehicle parking area. | Provision of the shopping list for teaching aids and educational displays. | Purchasing of teaching aids and educational displays. | Receiving and placing of educational displays and teaching aids | Updated and effective Environmental Education Centre | Invoices, Works orders and educational material
CWP_101 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Construction of ablution facilities at Tom Naude Park | N | City | 22 | Director Community Services | CRR |  | 800000 | 400 000 | Prepare and submit a report to BAC for the appointment of the architect to design Ablution facility | Appointment of the architect to plan, design and determine the Project specification and BOQ for Ablution Facility. | N/A | Apppointment of Service provider to build ablution facilities | Apppointment of Service provider to build ablution facilities | BAC Reports, Appointment letters, and designs
CWP_102 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Development of Ablution facilities at Various Municipal Parks | N |  | 22, 19, 20, 39, 25, 26, 32, 31 | Director Community Services | CRR |  | 500000 | 500 000 | Plans and designs | Plans and designs | Appointment of the architect to develop 2 models for ablution facilities for municipalparks | Completed models | Completed model desings | Appointment letter and completed model designs
CWP_103 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Animal Pound ( Ga-Kgoroshi and Laboria) | N |  | Municipal Wide | Director Community Services | CRR |  | 900000 | 900 000 | Submit the report for the establishment of the animal pound to Council | Repair the available sites through annual contractors | Procurement of fencing material for Animal pounds | Fencing of animal pound at Aganang cluster ( Ga-Kgoroshi). | An operational animal pound. Lesser roaming animals | Report. Invoices. Appointment letter. SLA
CWP_104 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Environmental Management | Upgrading of Ga- Kgoroshi community centre | N |  | 42 | Director Community Services | CRR |  | 500000 | 500 000 | Planting of 20 additional trees, procurement of 90 kerbs | Electrification and kerbing of childrens play area | Rehabilitation of an existing borehole. | Connecting electricity to the borehole. | Electrified facility | Invoices, Works orders
Total Environmental Management - Community Services
5050000
Waste Management - Community Services
CWP_105 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Waste Management | Extension of landfill site(weltevrede) - (Feasibility study to extend the Landfill site) | N | Municipal wide | Municipal wide | Director Community Services | CRR |  | 3000000 | 3 000 000 | Bid specification, approval and advertisement | Bid evaluation, adjudication and awarding | Landfill license application to LEDET | Outcome of the application process by LEDET | Landfill License | Feasibility study report, Application and Landfill license
CWP_106 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer station ( Sengatane) | N |  | 9 | Director Community Services | MIG |  | 4266667 | 3 800 091 | construction of the transfer station. Site hand over done on 14 may 2018 | construction of the transfer station | construction of the transfer station | construction and completion | complaeted transfer station | completion certificate and invoices
CWP_107 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer station (Dikgale) | N |  | 24 | Director Community Services | MIG |  | 4266667 | 4 999 719 | Site hand over and establishment to be done on 28 June 2018. contractor appointed on 25 May 2018 | construction of te transfer station | construction of the transfer station | construction and completion | completed transfer station | completion certificate and invoices
CWP_108 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer Station(Makotopong) | N |  | 28 | Director Community Services | MIG |  | 4266666 | 3 000 000 | evaluation and awarding | construction | construction | construction | Constructed transfere station | completion and invoices
CWP_109 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Waste Management | Rural transfer Station Planning (Molepo) | N |  | 1,2,3,4,5 | Director Community Services | CRR |  | 1000000 | 1 000 000 | Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
Total Waste Management - Community Services
16800000
Sport & Recreation - Community Development
CWP_110 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Construction of Mankweng Sport facility-2 | N | Mankweng | 25 | Director Community Development | MIG |  | 11440000 | 3 000 000 | Appointment of Service provider,Bulk civil works for roads and parking,finishes for the main pavilion | External buildings,Bulk services installation viz:water,sewerage,external lights and stormwater drainage | Building finishes,seats,soccer pitch and baseball drainage | Refurbishment of old courts(Basketball,netball | Completed roads and parking area;pavilion;completely refurbished basket and netball and netball courts | Appointment letters,Project reports, certificates;pictures
CWP_111 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Sport stadium in Ga-Maja | N | Ga-Maja | 2 | Director Community Development | MIG |  | 9600000 | 8 000 000 | Fencing;Bulk earthworks for all structures;Combi couts,ablution block;connection of water services | Borehole and septic tank;parking | Start with the construction of the community hall,excavation of the foundation;Construction of the concrete footing;construction of the floor | Construction of a community hall-;construction of the superstructure;Erection of the trusses,laying the roof cover;lighting,painting ;finishing off | Complete combi courts,ablution facility;borehole;septic tank;connection os services;community hall;lighting | Appointment letters,Project reports, certificates;pictures
CWP_112 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | EXT 44/77 Sports and Recreation Facility | N | Ext 44/77 | 8 | Director Community Development | MIG |  | 1500000 | 1 000 000 | Appointment of consultant, Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
CWP_113 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Upgrading of Tibane Stadium | U | Tibane | 44 | Director Community Development | CRR |  | 475000 | 475 000 | Procurement of contractor (Tender documents have been prepared) | Upgrading water supply system and providing additional ablution facilities | Project completion and finalisation | NA | Water supply system, tank and ablutions completed | Contract/ SLA/ progress reports, site meeting minutes as-built documents
CWP_114 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Sebayeng/Dikgale Sports Complex (Planning) |  | Sebayeng/Dikgale |  | Director Community Development | CRR |  | 1000000 | 1 000 000 | Appointment of consultant, Identification of site, Design development | Approval of designs | Preparation of Bid document and final construction estimates | Advertising of Bid and Adjudication. | Planning | Bid document. Drawings
CWP_115 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Rehabilitation of Swimming Pool to be commercialized | R | City | City | Director Community Development | CRR |  | 1575000 | 1 575 000 | Plant room maintenance and Pumps instalation | Filtration system and completion | N/A | N/A | Rehabilitated swimming pools | Project progress report and pictures
CWP_116 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Upgrading of Mohlonong Stadium | U | Aganang | Aganang | Director Community Development | MIG |  | 7300000 | 6 400 000 | Construction of Retaining structure, lawns (artificial grass), augmentation of water system and gravel athletics track | Construction of Retaining structure, lawns (artificial grass), augmentation of water system and gravel athletics track | Concluding reporting and documentation, close out report and as-built plans | NA | Functioning water supply system, lawns and athletics track | Contract/ SLA/ progress reports, site meeting minutes as-built documents
Total Sport & Recreation - Community Development
32890000
Security Services - Community Services
CWP_117 | Basic Service Delivery | To ensure social protection and education outcomes | Sport & Recreation | Upgrading of offices at Itsoseng for Security Services | N | City | City | Director Community Development | CRR |  | 600000 |  | specification and advertisement | Evaluate and appoint contractor and site handover . | project implementation | completion of the project | upgraded offices | invoices
Total Security Services - Community Services
600000
#REF!
Information Services - Corporate and Shared Services
CWP_118 | Good Governance and Public Participation | To ensure efficiency and effectiveness of Municipal administration | ICT Programme | Implementation of ICT Strategy (Upgrading of Council Chambers by installing translation devices) | N | Municipal wide | Municipal Wide | Director Corporate and Shared Services | CRR |  | 2700000 | 2 700 000 | Finalization of Specification | Service Provider apointment | Project completion | N/A | installed translation system | Project Handover Report
CWP_119 | Good Governance and Public Participation | To ensure efficiency and effectiveness of Municipal administration | ICT Programme | Network Upgrade (Reliable network connectivity to cluster offices) | U | Municipal wide | Municipal Wide | Director Corporate and Shared Services | CRR |  | 4000000 | 4 000 000 | Appoinment of Service Provider | 30% Implementation | 70% connecting all the Ladanna, Seshego, Moletji and Aganang offices | 100% connecting Mankweng, Sebayeng, Maja, Molepo and CBD offices | 100% connecting Mankweng, Sebayeng, Maja, Molepo and CBD offices | Project Handover Report
Total Information Services - Corporate and Shared Services
6700000
City Planning - Planning and Economic Development
CWP_120 | Spatial Rationale | Promotion of economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Township establishment-Farm Volgestruisfontein 667 LS | N | Municipal wide | Municipal wide | Director Planning and Economic Development | CRR |  | 2000000 | 2 000 000 | Lum Resolution ROD General Plan approval | Lum Resolution ROD General Plan approval | Approved Layout Plan and Condition of Establishment, General Plan Approval | Proof of Submission for regsiation at Deeds office | Registration of Township and Proclamation | MPT Resolution, Proclamation notice, Proof of submission of application Final Layout ROD Approved General Plan Township Register
CWP_122 | Spatial Rationale | Promotion of economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Township establishment-Portion 74 and 75 of Ivy Dale Agricultural Holdings | N | Municipal wide | Municipal wide | Director Planning and Economic Development | CRR |  | 1000000 | 1 000 000 | LUM Resolution ROD Approved General Plan | Township Regsiter | Draft Layout CoE Environmental Management Plan Township Application | LUM Resolution Township Layout | Proclaimed Township Serviced Township | LUM Resolution Final Layout ROD Approved General Plan Township Register Proclamation Notice
CWP_124 | Spatial Rationale | Promotion of economic growth ,job creation and Sustainable human settlement | Human Settlement/City Planning | Planning for Installation of engineering services at Polokwane extension 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 (water, electricity, sewerage network and roads) | N | 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 34 | 108, 72, 78, 79, 106, 107, 126, 127, 133, 134, 121, Nivarna x5, southern gateway x1 and Ivy Park 35 | Director Planning and Economic Development | CRR |  | 1000000 | 1 000 000 | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | A spreadsheet of subserviced townships sent to Engineering department, IUDF funding to assist with services. Discussions with Engineering underway | Opening of Township Register | Opening of Township register and proclamation | Proclaimed Township ready for installation of services | LUM Resolution Final Layout ROD Approved General Plan Township Register Proclamation Notice
Total City Planning - Planning and Economic Development
4000000
Transport Operations(IPRTS)- Transport and Services
CWP_127 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Control Centre | N | Municipal wide | 20 | Director Transportation Services | PTNG |  | 1500000 | 1 500 000 | Advertisement of tender to procure (PTMS) monitoring system to be installed in busses and control centre | Install PTMS elements: Server, Video walls | N/A | Operations of leeto la Polokwane system | Appointment letter , SLA of the fare collection service provider | Appointment letter for the service provider, Bid Document, SLA, Advertisement of the Fare Collection Service Provider
CWP_129 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Public Transport facility upgrade (Pick n Pay and City Center facility) | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG |  | 5750000 | 5 750 000 | Designs of Taxi Facility upgrades | Appointment of contractor | Construction | Operations | Operations | Operations
CWP_130 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Upgrad & constr of Trunk route 108/2017 WP1 (Nelson Mandela Road) | N |  | 8, 13, 14, 17, 19 | Director Transportation Services | PTNG Pledge |  | 16844000 | 16 844 000 | Establishment, excavations, mass earthworks, Road layers | Road layer, BT Base, patching and milling on existing lanes, surfacing, kerbing and storm water drainage. | Road markings, Rumble blocks, road signs and finishing | n/a | 0.6km New BRT lanes & rehabilitation of mixed traffic lanes | Appointment letter, site meeting minutes, progress reports
CWP_131 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Construction of bus depot Civil works 108/2017 WP3 (Seshego Zone 8) | Upgrad & constr of Trunk route 108/2017 WP1 (Nelso+E180 |  | 11 | Director Transportation Services | PTNG Pledge |  | 5767000 | 5 767 000 | Establishment, excavations, mass earthworks, pavement layers, fencing | Installation of stormwater systems, construction of pavement layers and platforms for buildings, concrete paving & kerbing, fencing | Construction of external stormwater system, completion of roadbed and selected & subbase roadlayers, construction of segmented blockpaving | Completion o segmented block paving with kerbing and palisade fencing. | Fenced Depot site, paved bus parking area with, fueling and washbay facility areas, with stormwater drainage systems | Appointment letter, site meeting minutes, progress reports
CWP_132 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Construction of bus station Civil works 108/2017 WP4 (General Joubert) | N |  | 22 | Director Transportation Services | PTNG Pledge |  | 20476000 | 20 476 000 | Establishment, excavations, mass earthworks, demolishing of public toilets, pavement layers | Pavement layers, rehabilitation and upgrading of roadways, construction of paving and kerbing | Demolishing of existing paved parking and roadways and existing ablution facility, construction of roadlayers on northeren bus lanes upto subbase layer. | Construction of roadlayers on the southeren bus lanes, Construction of BTB base and surfacing, construction of paving and kerbing on precinct area | Bus lanes, rehabilitated road ways, busstation platforms, paved station precinct | Appointment letter, site meeting minutes, progress reports
CWP_133 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Construction of bus station Civil works 108/2017 WP4 | N | Municipal wide | Municipal Wide | Director Transportation Services | PTNG |  | 7700000 | 7 700 000 | Establishment, excavations, mass earthworks, demolishing of public toilets, pavement layers | Pavement layers, rehabilitation and upgrading of roadways, construction of paving and kerbing | Demolishing of existing paved parking and roadways and existing ablution facility, construction of roadlayers on northeren bus lanes upto subbase layer. | Construction of roadlayers on the southeren bus lanes, Construction of BTB base and surfacing, construction of paving and kerbing on precinct area | Bus lanes, rehabilitated road ways, busstation platforms, paved station precinct | Appointment letter, site meeting minutes, progress reports
CWP_134 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Daytime lay-over 108/2017 WP2 (Itsoseng) | N | City | City | Director Transportation Services | PTNG Pledge |  | 7792000 | 7 792 000 | Site establishment, demolishing of existing parking area, excavations, mass earthworks and layerworks, installation of stormwater systems, | Construction of concrete paving and kerbing, perimeter fencing. | Completion of slected and subbase road layers and connection of stormwater pipe systems. | Construction of segmented paving with kerbing, pallisade fencing and finishing of the site | Provision of secured (fenced) paved parking area. (holding area) with stormwater drainage systems | Appointment letter, site meeting minutes, progress reports
CWP_135 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | CBD Transit Mall 108/2017 WP4 | N | City | City | Director Transportation Services | PTNG Pledge |  | 10925000 | 10 925 000 | n/a | Rehabilitation of mixed traffic lanes, construction of que jump lanes at intersections | Starting with light rehabilitation on mixed traffic lanes from the station area along to the northeren end of Chrurch street Transit Mall. | Complete the rehabilitation on the Transit Mall route, construction of que jump lanes at intersections. Provision of UTC traffic signals, roadmarkings | Que jump lanes and UTC systems at intersections, rehabilitated road ways | Appointment letter, site meeting minutes, progress reports
CWP_136 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Construction & provision of Depot Upper structuresm |  | City | City | Director Transportation Services | PTNG Pledge |  | 14950000 | 14 950 000 | n/a | n/a | n/a | Excavations & construction of foundations for the Maintenance building with service pits & storeroom. Procurement of temporary offices, restsrooms and guardhouse | Fenced Depot site, paved bus- and staff parking area, temporary offices, restrooms, guardhouse & foundations for Maintenance- and storeroom buildings | Appointment letter, site meeting minutes, progress reports
CWP_137 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Construction & provision of Station Upperstructures |  | City | City | Director Transportation Services | PTNG |  | 20834000 | 20 834 000 | n/a | n/a | n/a | Construction of 3 platforms for stations, construction of the topstructures for 2 module station (structures with canopies) | 3 platforms, 2 structures with canopies for the 2 module station | Appointment letter, site meeting minutes, progress reports
CWP_138 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Construction & provision of Station Upperstructures |  | City | City | Director Transportation Services | PTNG Pledge |  | 7916000 | 7 916 000 | n/a | n/a | n/a | Construction of 3 platforms for stations, construction of the topstructures for 2 module station (structures with canopies) | 3 platforms, 2 structures with canopies for the 2 module station | Appointment letter, site meeting minutes, progress reports
CWP_139 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Refurbishment of Daytime Layover Buildings |  | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge |  | 4025000 | 4 025 000 | n/a | Removal of old interior finishing and equipment. Repaint and tile ablution and admin building, internal walls and drywalling, | Removal of old interior finishing and equipment. Demolishing some internal walls. | Repaint and tile ablution and admin building, amendment to internal walls - drywalling & partitioning & fitment of ablution equipment and furniture. (store room & wash bay) | Ablution facility, rest rooms, offices, canteen, server room, store room and washbay, parking areas | Appointment letter, site meeting minutes, progress reports
CWP_143 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Upgrade & rehab of Trunk Ext in Seshego & SDA1 109/2017 | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge (Seshego Zone 1) |  | 8855000 | 8 855 000 | Establishment, excavations and relocation of services, mass earthworks, installation of stormwater pipe systems | Construction of pavement layers, stormwater drainage, milling of existing road prism, concrete kerbing, surfacing, road markings and road signs & finishing | Completion with the construction of the base coarse layer and surfacing, road markings and road signs. | n/a | 1.25 km upgraded and widened street section. | Appointment letter, site meeting minutes, progress reports
CWP_144 | Basic Service Delivery | To ensure the provision of basic and environmental services in a sustainable way to our communities | Transportation Services | Rehabilitation of Feeder Routes in Polokwane 110/2017 | N | Municipal wide | Municipal wide | Director Transportation Services | PTNG Pledge (Thabo Mbeki) |  | 5750000 | 5 750 000 | Establishment, relocation of services, deep milling of road layers | Completion of road structural layers, prime, surfacing and road markings | Additional scope - renovation of stormwater kerb inlets, cleaning of pipe systems and patching on Grobler street | n/a | 1.25km rehabilitated mixed traffic lanes | Appointment letter, site meeting minutes, progress reports
Total Transport Operations(IPRTS)- Transport and Services
139084000
Supply Chain Management - Budget and Treasury Services
CWP_146 | Financial Viability | ITo ensure efficiency and effectiveness of Municipal administration | Supply chain management | Upgrading of stores | U | City | City | Chief Financial Officer | CRR |  | 8500000 | 8 500 000 | Site handover to contractor, Site establishment. | Upgrading of Building 2 main entrance and offices. | Construction of Boundary wall and Guard house, Construction of new Warehouse | Completion of works | Upgrading of Building 2 main entrance and offices.Construction of Boundary wall and Guard house, Construction of new Warehouse. | Appointment letter, site meeting minutes, progress reports
Note on E68: Vheli Mthombeni: BTO
Note on E163: Vheli Mthombeni: Include description
Note on E167: Vheli Mthombeni: Same as above 133, 135,136
Note on E169: Vheli Mthombeni: Same as above 132, 133,135
Note on E171: Vheli Mthombeni: 137 and 138 Same project