## Contr B1 + B2 (hidden)
POLOKWANE MUNICIPALITY | [10 empty] | POLOKWANE MUNICIPALITY B 3
CONTRACT PAYMENT COVER SHEET | [10 empty] | SUMMARY OF CESSION PAYMENTS ON CERTIFICATE
PROJECT DESCRIPTION : |  |  | PROJECT NAME: UPGRADING OF ARTERIAL ROAD IN GA-MAGONGOA VILLAGE FROM ROAD D3378 TO D19 (WARD 42) |  |  |  |  | (computer based) |  |  | CONTRACT NO. : | PM53/2022 |  | CERT. No. : | 1 |  | CONTRACTOR : | Malerate Construction
1. I hereby certify that the project has been inspected and that the |  |  |  |  | 3. I have inspected this claim and I am satisfied that payment as indicated
work has been executed satisfactorily and according to specification |  |  |  |  | can be made. | [6 empty] | VALUE OF PRESENT CLAIM------------------ "subtotal A" | [6 empty] | 1003766.89
and that the quantities and prices shown are correct. | [12 empty] | PLUS ------------------- retention payout | [5 empty] | 0
[13 empty] | LESS ------------------- all cessions |  |  |  |  | [F] | 0
28/10/2024 |  | ........................................................ |  |  | ……………….. |  | ......................................................... | [11 empty] | 1003766.89 | A
Date |  | Engineer |  |  | Date |  | On behalf of Technical Manager | [10 empty] | VAT @ 15 % | 150565.0335
[18 empty] | TOTAL | 1154331.9235
Name: |  | .......................................... |  |  | Name: |  | .........................................................
[12 empty] | RETENTION MONEY on this certificate TO RETENTION ACCOUNT !!! | [6 empty] | 100376.689 | B
Capacity : |  | .......................................... |  |  | Capacity: |  | ......................................................... |  |  |  |  | Account reference No. : | [5 empty] | VAT 15 % | 15056.5034
2. I have inspected this claim and I am satisfied that payment as |  |  |  |  | 4. I certify that the above-mentioned work has executed satisfactorily | [12 empty] | TOTAL | 115433.1924
indicated can be made. |  |  |  |  | and that the work to the value of the amount has been performed
……………….. |  | ........................................................ | [9 empty] | CESSION PAYMENTS INCLUDED IN THIS CERTIFICATE |  |  |  |  | SUPPLIER |  | AMOUNT
Date |  | On behalf of Project Manager. |  |  | ……………….. |  | ......................................................... | [9 empty] | SIGNATURE
[5 empty] | Date |  | On behalf of IA - Technical Director |  |  |  | 1] | [7 empty] | 0 | C
Name: |  | ........................................................ | [15 empty] | VAT 15 % | 0
[5 empty] | Name: |  | ...................................................... | [10 empty] | TOTAL | 0
Designation: |  | ........................................................
ok | [6 empty] | VAT incl / excl ? | excl |  |  | 2] | [7 empty] | 0
PLK M | CONTRACTOR : |  | Malerate Construction |  | Contract amount as awarded |  | R | 7961440.5462 | vat excl |  |  | VAT cert. no | [5 empty] | VAT 15 % | 0
No. |  |  | PM53/2022 |  | Additional expenditure authorized |  | R |  | vat excl | [8 empty] | TOTAL | 0
[5 empty] | counter funding |  |  | 0 | vat excl
FUND | ADDRESS : | 17 General Joubert Str |  |  |  | sub total | R | 7961440.5462 |  |  | 3] | [7 empty] | 0 | E
|  | Polokwane, 0699 |  |  |  | VAT | R | 1194216.0819 |  |  |  | VAT cert. no | [5 empty] | VAT 15 % | 0
[5 empty] | TOTAL APPROVED AMOUNT |  | R | 9155656.6282 | [9 empty] | TOTAL | 0
[6 empty] | TEL : | 015-590-1843 | FAX : | 086-546-3520
SUMMARY OF PREVIOUS CLAIMS | [10 empty] | 4] | [8 empty] | F
Certificate No. | Date | Amount (VAT excl) | Certificate No. | Date | Amount (VAT excl) | Certificate No. | Date | Amount (vat excl) |  |  |  | VAT cert. no | [5 empty] | VAT 15 % | 0
1 |  |  | 5 |  |  | 9 |  |  | total | [8 empty] | TOTAL | 0
2 |  |  | 6 |  |  | 10 |  |  | of
3 |  |  | 7 |  |  | 11 |  |  | "amount" |  | 5] | [8 empty] | G
4 |  |  | 8 |  |  | 12 | [5 empty] | VAT cert. no | [5 empty] | VAT 15 %
[9 empty] | 0 | [8 empty] | TOTAL | 0
THIS CERTIFICATE No. : |  |  | 1 | is this a cert. of completion | No
PARTICULARS OF PRESENT CLAIM |  |  |  | 12 mth retention | No |  |  | CONTRACT AMOUNTS |  |  | 6] | [8 empty] | H
TO CONTRACTOR FOR WORK DONE UP TO DATE : |  |  |  |  | 28/10/2024 |  |  | R | 9155656.6282 |  |  | VAT cert. no | [5 empty] | VAT 15 % | 0
| Value of all work done [including cession payments] up to date | [5 empty] | [VAT excl.] | 1003766.89 | [9 empty] | TOTAL | 0
| Value of all Nominated sub contractors work up to date | [5 empty] | [VAT excl.] |  |  |  | LIST OF ALL CESSION HOLDERS ON PROJECT
| Escalation of cost up to date | [5 empty] | [VAT excl.] |  |  |  |  | SUPPLIERS |  | VALUE | SIGNATURE |  | PAYMENT TO | [ A ] | 903390.201
[7 empty] | SUBTOTAL | 1003766.89 |  | 1 | [6 empty] | CONTRACTOR | VAT @ 15% | 135508.5302
| Less Any Penalties that may be applicable | [7 empty] | 7961440.5462 | 2 | [7 empty] | TOTAL | 1038898.7312
| Less all previous payments [VAT excl] made up to certificate no. | [5 empty] | 1 | 0 |  | 3
[7 empty] | SUBTOTAL | 1003766.89 |  | 4 | [6 empty] | TOTAL OF | [ B ] | 100376.689 | I
[10 empty] | 5 | [6 empty] | RETENTION | VAT @ 15% | 15056.5034
| Plus materials on site @ 80 % of invoiced payments | [5 empty] | [VAT excl.] |  |  | 6 | [7 empty] | TOTAL | 115433.1924
[7 empty] | SUBTOTAL | 1003766.89 | (A) | 7
[7 empty] | VAT 15 % | 150565.0335 |  | 8 | [7 empty] | [ C+D+E+F+G+H ] | 0
[5 empty] | TOTAL OF PRESENT CLAIM |  |  | 1154331.9235 |  | 9 | [6 empty] | TOTAL OF | VAT @ 15% | 0
AMOUNT IN WORDS : | [9 empty] | 10 | [6 empty] | CESSIONS | TOTAL | 0
Three Million nine handred and seventy five thousand, one handred and two and sexteen cent
CATEGORY | 4A | SUMMARY OF PREVIOUS RETENTION & SURITY RETAINED |  |  |  | total value of retention |  | 100376.689 | total in ret. |  | ```````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````` |  |  |  |  | TOTAL [ VAT incl ] |  |  | 1154331.9235
surety limit % | 10 | Certificate no | Amount | Certificate no | Amount | previous retention held |  | 0 | account
surity bond | NO | 1 |  | 7 |  | retention on this certificate |  | 100376.689 | 100376.689
cash | NO | 2 |  | 8 |  | retention to be paid out |  |  | to be paid
reten. limit % | 10 | 3 |  | 9 |  | on completion certificate % |  | 0 | from ret.
contr. bond | NO | 4 |  | 10 |  | on retention certificate % |  | 0 | account
maint. bond | NO | 5 |  | 11 |  | 0 | o |  | 0 |  |  |  | Signed by Contractor |  |  |  |  | Signed by Project Manager
total reten. | % | 6 |  | 12 |  | PAYMENT TO CONTRACTOR : |  |  | 1038898.7312
& cash to | 10 | surity bond | total previous retention |  | 0 | RETENTION TO RETENTION ACCOUNT. : |  |  | 115433.1924
1 | 0 | only !! | Bond no. = | ……………. | VAT (EXCL) | ALL SESSION PAYMENTS : |  |  | 0
[6 empty] | ( details on sheet B3 ) |  |  | 1154331.9235 |  |  |  | Date |  |  |  |  | Date

## COVER (hidden)
POLOKWANE LOCAL MUNICIPALITY
GA-MAGONGOA ROAD UPGRADE
CONTRACT NO. PM53/2023
SUMMARY CONTRACT DATA/PART B
CLIENT |  |  | POLOKWANE LOCAL MUNICIPALITY
CLEINT AGENT: SMV CIVIL ENGINEERS |  |  | CONTRACTOR: MALERATE CONSTRUCTION
CONTRACT |  |  | GENERAL CONDITION OF CONTRACT (2015)
PROCUREMENT PROCEDURE |  |  | CLOSE BIDDING_FRAMEWORK TERM CONTRACTS
ARITHMETICAL ERRORS AND OMISSIONS |  |  | NONE
PROPOSED AMENDMENTS, AND QUALIFICATIONS CONDITIONS |  |  | NONE
COMMENCEMENT DATE |  |  | ??
COMMENCEMENT WORKS |  |  | ??
CONTRACTUAL DOCUMENTATION COMPLIANCE |  |  | YES | NO | Still in Progress until full approval of all documentation including the BoQ
CIDB GRADING |  |  | 5CE
CONSTRUCTION PERIOD |  |  | 5 MONTHS
PRICING STRATEGY |  |  | BILL OF QUANTITY
SMME'S SUPPLY VALUE |  |  | 4%
SUB CONTRACTING VALUE |  |  | 6%
LOCAL LABOUR VALUE |  |  | 6%
BILL OF QUANTITIES SECHEDULE SECTION BUDGET
| Bill of Quantity Sections |  |  | Dif. % | Engineer Estimate | Original Contractor Offer | New Contractors Offer
| 1200 | General Requirements & Provisions |  | 14.47% | 406239.0198 | 465017.5473 | 401709.0198
| 1300 | Establishment and General Obligations |  | 2.68% | 915465.8815 | 940000 | 915465.88
| 1400 | Housing, Offices & Laboratories |  | -32.4% | 105462.5 | 71287.5 | 101789.95
| 1500 | Accommodation of Traffic |  | -35.12% | 379947.6105 | 246525 | 343585
| 1700 | Clearing and Grubbing |  | 51.35% | 90520 | 137000 | 24200
| 1800 | Dayworks |  | 0% | 55000 | 55000 | 55000
| 2100 | Drains |  | 106.2% | 19200 | 39600 | 39600
| 2200 | Prefabricated Culverts |  | 0% | 0 | 0 | 0
| 2300 | Concrete kerbing, concrete channelling, open concrete chutes and concrete linings for open drains |  | 21.97% | 843748 | 1029105 | 913580
| 3100 | Borrow Materials |  | -6.798% | 363728 | 339000 | 389000
| 3300 | Mass Earthworks |  | 35.68% | 1641135.86 | 2226767 | 1621932.46
| 3400 | Pavement Layers of Gravel Material |  | 28.52% | 520834.0575 | 669363 | 538693.5
| 3500 | Stabilization |  | 0.3223% | 345769.218 | 346883.73 | 331166.3325
| 4100 | Prime Coat |  | 0% | 163680 | 163680 | 163680
| 4200 | Asphalt Seals |  | 56.42% | 1494000 | 2336886.0994 | 1493300
| 5100 | Pitching, Stonework and Protection Against Erosion |  | 57.97% | 27050 | 42730 | 27050
| 5600 | Road signs |  | 32.93% | 28044.1875 | 37280 | 37047.1875
| 5700 | Road Markings |  | -18.06% | 72525 | 59425 | 66025
| 5900 | Finishing the Road and Road Reserve and treating old roads |  | 174.5% | 38250 | 105000 | 49500
| 7300 | Concrete Block Paving for Roads |  | 0% | 0 | 0 | 0
| 8100 | Testing Materials and Workmanship |  | 100% | 70000 | 140000 | 70000
| TOTAL SCHEDULE A : (CARRIED TO SUMMARY) |  |  | 0.02276% | 7580599.3348 | 9450549.8767 | 7582324.3298
0
| TENDER (CONTRACT) SUM |  |  |  |  | 0
| 1) CONTRACT PRICE ADJUSTMENT (± 0%) |  |  |  | 0 | 0 | 0
| 2) CONTINGENCIES (This amount is under the control of the employer) (5%) |  |  |  | 379029.9667 | 472527.4938 | 379116.2165
| SUBTOTAL |  |  |  | 7959629.3015 | 9923077.3705 | 7961440.5462
| ADD 15% VAT |  |  |  | 1193944.3952 | 1488461.6056 | 1194216.0819
| TENDER (CONTRACT) PRICE AS FINAL OFFER |  |  |  | 9153573.6967 | 11411538.9761 | 9155656.6282
CONTRACT VALUE
Comments:
The Contractor was given to price the BoQ on 19 August 2024, The Contractor submitted the priced BoQ on 22 August 2024, during the evaluation of the BoQ it was assessed that some of the rates were overpriced. Therefore on 28 August 2024, the Contractor was requested to revise their BoQ accordingly. Final negotiations to balance the BoQ were held on 13 September 2024.
The following resolutions were taken during the final negotiations for the BoQ to balance:
1. Items No: 1201(a) Relocation and Protection of Service was allocaetd R161 905,04 plus 10% hadling cost of R 16,190.50 and the item was then reduced to 137 508,20 for the Relocation & Protection of services plus 10% handling cost 13,750.82.
2. Items No: B12.31(a) Generic Training was removed from the original Bill in section 1200 to cater for the cost variance from the contractor.
3. Items No: 42.04 (a) The quantity of tack coat in section 4200 was reduced because it will not be utilised.
Approval of Bill of Qantities
| Contractor: Malerate Construction |  | Designation |  |  | Signature | Date
| Principal Agent: SMV Civil Engineers |  | Designation |  |  | Signature | Date
| Employer: Polokwane Municipality |  | Designation |  |  | Signature | Date

## summary A
SCHEDULE A ROAD CONSTRUCTION
PROJECT DESCRIPTION: THE APPOINTMENT PANEL OF CONTRACTORS (40) FOR CONSTRUCTION OF ROADS INFRASTRUCTURE IN POLOKWANE MUNICIPALITY ON AN AS AND WHEN REQUIRED BASIS FOR A PERIOD OF THREE (3) YEARS
SECTION | DESCRIPTION | CONSULTANT AMOUNT | CONTRACTOR AMOUNT | AMOUNT
1200 | General Requirements & Provisions | 406239.0198 | 465017.5473 | R | 514737.5473
1300 | Establishment and General Obligations | 915465.8815 | 940000 | R | 975000
1400 | Housing, Offices & Laboratories | 105462.5 | 71287.5 | R | 127162.5
1500 | Accommodation of Traffic | 379947.6105 | 246525 | R | 413825
1700 | Clearing and Grubbing | 90520 | 137000 | R | 87120
1800 | Dayworks | 55000 | 55000 | R | 55000 | [6 empty] | 6665133.4533
2100 | Drains | 19200 | 39600 | R | 19200 | [6 empty] | 999770.018
2200 | Prefabricated Culverts | 0 | 0 | R | 0
2300 | Concrete kerbing, concrete channelling, open concrete chutes and concrete linings for open drains | 843748 | 1029105 | R | 850103
3100 | Borrow Materials | 363728 | 339000 | R | 370000
3300 | Mass Earthworks | 1641135.86 | 2226767 | R | 1394116.4
3400 | Pavement Layers of Gravel Material | 520834.0575 | 669363 | R | 485811.75
3500 | Stabilization | 345769.218 | 346883.73 | R | 311165.9437
4100 | Prime Coat | 163680 | 163680 | R | 133920
4200 | Asphalt Seals | 1494000 | 2336886.0994 | R | 1621920
5100 | Pitching, Stonework and Protection Against Erosion | 27050 | 42730 | R | 14423
5600 | Road signs | 28044.1875 | 37280 | R | 28044.1875
5700 | Road Markings | 72525 | 59425 | R | 72525
5900 | Finishing the Road and Road Reserve and treating old roads | 38250 | 105000 | R | 38250
7300 | Concrete Block Paving for Roads | 0 | 0 | R | 0
8100 | Testing Materials and Workmanship | 70000 | 140000 | R | 70000
TOTAL SCHEDULE A : (CARRIED TO SUMMARY) |  | 7580599.3348 | 9450549.8767 | R | 7582324.3285 |  | 9767771.64 |  | 6092586.7812 | 913888.0172
976777.164
TENDER (CONTRACT) SUM |  | 7580599.3348 | 9450549.8767 | R |  | 1869950.5419 | 10744548.804
1) CONTRACT PRICE ADJUSTMENT (7%) (APPLICABLE INDICES) |  | 0 | 0 | R |  |  | 12356231.1246 |  |  | Budget
2) CONTINGENCIES (This amount is under the control of the employer) (10%) |  | 379029.9667 | 472527.4938 | R |  |  |  |  | 7959629.3015 | 11000000 | -3040370.6985
SUBTOTAL |  | 7959629.3015 | 9923077.3705
ADD 15% VAT |  | 1193944.3952 | 1488461.6056 | R | 9155656.6267
TENDER (CONTRACT) PRICE CARRIED TO FORM OF OFFER OF ACCEPTANCE |  | 9153573.6967 | 11411538.9761 | R | 9155656.6255
0.80213
17550
20000
75
Rate only
Rate Only
[8 empty] | Rate Only | 100
,,,,,,,,,,,,,
,,,

## 1200
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference | OLD rateS |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | RATE | AMOUNT | [9 empty] | AMOUNT
GENERAL REQUIREMENTS AND PROVISIONS
12.02 |  | Services
|  | a) Relocation and Protection of existing services | P.C. Sum | 1 | 137508.1998 | 137508.1998 | 17.74% |  |  | 161905.043 | 0 |  | 6.1425
|  | b) Handling cost and profit in respect of subitem 12.02(a) | % | 0 | 10% | 0 | 0% | 10% |  | 10% | 0
|  | Project Name Board | No | 1 | 15000 | 15000 | 33.33% | 25000 |  | 20000 | 20000 | approved
B12.31 |  | Accredited training
|  | (a) Entrepreneurial skills | P.C. Sum | 1 | 75000 | 75000 |  |  |  | 75000 | 75000
|  | (b) Allow a provisional sum for payment of salary for 1 student(@R4500 p/m) | Prov. Sum | 1 | 22500 | 22500 | 0% |  |  | 22500 | 22500
|  | (c) Handling cost and profit in respect of subitem 12.31(a) and (b) above | % | …….. | 10% | #VALUE! | 0% | 10% |  | 10% | #VALUE!
B12.34 |  | Public Participation
(a) Allow a provisional sum for payment
|  | of salary for CLO (@R4500 p/m) | Prov Sum | 1 | 4500 | 4500 | 0% |  |  | 4500 | 4500 |  |  |  |  | 4500 | 8 | 36000
|  | (b) Allow a provisional sum for payment of a (6-10) member Project Steering Committee (@R140/sitting/month) including induction | Prov. Sum | 1 | 7000 | 7000 | 0% |  |  | 7000 | 7000 |  | 7000 |  |  | 8 | 5 | 175 | 2 | 14000
|  | (c) Allow a provisional sum for payment of salary of a Safety Representative(@R4500 p/m) | Prov. Sum | 1 | 22500 | 22500 | 0% |  |  | 22500 | 22500 |  |  |  |  | 8 | 4500 | 36000 |  | 0
(d) Handling cost and profit
|  | in respect of sub-item B12.34 (a) to (c) | % | 0 | 10% | 0 | 0% | 10% |  | 10% | 0
PSA6.3 |  | Occupational Health & safety
Provision for the cost of the Occupational Health &Safety Act, 85 of 1993, and the relevant regulation
|  | a) Preparation of Health & Safety File | Sum | 1 | 25000 | 25000 | -60% | 22000 |  | 10000 | 10000 | approved
|  | c) Health & safety induction training of employees | Sum | 1 | 30530 | 30530 | -83.62% | 15000 |  | 5000 | 5000 | approved
|  | d) Compilation and keeping up with date the Health & Safety file which shall include all documentation required in terms of the Act. | Sum | 1 | 20000 | 20000 | -75% | 132000 |  | 5000 | 5000 | approved
1200 |  | TOTAL CARRIED TO SUMMARY |  |  |  | #VALUE! |  |  |  |  | #VALUE! | 0 | 7006.1425 | 0 | 0 | 4516 | 4513 | 72175 | 2 | 14000
#VALUE!
378910

## 1300
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
CONTRACTORS ESTABLISHMENT ON SITE
AND GENERAL OBLIGATIONS
B13.01 |  | The contractors general obligations :
|  | (a) Fixed obligations | Lump sum | 1 | 215465.8815 | 215465.8815 | -100%
|  | (b) Value-related obligations | Lump sum | 1 | 100000 | 100000 | -100%
|  | (c) Time-related obligations | Month | 1 | 120000 | 120000 | -100%
1300 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 435465.8815

## 1400
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | AMOUNT | AMOUNT
RATE
HOUSING, OFFICES AND LABORATORIES FOR
THE ENGINEER'S SITE PERSONNEL
14.01 |  | Office and laboratory accommodation:
The provision of accommodation as specified, including roof, external and internal walls, windows complete with glazing, doors with locks and fittings burglar proofing, painting, floors, fencing, the provision of a 220/250 volt electrical installation
with wiring, switchboards, etc, water and sewerage installation, and stores, complete, in accordance with the drawings and specifications, except for items scheduled elsewhere :
|  | (a) Offices (interior floor space only) | m² | 1 | 1100 | 1100 | -100%
|  | (b) Laboratories (interior floor space only) | m² | 1
|  | (c) Open concrete working floors, 150mm thick | m² | 1
|  | (d) Roofs over open concrete working floors | m² | 1
|  | (e) Ablution units | m² | 1 | 2500 | 2500 | -100%
|  | (f) Stores | m² | 1 | 650 | 650 | -100%
14.02 |  | Office and laboratory furniture:
|  | (a) Chairs (heavy duty plastic chairs) | No. | 1
|  | (d) Desks, complete with drawers and locks | No. | 1 | 4000 | 4000 | -100%
|  | (f) Conference tables | No. | 1 | 4000 | 4000 | -100%
B14.03 |  | Office and laboratory fittings, installations
and equipment:
(a) Items measured by number :
|  | (i) 220/250 volt power points | No. | 1 | 450 | 450
(iii) Double 80 watt fluorescent-light
|  | fittings complete with ballast and tubes | No. | 1 | 350 | 350
(vi) Wash-hand basins complete with
|  | taps and drains | No. | 1 | 3500 | 3500 | -100%
(vii) Laboratory basins complete with swan-
|  | neck taps and drains | No. | 1
(viii) Extractor fans installed complete with own power
|  | connection | No. | 1
(x) Fire extinguishers, 9,0kg, all purpose dry
|  | powder type, complete, mounted on wall with brackets | No. | 1 | 1000 | 1000 | -100%
(xi) Air-conditioning units with, 2,2kW
minimum capacity, mounted and with
|  | own power connection | No. | 1
(xiv) General - purpose steel cupboards
|  | with shelves | No. | 1 | 2500 | 2500 | -100%
14.03 |  | (b) Prime-cost items and items paid for in a lump sum
|  | (ii) 1. Supply of cellular telephones: | PC Sum | 1
|  | 2. Cost of calls and internet charges | PC Sum | 1
B14.03 |  | (c) Items measured by area:
|  | (viii) Notice boards as specified | m2 | 1 | 650 | 650 | -100%
14.04 |  | Car ports
added |  | Car ports as specified, at offices and laboratory building | No. | 1 | 4500 | 4500
1400 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 25200
919062.5

## 1500
PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE | [5 empty] | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
| ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
ACCOMMODATION OF TRAFFIC
| B15.01 |  | Accommodating traffic and maintaining
|  |  | temporary deviations: | km | 1 | 10000 | 10000 | -100%
| 15.02 |  | Earthworks for temporary deviations:
|  |  | (a) Shaping of temporary deviations | km | 1 | 4848.407 | 4848.407 | -100%
|  |  | (b) Cut and borrow to fill | m³ | 1 | 90 | 90 | -100%
|  |  | (c) Cut to spoil | m³ | 1
| B15.03 |  | Temporary traffic-control facilities:
|  |  | (a) Flagmen | man-days | 1 | 150 | 150 | -100%
|  |  | (b) Portable STOP and GO-RY signs | No. | 1 | 2500 | 2500 | -100%
|  |  | (d) Amber flicker lights | No | 1
(e) Road signs, R- and TR-series
|  |  | (i) 900mm | No | 1 | 950 | 950 | -100%
|  |  | (ii) 1200mm | No | 1
(f) Road signs, TW-series
|  |  | (i) 1500mm | No | 1 | 1250 | 1250 | -100%
|  |  | (ii) 2400 mm x 400 mm | No | 1
(g) Road signs, STW-, DTG-, TGS- and TG-series
(excluding delineators and barricades)
|  |  | (i) 1600mm x 1200mm | No | 1 | 1250 | 1250 | -100%
|  |  | (ii) 2400 mm x 1800 mm | No | 1
(h) Delineators (DTG50J) (800mm x 200mm):
|  |  | (i) Single | No. | 1
|  |  | (ii) Mounted back to back | No. | 20 | 650 | 13000 | -100%
|  |  | (i) Movable barricade/road sign combination | No. | 8 | 2250 | 18000 | -100%
|  |  | (j) Traffic cones (500mm height) | Lump Sum | 20 | 450 | 9000 | -100%
|  |  | (m) Two-way communication devices | No. | 1 | 17550
| B15.03 |  | (n) Provision of high visibility safety vests and safety hats | No. | 4 | 500 | 2000 | 0%
|  |  | (o) Special information signs as required by Engineer | m2 | 15 | 130 | 1950 | -100%
| 15.04 |  | Relocation of traffic-control facilities | Lump sum | 1 | 75
| 15.05 |  | Gravelling and repair of temporary deviations
and existing gravel shoulders used as
temporary deviations:
|  |  | (a) Temporary deviations | m³ | 375 | 95 | 35625 | -100%
|  |  | (b) Existing gravel shoulders | m³ | 75 | 95 | 7125 | -100%
| 15.06 |  | Watering of temporary deviations | kl | 2400 | 59 | 141600 | -100%
| 15.07 |  | Blading by road grader of:
|  |  | (a) Temporary deviations | km-pass | 1
|  |  | (c) Existing gravel shoulders used as temporary deviations | km-pass | 1
| 15.1 |  | Accommodation of traffic where the road is constructed | km | 1
in half widths
| 1500 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 249338.407

## 1700
PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  |  |  | CONSULTANT'S RATES |  | Rate Difference
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
CLEARING AND GRUBBING
17.01 |  | Clearing and grubbing
(a) Normal areas:
|  | (i) Within the road reserve | ha | 1.44 | 18000 | 25920 | -100%
|  | (ii) In borrow pits | ha | 3.4 | 19000 | 64600 | -100%
17.02 |  | Removal and grubbing of large trees and
tree stumps:
|  | (a) Girth exceeding 1m up to and including 2m | No | 1
|  | (b) Girth exceeding 2m up to and including 3m | No | 1
17.04 |  | Clearing and grubbing at inlets and outlets of hydraulic structures | m2 | 1
1700 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 90520

## 1800
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | AMOUNT | AMOUNT
RATE
18.00 |  | DAYWORKS
B18.01 |  | Labourers
|  | (i) Unskilled | hour | rate only
|  | (ii) Semi-skilled | hour | rate only
|  | (iii) Skilled | hour | rate only
|  | (iv) Survey assistants | hour | rate only
B18.02 |  | Foreman | hour | rate only
B1.03 |  | Tipper truck
|  | (i) 3 - 5 ton | hour | rate only
|  | (ii) 5.1 - 10 ton | hour | rate only
|  | (iii) 10.1 - 15 ton | hour | rate only
B1804 |  | Loader (0.5m3 bucket) | hour | rate only
B18.05 |  | Grader (CAT 14G or similar) | hour | rate only
B18.06 |  | Vibratory roller (as per 33.04(b)(i)) | hour | rate only
B18.07 |  | Grid roller (as per 33.04(b)(iii)) | hour | rate only
B18.08 |  | Walk behind roller (Bomag BW90) | hour | rate only
B18.09 |  | Air compressor, 4m3/min, complete with drills | hour | rate only
B18.10 |  | Waterpump including all necessry hoses | hour | rate only
B18.11 |  | Concrete mixer (0.3m3) | hour | rate only
B18.12 |  | Trench vibrating roller or pad 0.6m width | hour | rate only
B18.13 |  | Backactor, 0.3m3 | hour | rate only
B18.14 |  | Tracked excavator 20t | hour | rate only
B18.15 |  | Watercart, 500l | hour | rate only
B18.16 |  | Allow provisional for purchase of materials | P.C Sum | 1 | 50000 | 50000
B18.17 |  | Handling cost and profit | % | 10% | 50000 | 5000
1800 |  | TOTAL SCHEDULE C: (CARRIED TO TENDER SUMMARY) |  |  |  | 55000

## 2100
PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  |  |  | CONSULTANT'S RATES |  | Rate Difference | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | RATE | AMOUNT | AMOUNT
DRAINS
21.01 |  | Excavation for open drains:
(a) Excavating soft material situated within the
following depth ranges below the surface
|  | level: | [12 empty] | 4.5 | 2 | 8450
|  | (i) 0m up to 1,5m | m³ | 1 | 30 | 30 | -100% | 60 |  |  |  |  | 3718.5
|  | (ii) Exceeding 1,5m and up to 3,0m | m³ | 1 |  |  |  | 85
(b) Extra over subitem 21.01(a) for excavation in
|  | hard material, irrespective of depth | m³ | 1 | 250 | 250 | -100% | 450
21.02 |  | Cleaning and shaping existing open drains (including the 7x1200mm Dia. Culvert) | m³ | 1 |  |  |  | 1155
21.03 |  | Excavation for subsoil drainage systems:
(a) Excavating soft material situated within the
following depth ranges below the surface
level:
|  | (i) 0m up to 1,5m | m³ | 1 |  |  |  | 60
(b) Extra over subitem 21.03(a) for excavtion in
|  | hard material, irrespective of depth | m³ | 1 |  |  |  | 450
21.04 |  | Impermeable backfilling to subsoil drainage
|  | systems | m³ | 1 |  |  |  | 120
21.05 |  | Banks and dykes | m³ | 1 |  |  |  | 120
21.06 |  | Natural permeable material in subsoil drainage
systems (crushed stone):
(b) Crushed stone obtained from commercial
sources ( no overhaul):
|  | (i) 7mm stone aggregate | m³ | 1 |  |  |  | 142.5
(ii) Coarse grade stone (19mm nominal size
|  | aggragate) | m³ | 1 |  |  |  | 661.5 | [5 empty] | 150 | 0.6 | 0.5 | 45
21.07 |  | Natural permeable material in subsoil drainage
systems (sand):
[14 empty] | 150 | 0.6 | 0.3 | 27
|  | (b) Sand from commercial sources (no overhaul) | m³ | 1 |  |  |  | 425
21.08 |  | Pipes in subsoil drainage systems:
(b) Unplasticized PVC pipes and fittings, normal
duty, complete with couplings:
|  | (i) 160mm diameter, perforated | m | 1 |  |  |  | 182
|  | c) High Density PE (160mm dia, perforated) | m | 1 |  |  |  | 136.5
B21.09 |  | Polyethylene sheeting, 0,25mm thick, or similar
approved material, for lining subsoil drainage
|  | systems | m² | 1 |  |  |  | 13
2100 |  | TOTAL CARRIED FORWARD |  |  |  | 280
CONSULTANT'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT | Rate Difference | old rate
|  | AMOUNT BROUGHT FORWARD |  |  |  | 280
21.1 |  | Synthetic-fibre filter fabric:
(a) Non-wowen needle punched type:
|  | (I) Kaymat U24 or approved equivalent | m² | 1 |  |  |  | 36 | [5 empty] | 120 | 3.6 | 432
21.12 |  | Concrete outlet structures, mahole boxes,
junction boxes and cleaning eyes for subsoil
drainage systems:
|  | (a) Outlet structures | No. | 1 |  |  |  | 15000
|  | (b) Manhole Boxes | No | 1 |  |  |  | 15000
|  | (c) Junction boxes | No | 1 |  |  |  | 15000
|  | (d) Cleaning eyes | No | 1 |  |  |  | 850
21.13 |  | Concrete caps for subsoil drain pipes | No. | 1 |  |  |  | 295
21.15 |  | Overhaul for material hauled in excess of 5,0km
|  | free-haul (normal overhaul) | m³-km | 1 |  |  |  | 19
21.17 |  | Test flushing of pipe subsoil drains | No. | 1 |  |  |  | 1550
B21.20 |  | Galvanized wire mesh, 250 x 250mm, at the
outlets of subsoil drainage systems. Mesh
|  | 10mm x 10mm x 2,5mm wire diameter | No. | 1 |  |  |  | 640
2100 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 280

## 2200
PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  |  |  | CONSULTANT'S RATES |  | Rate Difference | Old rate |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | RATE | AMOUNT | AMOUNT
PREFABRICATED CULVERTS
22.01 |  | Excavation:
(a) Excavating soft material situated within the
following depth ranges below the surface level:
|  | (i) 0m up to 1.5m | m³ | 1 |  |  | #DIV/0! | 65
|  | (ii) Exceeding 1.5m up to 3,0m | m³ | 1 |  |  | #DIV/0! | 95
(b) Extra over subitem 22.01(a) for excavation in
|  | hard material irrespective of depth | m³ | 1 |  |  | #DIV/0! | 250
22.02 |  | Backfilling:
|  | (a) Using the excavated material | m³ | 1 |  |  | #DIV/0! | 60
|  | (b) Using imported selected material | m³ | 1 |  |  | #DIV/0! | 220
(c) Extra over subitems 22.02(a) and 22.02(b) for
|  | soil cement backfilling (3% cement) | m³ | 1 |  |  |  | 500
22.03 |  | Concrete pipe culverts:
(b) On Class B bedding:
|  | (i) 525mm dia. (Class 100D) | m | 1 |  |  |  | 1856.4
|  | (ii) 600mm dia. (Class 100D) | m | 1 |  |  | #DIV/0! | 2471.7
|  | (iii) 750mm dia. (Class 100D) | m | 1 |  |  |  | 3706.5
|  | (iv) 900mm dia. (Class 100D) | m | 1 |  |  |  | 5103
|  | (v) 1200mm dia. (Class 100D) | m | 1 |  |  |  | 8673
(c) In inlet and outlet structures, catchpits,manholes, thrust and anchor
blocks, excluding formwork but including Class U2 surface finish:
|  | (i) Class 25/19 concrete | m³ | 1 |  |  | #DIV/0! | 3200
(d) Formwork of concrete under subitem 22.07(c)
|  | (i) Class F1 surface finish | m² | 1 |  |  | #DIV/0! | 550
22.07 |  | Concrete in Culvert bedding
|  | a) 25/19 Concrete | m³ | 1 |  |  | #DIV/0! | 3200
22.1 |  | Steel reinforcement:
|  | (a) Mild steel bars | t | 1 |  |  |  | 28135
|  | (b) High-tensile steel bars | t | 1 |  |  |  | 47250
|  | (c) High tensile steel mesh Reference 245: | t | 1 |  |  | #DIV/0! | 52655
21.17 |  | Manholes, kerb inlets, catch pits, cast in situ inlet and outlet structures complete
|  | (a) Manholes, and junction boxes (standard depth up to 2.0m) | No | 1 |  |  |  | 15000
|  | (c) Cast insitu inlet and outlet structure as per detail drawing 12135/T/2328 for 600mm diameter pipes | No | 1 |  |  |  | 15000
|  | (d) Extra over or less than subitem 22.17(a) for variations in the depths of manholes, and junction boxes from the standard depth designated for tendering purposes (standard depth = 2.0m) | m | 1 |  |  |  | 12000
|  | (f) Kerb inlet complete (as per detail standard length = 2.0m) | No | 1 |  |  |  | 15000
2200 |  | TOTAL CARRIED FORWARD |  |  |  | 0
[5 empty] | CONSULTANT'S RATES |  | Rate Difference | Old rate
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | AMOUNT BROUGHT FORWARD |  |  |  | 0
|  | (g) Extra over or less than subitem 22.17(f) for variations in the lengths of kerb inlets from the standard length designated for tendering purposes (standard length = 6.0m, type as shown on drawing 12135/T/239) | m | 1 |  |  |  | 45000
22.28 |  | Prefabricated reinforced concrete skew end units for
concrete culverts constructed at skew angle.
|  | (i) 600mm dia. (Class 75D) | No. | 1 |  |  |  | 2236.5
|  | (iii) 750mm dia. (Class 50D) | No. | 1 |  |  |  | 3517.5
2200 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 0

## 2300
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
23 |  | CONCRETE KERBING, CONCRETE CHANNELLING
OPEN CONCRETE CHUTES AND CONCRETE
LININGS FOR OPEN DRAINS
23.01 |  | Concrete kerbing: Class 25/19 cast in-situ concrete
|  | (a) Prefabricated barrier kerbs SABS 927 (1969) fig 7 dwg | m | 1
[16 empty] | Dia | Rad. | Rad. | Kerb | Total kerb on 1 bellmouth | Total Qty
23.02 |  | Concrete kerbing-channelling combination | [13 empty] | 40 | 20 | 125.7143 | 35.4286 | 70.8571 | 283.4286
(Class 25/19 cast in situ concrete in channel):
|  | (a)(i) Prefabricated mountable kerbs SABS 927 (1969) fig 8 | m | 1 | 250 | 250 | -100% |  |  |  |  | kerb supply price | 150 | Nazara kerb supply
|  | (ii) Class 20/19 cast in-situ concrete in channel | m | 1
|  | (b) Prefabricated mountable kerbs SABS 927 (1969) fig 3 dwg | [12 empty] | 53.84 | 2 | 107.68
|  |  | m | 1
[16 empty] | 3.5 | 18 | 18.3371
23.03 |  | Concrete chutes: | [15 empty] | 0
|  | (a) Prefabricated concrete chutes SABS 927 class 75 fig 7 | m | 1 | [11 empty] | 3.5 | 12 | 12.5
23.04 |  | Cast in situ concrete chutes ( measured by compoments)
|  | (a) (i) Structural concrete (Class 25/19) | m³ | 1
|  | (ii) Mass concrete (Class 15/38) | m³ | 1
|  | (b) Vertical Formwork (Class F1 surface finish) | m² | 1 | [10 empty] | #NAME?
23.06 |  | Inlet, outlet, transition and similar structures
(measured by components):
(a) Concrete (Class 20/19)
|  | (i) In side inlets | m³ | 1
|  | (ii) in transition and outlet structures | m³ | 1
|  | (iii) Energy breaker blocks | m³ | 1 | 350 | 350 | -100%
|  | (b) Formwork: | [9 empty] | supply
|  | (i) Class F1 surface finish | No | 1 | [7 empty] | 3Q _concrete supply | 1636 | transport
23.07 |  | Trimming of excavations for concrete-lined
open drains:
|  | (a) In soft material | m³ | 1
|  | (b) In hard material | m³ | 1
23.08 |  | Concrete lining for open drains:
|  | (a) Cast in situ concrete V-drain (Class 25/19) | m³ | 1 | 2450 | 2450
23.12 |  | Steel reinforcement:
|  | (b) High tensile steel bars Y10 | kg | 1
|  | (c) Welded steel fabric (High-tensile steel) ref 245 | m² | 1 | 52.8 | 52.8
2300 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 3102.8
9
63

## 3100
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | AMOUNT | AMOUNT
RATE
BORROW MATERIALS
31.01 |  | Removal of excess overburden | m³ | 1 | 50 | 50 | -100%
31.03 |  | Finishing-off borrow areas in:
|  | (a) Hard material | ha | 1 | 35000 | 35000 | -100%
|  | (b) Intermediate material | ha | 1 | 25000 | 25000 | -100%
|  | (c) Soft material | ha | 1 | 20000 | 20000 | -100%
B31.04 |  | Compensation to landowners:
|  | (a) Prime cost sum for compensation to landowners | P.C. sum | 1 | 50000 | 50000 | -100%
|  | (b) Handling costs and profit in respect of subitem B31.04(a) above | % | 50000 | 10% | 5000 | -100%
B31/55.02 |  | Fencing of borrow pits | km | 1 | 41864 | 41864 | -100%
3100 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 176914

## 3300
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference | old rate
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  |  | RATE | AMOUNT | AMOUNT
RATE
MASS EARTHWORKS
33.01 |  | Cut and borrow to fill, including free-haul up
to 1.0km:
(a) Material in compacted layer thicknesses of
200mm and less:
|  | (ii) Compacted to 93% of modified AASHTO density | m³ | 1 | 100 | 100 | -100% | 150
33.03 |  | Extra over item 33.01 for excavating and
breaking down material in:
|  | (a) Intermediate excavation | m³ | 1 | 220 | 220 | -100% | 120
|  | (b) Hard excavation | m³ | 1 | 510 | 510 | -100% | 300
0
33.04 |  | Cut to spoil, including free-haul up to 0,5km.
Material obtained from:
|  | (a) Soft excavation | m³ | 1 | 95 | 95 | -100% | 180 |  |  |  |  | 1846.8
|  | (b) Hard excavation | m³ | 1 | 275 | 275 | -100% | 220
|  | (c) Intermediate excavation | m³ | 1 | 220 | 220 | -100% | 200
|  | (d) Boulder excavation Class B | m³ | 1 | 450 | 450 | -100% | 250
33.06 |  | Variations in the number of roller passes (applicable to subsubitem 33.01(a)(iii) and 33.01(b)(iii) and item 33.11)
|  | (a) Vibratory rollers | m2-pass | 1 |  |  |  | 138
|  | (b) Grid rollers | m2-pass | 1 |  |  |  | 174
33.07 |  | Removal of unsuitable material (including free-haul of 0,5km):
(a) In layer thicknesses of 200mm and less:
|  | (ii) Unstable material | m³ | 1 |  |  |  | 85
33.08 |  | Widening of cuts(extra over items 33.01, 33.02 and 33.04)
(b) In boulder material
|  | class A or class B | m³ | 1 |  |  |  | 140
33.1 |  | Roadbed preperation and the compaction of material
|  | (b) Compaction 150mm thick to 93% of modified AASHTO density | m³ | 1 | 115 | 115 | -100% | 120
33.11 |  | Three roller passes compaction in collapsible sandy material on the road to a layer thickness of 600mm below the roadbed:
|  | (a) Vibratory roller | m² | 1 |  |  |  | 138
|  | (b) Oscillatory Roller | m² | 1 |  |  |  | 245
|  | (c) Grid roller | m² | 1 |  |  |  | 174
33.12 |  | In situ treatment of roadbed:
|  | (a) In situ treatment by ripping | m³ | 1 | 65 | 65 | -100% | 75
|  | (b) In situ treatment by blasting | m³ | 1 |  |  |  | 2850
33/16.00 |  | Overhaul on material hauled in excess of 1.0km | m³-km | 1 | 17 | 17
3300 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 2067
70161.4
70178.4

## 3400
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
34 |  | PAVEMENT LAYERS OF GRAVEL MATERIAL
34.01 |  | Pavement layers constructed from gravel taken
from cut or borrow, including free-haul up to 1.0km
(a) Gravel selected layers compacted to:
|  | (i) 93% of modified AASHTO density (150mm) | m³ | 1 | 104.15 | 104.15
|  | (ii) 95% of modified AASHTO density (150mm) | m³ | 1
c) Gravel subbase layer G6 (unstabilised material) compacted to:
|  | (i) 95% of modified AASHTO density:(150mm approved gravel) | m³ | 1
d) Gravel subbase C3 material (chemically stabilized material) compacted to:
|  | (i) 97% of modified AASHTO density:(150mm approved gravel) | m³ | 1
(f) Gravel base C4 Material (chemically stabilized material) compacted to:
|  | (i) 98% of Modified AASHTO density (150mm) | m³ | 1 | 115 | 115 | -100%
Crushed-stone base:
36.01 |  | c) Constructed from type G2 material obtained | m³ | 1
from commercial sources and compacted to
85% of bulk density(150mm)
(g) Gravel shoulders compacted to:
|  | (i) 95% of modified AASHTO density (200mm) | m³ | 1 | 115 | 115 | -100%
34.01/1601 |  | Overhaul in excess of 1km | m³-km | 1 | 17 | 17 | -100%
34.02 |  | Extra over item 34.01 for excavation of material in:
|  | (a) Intermediate excavation | m³ | 1
|  | (b) Hard material | m³ | 1
3400 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 351.15

## 3500
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT |  |  |  | AMOUNT
[11 empty] | 205 | 0.15 | 30.75
35 |  | STABILIZATION
35.01 |  | Chemical stabilization extra over unstabilized
compacted layers:
|  | (a) Base layer, 150mm thick | m³ | 1 | 100 | 100 | -100%
|  | (b) Subbase layer, 150mm thick | m³ | 1 | 100 | Rate Only | -100%
35.02 |  | Chemical stabilizing agent:
|  | (a) Ordinary portland cement | t | 1 | 2800 | 2800 | -100%
|  | (b) Slaked road lime | t | 1
35.04 |  | Provision and application of water for curing | kl | 1 | 99.3 | 99.3 | -100%
35.13 |  | Extra over item 35.01 for trial sections | m² | 1
3500 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 2999.3

## 4100
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | AMOUNT | AMOUNT
41 |  | PRIME COAT
41.01 |  | Prime coat:
|  | (a) MC-30 cut back bitumen | litre | 1 | 22 | 22 | -100%
Application rate of 0,8 l/m2
|  | (b) MSP1 | litre | 1
Application rate of 0,8 l/m2
41.02 |  | Aggregate for blinding | m³ | 1
41.03 |  | Extra over item 41.01 for applying the prime
coat in areas accessible only to hand held
|  | equipment | litre | 1
4100 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 22

## 4200
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference
ITEM | LI | DESCRIPTION | UNIT | QTY | Rate | Amount |  | RATE | Rate | Amount | AMOUNT
42 |  | ASPHALT BASE AND SURFACING
42.02 |  | Asphalt surfacing
( 60/70 penetration grade bitumen)
(a) Medium continously graded asphalt
|  | (i)Thickness - 30mm | m² | 1 | 200 | 200 | -100%
|  | (ii)Thickness - 40mm | m² | 1 | 201 | 201 | -100%
42.03 |  | Rolled in chippings (9.5mm)
|  | (a) in surfacing | t | 1
42.04 |  | Tack coat of 30% stable grade emulsion | litre | 1
|  | a) Application rate of 0,5 l/m2 | litre | 1 | 30 | 30 | -100%
4200 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 431

## 5100
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference | old rate |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QTY | Rate | Amount |  |  | RATE | Rate | Amount | AMOUNT
5100 |  | PITCHING, STONEWORK AND PROTECTION AGAINST EROSION
51.01 |  | Stone pitching (complete with excavations trimming and compaction)
|  | (b) Grouted stone pitching | m2 | 1 | 350 | 350 | -100% | 350
51.05 |  | Concrete Edge Beams
|  | (a) Class 30/19 | m3 | 1 | 3050 | 3050 |  | 3800
5100 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 3400

## 5600
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
ROAD SIGNS
56.01
semi-matt background. Symbols, lettering and
borders in semi-matt black or in Class 1 retro-
reflective material, where the sign board is
constructed from:
|  | (i) Area not exceeding 2m² | m² | 1 | 620 | 620 | -100%
|  | (ii) Area exceeding 2m² but not exceeding 10m2 | m² | 1
56.02 |  | Extra over item 56.01 for using:
(a) Background of retro-reflective material:
|  | (i) Class l | m² | 1 | 70 | 70 | -100%
56.03 |  | Road sign supports (over-head road sign
|  | structures excluded): |  | 1
(a) Steel tubing
"D"-shaped steel tubing profile
|  | (i) 75mm diameter and 3.5mm wall thickness | t | 1 | 32000 | 32000 | -100%
56.05 |  | Excavating and backfilling for road sign
|  | supports (not appicable for kilometre posts) | m³ | 1 | 120 | 120 | -100%
56.06 |  | Extra over item 56.05 for cement-treated soil
|  | backfill | m³ | 1 | 45 | 45 | -100%
56.09 |  | Dismantling and storing road signs with a
surface area of:
|  | (a) Up to 2m² | No | 1
|  | (b) Exceeding 2m² but not 10m² | No | 1
B56.10 |  | Danger plates (Types W401 and W402)
|  | (a) Size 200mm x 800mm at stormwater culverts | No | 1 | 400 | 400 | -100%
|  | (b) Size 300mm x 1200mm at bridge structures | No | 1
5600 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 33255

## 5700
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  |  | RATE | AMOUNT | AMOUNT
RATE
5700 |  | ROAD MARKINGS
57.02 |  | Retro-reflective road-marking paint:
(a) White lines (broken or unbroken):
|  | (i) 100mm wide | km | 1 | 18000 | 18000 | -100%
|  | (ii) 200mm wide | km | 1
|  | (iii) 500mm wide | km | 1
(b) Yellow lines (broken or unbroken):
|  | (1i) 150mm wide | km | 1
|  | (d) White lettering and symbols | m² | 1 | 195 | 195 | -100%
|  | (e) Yellow lettering and symbols | m² | 1 | 195 | 195 | -100%
(f) Transverse lines, painted island and
|  | arrestor bed markings (any color) | m² | 1
57.04 |  | Variation in rate of application
|  | (a) White paint | liter | 1
|  | (b) Yellow paint | liter | 1
|  | (c ) Reflective beads | kg | 1
B57.05 |  | Supply and install road studs
(a ) Uni-directional
|  | (i) 360˚ Clear - All colours | No. | 1
|  | (ii) Ferolinx 48 (steel with shank or approved equivalent) - All colours | No. | 1
|  | (iii) Swanmank (or similar approved) - All colours | No. | 1
(b) Bi-directional
|  | (ii) Ferolinx 48 (steel with shank or approved equivalent) - All colours | No. | 1 | 0 |  | #DIV/0!
|  | (iii) Swanmank (or similar approved) - All colours | No. | 1
B57.06 |  | Setting out and pre-marking the lines (excluding traffic island markings, lettering and symbols) | km | 1 | 15000 | 15000 | -100%
B57.07 |  | Re-establishing the painting unit at the end of the maintenance period | Sum | 1 | 12000 | 12000 | -100%
5700 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 45390

## 5900
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
59 |  | FINISHING THE ROAD AND ROAD RESERVE
AND TREATING OLD ROADS
59.01 |  | Finishing the road and road reserve:
|  | (b) Single carriageway road | km | 1 | 18000 | 18000 | -100%
|  | (b) Treatment of old roads and temporary deviations | km | 1 | 7500 | 7500 | -100%
5900 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 25500
75
100

## 7300
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | rate difference
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | AMOUNT
7300 |  | CONCRETE BLOCK PAVING FOR ROADS
B73.01
|  | Supply and install concrete interlocking paving blocks including river sand blinding of 25mm (Grey 60mm SA-type) | m2 | 1 | 265 |  | -100% |  |  | 52.5 | 2 | 105
|  | Supply and install concrete interlocking paving blocks 80mm thick including river sand blinding of 25mm (Grey 80mm SA-type) | m2 | 1
|  | Supply and install concrete interlocking paving blocks including river sand blinding of 25mm (Terracotta 60mm SA-type) | m2 | 1 | 265 |  | -100% |  |  | 105 | 2 | 210
|  | Supply and install concrete interlocking paving blocks 80mm thick including river sand blinding of 25mm (Terracotta 80mm SA-type) |  | 1
B73.02 |  | Supply and install prefabricated Figure 10 kerbing as edge restraints | m | 1 | 175 |  | -100% |  |  | 36
7300 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 0
100

## 8100
|  | PANEL OF CONTRACTORS FOR ROAD INFRASTRUCTURE |  |  | CONSULTANT'S RATES |  | Rate Difference |  | CONTRACTOR'S RATES
ITEM | LI | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT |  | RATE | RATE | AMOUNT | AMOUNT
81
81.02 |  | TESTING MATERIALS AND WORKMANSHIP
|  | (for use by the engineer) | P.C Sum | 1 | 70000 | 70000 | -100%
8100 |  | TOTAL CARRIED TO SUMMARY |  |  |  | 70000
17550
20000
75
[5 empty] | 100 |  |  |  | 100