## CONTRACTOR COVER (hidden)
POLOKWANE MUNICIPALITY
CONTRACTOR'S PAYMENT CERTIFICATE
Project Name : |  |  | Ntlolane Water Supply
Contract Number : |  |  | PM38/2022 | [7 empty] | Payment Certificate Number : 2
Contractor's Name : |  |  | Capotex Construction
Contractor's Address : |  |  | 7 Bodenstein Street, Polokwane, 0700 | [7 empty] | Date:03/04/2024
Contractor's VAT Reg. No |  |  | 4880256831 | [7 empty] | Period of contract: 5 months
Consultant : |  |  | Studio Martini Ingegneria
Funder |  |  | Water Services Implementation Grant (WSIG) | [7 empty] | Vote No:
SBU |  |  | Water and Sanitation | [7 empty] | Interim Certificate: |  | Y
[11 empty] | Completion Certificate: |  | N
[11 empty] | Final Completion Certificate: |  | N
1. | TENDERED CONTRACT PRICE | [9 empty] | R c
| 1.1 | Tender sum (excluding contingencies and VAT) | [8 empty] | 6736136.1
| 2 | Approved variations |  | : | a. | Total additions (VO) |  |  |  | * | 0
[5 empty] | b. | Total omissions (Exclusion) |  |  |  | * | 0
[5 empty] | c. | NET VARIATION (a - b) |  |  |  |  | 0
| 3 | Contingencies |  | : | a. | Original allowance |  | 10% |  |  | 673613.61
[5 empty] | b. | Net variation (1.2 c.) |  |  |  |  | 0
[5 empty] | c. | CONTINGENCIES REMAINING (a-b) |  |  |  |  | 673613.61
| 4 | PRESENT CONTRACT PRICE (excluding CPA and VAT) | [8 empty] | 7409749.71
| 5 | Estimate of total CPA allowed on the contract | [5 empty] | 2% |  |  | 0
| 6 | TOTAL TENDERED CONTRACT PRICE (excluding VAT) | [8 empty] | 7409749.71
2. | VALUE OF WORK DONE | [9 empty] | Value to Date | This Certificate | Previous Certificate
[11 empty] | R c | R c | R c
| 1 | Total from Summary of Schedule of Quantities | [7 empty] | * | #REF! | #REF! | 730374
| 2 | Value of materials on site (100%) | [7 empty] | * | 0 | 0 | 0
| 3 | Variations and dayworks completed | [7 empty] | * | 0 | 0 | 0
| 4 | Sub-total (2.1 + 2.2 + 2.3) | [8 empty] | #REF! | #REF! | 730374
| 5 | Contract price adjustment on item 2.4 | [7 empty] | * | 0 | 0 | 0
| 6 | Variations completed which are not subject to CPA | [7 empty] | * | 0 | 0 | 0
| 7 | TOTAL VALUE CERTIFIED excl. materials on site and VAT (2.4 - 2.2 + 2.5 + 2.6) | [8 empty] | #REF! | #REF! | 730374
| 8 | Percentage completeion (to date) / Percentage progress (this certificate)
|  | Including contract price adjustment | [8 empty] | #REF! | #REF! | 9.857%
3. | PAYMENT
|  | Bank Guarantee | Y | N
| 1 | Total value certified (2.7) |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | 730374
| 2 | Less Retention of | 10% |  |  | Up to maximium of | 740974.971 |  |  |  | #REF! | #REF! | 73037.4
| 3 | Less Surety of | 0% |  |  | Up to maximium of | 0 |  | 5 | 0 | 0 | 0 | 0
| 3.1 | release 50 % retention | [8 empty] | 0 | 0
| 4 | Add Materials on site (80%) | [8 empty] | 0 | 0 | 0 | 83993.01
| 5 | Penalties, other debits / bonus, other credits | [8 empty] | 0 | 0 | 0 | 73037.4
| 6 | Sub-total (3.1 - 3.2 - 3.3 + 3.4 ± 3.5) | [8 empty] | #REF! | #REF! | 657336.6 | #REF!
| 7 | Value Added Tax (15%) | [8 empty] | #REF! | #REF! | 98600.49
| 8 | Sub-total (3.6 + 3.7) | [8 empty] | #REF! | #REF! | 755937.09
| 9 | Total amount of previous payments including VAT | [7 empty] | 0 | 755937.09 | ^ These two amounts
| 10 | AMOUNT NOW PAYABLE INCLUDING VAT (3.8 - 3.9) | [7 empty] | #REF! | #REF! | < must be equal
* These figures are to be documented in detail and copies of invoices and/or receipts attached as applicable
| We hereby certify that the quantities of completed work shown in this certificate are accurate and that the rates and amounts are correct. We also certify that the value of materials on site is correct. | [7 empty] | Municipality Certification
Name
Name of Contractor
[10 empty] | Acting Manager:Water and Sanitation |  |  | Date
|  | Signature |  |  |  |  | Date
Name
Name of Engineer
[10 empty] | Director: Water and Sanitation |  |  | Date
|  | Signature |  |  |  |  | Date
[10 empty] | Chief Financial Officer / DFCO |  |  | Date
Ward Cllr / PSC Chairperson
|  | Signature |  |  |  |  | Date |  |  | Municipal Manager |  |  | Date
Summary of Cession Payments
No. | Name of Service Provider (Cessions) |  |  |  |  | Contract amount | Amount Prev. claimed |  | This Certificate |  | Balance | Type of Service Supply-Construction
1 | [10 empty] | 0
2 | [10 empty] | 0
3 | [10 empty] | 0
4 | [10 empty] | 0
5 | [10 empty] | 0
6 | [10 empty] | 0
0
[6 empty] | 0 | 0 |  | 0 |  | 0

## SUMMARY
Water and sanitation Infrastructure BOQ
SUMMARY SCHEDULE OF QUANTITIES
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE | SECTION | DESCRIPTION | AMOUNT
A | 1 | PRELIMINARY AND GENERAL - TIME RELATED OBLIGATIONS
| 2 | PRELIMINARY AND GENERAL - DAYWORK
C | 3 | SITE CLEARANCE
DB | 4 | EARTHWORKS FOR PIPE TRENCHES
LB | 5 | PIPE BEDDING
L | 6 | MEDIUM PRESSURE PIPELINES
LF | 7 | ERF CONNECTIONS (WATER)
GA | 8 | CONCRETE (SMALL WORKS)
H | 9 | CONSTRUCTION OF ELEVATED STEEL TANKS
PME | 10 | ANCILLARY WORKS
VC | 11 | PUMPS
TOTAL SCHEDULE OF QUANTITIES AMOUNT:
CALCULATION OF TENDER SUM
TOTAL SCHEDULE OF QUANTITIES AMOUNT BROUGHT FORWARD:
CONTINGENCIES@5%:
SUB-TOTAL:
ADD 15% VAT:
TOTAL TENDER AMOUNT CARRIED TO FORM OF OFFER:

## A2-P&G TIME RELATED
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE OF QUANTITIES:
SCHEDULE A: PRELIMINARY AND GENERAL OBLIGATIONS
SECTION 1: PRELIMINARY AND GENERAL - TIME RELATED OBLIGATIONS
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
A.1 | TIME RELATED ITEMS:
(As specified in SABS 1200 A, SABS 1200 AB and the Project Specifications.)
1.1 | Scheduled Tie-Related Items:
1.1.1 | Contractual Requirements | Month | 1 |  | 0
1.2 | Facilities for Engineer:
1.2.1 | Furnished offices (2 offices and a Boadroom to fit 12) | Month | 1 |  | 0
1.2.2 | Name boards (1 No) | Month | 1 |  | 0
1.3 | Facilities for Contractor:
1.3.1 | Offices and storage sheds. | Month | 1 |  | 0
1.3.2 | Workshops. | Month | 1 |  | 0
1.3.3 | Laboratories. | Month | 1 |  | 0
1.3.4 | Living accommodation. | Month | 1 |  | 0
1.3.5 | Ablution and latrine facilities. | Month | 1 |  | 0
1.3.6 | Tools and equipment. | Month | 1 |  | 0
1.3.7 | Water supplies, electric power and communications. | Month | 1 |  | 0
1.3.8 | Dealing with water. | Month | 1 |  | 0
1.3.9 | Access. | Month | 1 |  | 0
1.3.10 | Plant. | Month | 1 |  | 0
1.4.1 | Supervision for Duration of the Contract by contracts manager: | Month | 1 |  | 0
1.4.2 | Supervision for Duration of the Contract by site agent: | Month | 1
1.4.3 | Supervision for Duration of the Contract by Forman: | Month | 1
1.5 | Company and Head Office Overhead Costs's for the Duration of the Contract: | Month | 1 |  | 0
1.6 | Environmental Management: | Month | 1 |  | 0
1.7 | Occupational Health and Safety | Month | 1 |  | 0
TOTAL SCHEDULE A - SECTION 2 CARRIED TO SUMMARY: |  |  |  |  | 0

## A4- P&G DAY WORKS
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE OF QUANTITIES:
SCHEDULE A: PRELIMINARY AND GENERAL OBLIGATIONS
SECTION 5: PRELIMINARY AND GENERAL - DAYWORKS
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
A.2 | DAYWORK:
(As specified in SABS 1200 A and the Project Specifications.)
2.1 | Labour - Normal Working Hours: [Provisional]
2.1.1 | Skilled Labour (Artisan). | hr | 1 |  | Rate Only
2.1.2 | Semi-skilled Labour. | hr | 1 |  | Rate Only
2.1.3 | Unskilled Labour. | hr | 1 |  | Rate Only
2.1.4 | Foreman. | hr | 1 |  | Rate Only
2.1.5 | Extra-over rate for items 5.1.1 to 5.1.4 for work during non working hours. | hr | 1 |  | Rate Only
2.3 | Plant - Heavy Equipment: [Provisional]
(Plant shall not be more than 3 years old or have more than 3000 hrs logged. Operator to be qualified and competency certified.)
2.3.1 | Excavator - Size Cat 225. | hr | 1 |  | Rate Only
2.3.2 | Excavator - TLB. | hr | 1 |  | Rate Only
2.3.3 | Grader 140G or similar. | hr | 1 |  | Rate Only
2.3.4 | Front end loader - bucket capacity ≤ 1.5 m3. | hr | 1 |  | Rate Only
2.3.5 | Front end loader - bucket capacity ≤ 1.5 m3. | hr | 1 |  | Rate Only
2.3.6 | Tip truck - 5 m3 capacity. | hr | 1 |  | Rate Only
2.3.7 | Tip truck - 10 m3 capacity. | hr | 1 |  | Rate Only
2.3.8 | Vibratory compaction roller - 13.5 ton. | hr | 1 |  | Rate Only
2.4 | Plant - Small Equipment: [Provisional]
2.4.1 | Pedestrian roller - BW90 or similar. | hr | 1 |  | Rate Only
2.4.2 | Vibratory plate compactor. | hr | 1 |  | Rate Only
2.4.3 | Vibratory rammer. | hr | 1 |  | Rate Only
TOTAL SCHEDULE A - SECTION 5 CARRIED TO SUMMARY: |  |  |  |  | 0

## C-Site Clearance
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE OF QUANTITIES:
SCHEDULE C: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: SITE CLEARANCE
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
C.1 | SITE CLEARANCE
(As specified in SABS 1200 C and the Project Specifications.)
1.1 | Site Clearance:
1.1.1 | Clear vegetation, 800 mm wide. (Provisional) | m | 1 |  | 0
1.1.2 | Clear trees of girth over 1.0 m. | No. | 1 |  | 0
1.1.3 | Over 1m and up to 2m | No. | 1
1.1.4 | Over 2 m and up to 3m | No. | 1
1.1.5 | Re-clear surfaces | ha | 1
1.1.6 | Dismantle and remeove piplelines encased in contrete | m | 6
1.1.7 | Demolish and remove structures/ building and dismantle steelwork, etc.
1.1.8 | Concrete structures with footprint of 200m2 and less, independent of height. | No | 1
1.1.9 | Remove topsoil to nominal depth 150mm stockpile and maintain | m3
1.1.10 | Take down existing fence and reinstate to original position | m | 1 |  | 0
1.2 | Finishing:
Reinstatee road surface complete with all coursed
1.2.1 | a) Gravel on shoulders | m2 | 1
1.2.2 | b) Ashphalt of thickness 20mm | m2 | 1
1.2.3 | c) Asphalt of thickness 25mm roadway | m2 | 1
SUB-TOTAL SCHEDULE C - SECTION 1 CARRIED SUMMARY: |  |  |  |  | 0

## DB-Earthworks(Pipe Trenches (1)
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE OF QUANTITIES:
SCHEDULE DB: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: EARTHWORKS FOR PIPE TRENCHES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
DB.1 | EARTHWORKS: PIPE TRANCHES
(As specified in SABS 1200 DB and the Project Specifications.)
1.1 | Excavation
1.1.1 | a) Excavate in all materials for trenchs, backfill,compact and dispose of surplus material. | m | 1 |  | 0
1.1.2 | b) 1. Extra-over items (a) for excavation in intermediate material. | m3 | 1 |  | 0
1.1.3 | c) 2. Extra-over items (a) for hard rock excavation. | m3 | 1 |  | 0
1.1.4 | d) 3. Extra-over items (a) for hand excavation and backfill where ordered by engineer. | m3 | 1 |  | 0
1.1.5 | e) Soilcrete backfilling where ordered by Engineer. | m3 | 1 |  | 0
1.1.6 | Exceeding 0m but not exceeding 1m | m3 | 1
1.1.7 | Exceeding 1m but not exceeding 2m | m3 | 1
1.1.8 | Exceeding 2m but not exceeding 3m | m3 | 1
1.1.9 | Exceeding 3m but not exceeding 4m | m3 | 1
1.1.10
1.1.11 | Exceeding 4m but not exceeding 5m | m3 | 1
1.1.12
Restricted Excavation
1.1.13 | Hard rock excavation without explosives | m3 | 1
TOTAL SCHEDULE DB - SECTION 2 CARRIED FORWARD: |  |  |  |  | 0

## DB-Earthworks(Pipe Trenches)(2)
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE OF QUANTITIES:
SCHEDULE DB: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: EARTHWORKS FOR PIPE TRENCHES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
SUB-TOTAL SCHEDULE DB - SECTION 2 BROUGHT FORWARD: |  |  |  |  | 0
DB.1 | EARTHWORKS: (Continues)
(As specified in SABS 1200 DB and the Project Specifications.)
1.2 | Backfill and Compaction:
1.2.1.1 | Backfill and Compaction tranches | m3 | 1 |  | 0
1.2.1.2 | Dispose of surplus material | m3 | 1 |  | 0
1.3 | Excavation Ancillaries;
Make up deficiency in backfill material (Provisional)
1.3.1.1 | a) from other necessary excavations on site | m3 | 1 |  | 0
1.3.1.2
1.3.1.3 | (c) importing from commercial or off site source selected by the contractor. | m | 1 |  | 0
1.3.2 | Compaction within road reserve to 90 % of Modified AASHTO density clause 5.7.1. | m3 | 1 |  | 0
1.4 | Overhaul:
1.4.1 | b) Overhaul in excess of the free-haul of 3.0 km. | m3.km | 1 |  | 0
1.5 | Existing Services:
1.5.1 | a) Services that intersect a trench. | No. | 1 |  | 0
EXCAVATION, FILLING, ETC
EXCAVATION, FILLING, ETC OTHER THAN
BULK
1.6 | Excavation in earth not exceeding 2m deep
1.6.1 | Reducing levels under floors | m³ | 1
TOTAL SCHEDULE DB - SECTION 2 CARRIED TO SUMMARY: |  |  |  |  | 0

## LB-Bedding
SCHEDULE OF QUANTITIES:
0
SCHEDULE LB: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: PIPE BEDDING
ITEM NUMBER |  | UNIT | QUANTITY | RATE | AMOUNT
LB 1 | BEDDING:
(As specified in SABS 1200 LB and the Project Specifications.)
1.1 | Provision of Bedding from Trench Excavations:
(Bedding to be Class C for flexible pipes as indicated in the contract drawings)
1.1.1 | b) Provision of bedding from pipe trench excavation within 1.0 km, using selected fill material. | m3 | 1 |  | 0
1.2 | Supply Only of Bedding by Importation:
(Bedding to be Class C for flexible pipes as indicated in the contract drawings)
1.2.1 | b) Provision of bedding imported from designated borrow pit using selected fill material. | m3 | 1 |  | 0
1.3 | Encasing of Pipes in concrete Class A, 19mm stone ,20MPA reinforced & mass concrete:
1.3.1 | Encasement of pipe through stream crossings, Rate shall include formwork, mixing and placing of concrete(5m3) and Gabions (10m3) | m3 | 1 |  | 0
1.4 | Overhaul
1.4.1 | a) Limited overhaul (0,5 km to 1,0 km) | m3 | 1 |  | 0
1.4.2 | b) Long overhaul | m3.km | 1 |  | 0
TOTAL SCHEDULE LB - SECTION 4 CARRIED TO SUMMARY: |  |  |  |  | 0

## L-Pipe Works 1
SCHEDULE OF QUANTITIES:
SCHEDULE L: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: MEDIUM PRESSURE PIPELINES AND ANCILLARIES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
L 1 | MEDIUM PRESSURE PIPES:
(As specified in SABS 1200 L, SABS 1200 GA and the Project Specifications.)
1.1 | Supply, Lay and Bed uPVC Pipes Complete with Couplings
(The rates shall include disinfecting of pipes after completion of hydraulic pipe test.)
1.1.2 | 75 mm mPVC medium pressure pipes - Class 12 | m | 6
1.1.3 | 90 mm mPVC medium pressure pipes - Class 12. | m | 6 |  | 0
1.1.4 | 75 mm mPVC medium pressure pipes - Class 12 | m | 6 |  | 0
1.1.5 | 110 mm mPVC medium pressure pipes - Class 12 | m | 6 |  | 0
1.1.6 | 160 mm mPVC medium pressure pipes - Class 12 | m | 6 |  | 0
1.1.7 | 200 mm mPVC medium pressure pipes - Class 12 | m | 6 |  | 0
1.2 | Fittings and Specials - uPVC Laying Bends:
110 mm uPVC:
1.2.1.1 | uPVC bends less than 90 degree angle. | No. | 1
1.2.1.2 | uPVC bends less than 45 degree angle. | No. | 1
1.2.1.3 | uPVC bends with 22,5 degree angle. | No. | 1
1.2.1.4 | uPVC bends with 11,5 degree angle. | No. | 1
1.2.2 | 90 mm uPVC:
1.2.2.1 | uPVC bends less than 90 degree angle. | No. | 1 |  | 0
1.2.2.2 | uPVC bends less than 45 degree angle. | No. | 1 |  | 0
1.2.2.3 | uPVC bends with 22,5 degree angle. | No. | 1 |  | 0
1.2.2.4 | uPVC bends with 11,5 degree angle. | No. | 1 |  | 0
1.2.3 | 75 mm uPVC:
1.2.3.1 | uPVC bends less than 90 degree angle. | No. | 1 |  | 0
1.2.3.2 | uPVC bends less than 45 degree angle. | No. | 1 |  | 0
1.2.3.3 | uPVC bends with 22,5 degree angle. | No. | 1 |  | 0
1.2.3.4 | uPVC bends with 11,5 degree angle. | No. | 1 |  | 0
1.2.3 | 63 mm uPVC:
1.2.3.1 | uPVC bends less than 90 degree angle. | No. | 1 | 0 | 0
1.2.3.2 | uPVC bends less than 45 degree angle. | No. | 1 | 0 | 0
1.2.3.3 | uPVC bends with 22,5 degree angle. | No. | 1 | 0 | 0
1.2.3.4 | uPVC bends with 11,5 degree angle. | No. | 1 |  | 0
1.2.4 | Specials and Fittings - uPVC Equal Tees Cast Iron:
(Bitumen dipped and LAYING sockets on all sides all to SABS 546 and SABS 966.)
1.2.4.2 | 315mm dia | No. | 1 |  | 0
1.2.4.2 | 250mm dia | No. | 1 |  | 0
1.2.4.3 | 160mm dia | No. | 1
1.2.4.4 | 90mm dia | No. | 1
1.2.4.5 | 75mm Dia | No. | 1
SUB-TOTAL SCHEDULE L - SECTION 5 CARRIED FORWARD: |  |  |  |  | 0

## L-Pipe Works 2
0
SCHEDULE OF QUANTITIES:
SCHEDULE L: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: MEDIUM PRESSURE PIPELINES AND ANCILLARIES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
SUB-TOTAL SCHEDULE L - SECTION 5 BROUGHT FORWARD: |  |  |  |  | 0
L 2 | MEDIUM PRESSURE PIPES: (continues)
(As specified in SABS 1200 L, SABS 1200 GA and the Project Specifications.)
1.2.5 | Specials and Fittings - Cast iron for uPVC class 12 pipes, End Caps:
1.2.5.1 | 90 mm dia. | No. | 1 |  | 0
1.2.5.2 | 75 mm dia. | No. | 1 |  | 0
1.2.5.3 | 110mm dia | No. | 1
1.2.5.4 | 160mm dia | No. | 1
1.2.5.5 | 250mm dia | No. | 1
1.2.6 | Specials and Fittings - Cast ironReducers Class 12:
(Bitumen dipped and LAYING sockets on all sides all to SABS 546 and SABS 966.)
1.2.6.1 | 90 mm x 75 mm | No. | 1 |  | 0
1.2.6.2 | 110mm x 75mm | No. | 1
1.2.6.3 | 110mm x 90mm | No. | 1
1.2.6.4 | 160mm x 90mm | No. | 1
1.2.6.5 | 250mm x 160mm | No. | 1
1.2.7 | Specials and Fittings - uPVC Equal Crosses Class 12:
(Bitumen dipped and LAYING sockets on all sides all to SABS 546 and SABS 966.)
1.2.7.2 | 75mm x 75 mm | No | 1 |  | 0
1.2.8 | Specials and Fittings - uPVC Reducing Crosses Class 12:
(Bitumen dipped and LAYING sockets on all sides all to SABS 546 and SABS 966.)
1.2.8,1 | 90 mm x 75mm dia. [S] | No. | 1 |  | 0
1.2.8,2 | 75 mm x 63mm dia. [S] | No. | 0 |  | 0
1.2.9 | Specials and Fittings - uPVC Reducing Tee Class 12:
1.2.9.1 | 90 mm x 75mm dia. [S] | No. | 1 |  | 0
1.2.9.2 | 75 mm x 63mm dia. [S] | No. | 1 |  | 0
1.2.9.3 | 110mm x 75mm dia. [S] | No. | 1
1.2.9.4 | 110mm x 90mm dia. [S] | No. | 1
SUB-TOTAL SCHEDULE L - SECTION 5 CARRIED FORWARD: |  |  |  |  | 0

## L-Pipe Works 3
0
SCHEDULE OF QUANTITIES:
SCHEDULE L: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 5: MEDIUM PRESSURE PIPELINES AND ANCILLARIES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
SUB-TOTAL SCHEDULE L - SECTION 5 BROUGHT FORWARD: |  |  |  |  | 0
L 3 | MEDIUM PRESSURE PIPES: (continues)
(As specified in SABS 1200 L, SABS 1200 GA and the Project Specifications.)
1.2.10 | Specials and Fittings -Scour valves:
All gate valves shall be of the AVK type, shall comply with the requirements of SABS 664 and shall be suitable for a working pressure of 1,6 MPa (Class 16)
1.2.10.1 | 75 mm Gate Valve | No. | 0 |  | 0
SCOUR VALVE CHAMBER Chamber: 2 m × 2 m or larger, Depth: 2.5 m to 3 m+ fully installed with all special pipes, fittings and valve box for all depths on uPVC pipes (fittings rating PN16).
1.1.10.2 | Scour Valve Chamber
1.1.10.3 | VJ Coupling (315mm) | No. | 1
1.1.10.4 | VJ Coupling (355mm) | No. | 1
1.1.10.5 | VJ Coupling (400mm) | No. | 1
1.1.10.6 | Dismantling joint (315mm) | No. | 1
1.1.10.7 | Scour Tee (315mmx110mm) | No. | 1
1.1.10.8 | Scour Tee (315mmx160mm) | No. | 1
1.1.10.9 | Flushing pipe (160mm) | No. | 1
1.1.10.10 | Anchor piece (315mm) | No. | 1
1.1.10.11 | Manhole Cover/ Concrete lid | No. | 1
1.1.10.12 | Gate valve (80) | No. | 1
1.1.10.13 | Step Ladder | No. | 1
1.1.10.14 | Flushing pipe (160mm) | No. | 1
1.1.10.15 | uPVC pipe (110mm) 6m | No. | 1
1.2.11 | Specials and Fittings - Air Valve:
(Vent O' Mat SERIES RBX with screwed BSP male inlet, or similar. Complete with flange, barrel nipple, and gate valves)
1.2.11.1 | 50mm Air Valve | No. | 1 |  | 0
1.2.12 | Specials and Fittings -Gate valve:
All gate valves shall be of the AVK type or similar, shall comply with the requirements of SABS 664 and shall be suitable for a working pressure of 1,6 MPa (Class 16).
1.2.12.1 | 300 mm Gate Valve | No | 1
1.2.12.2 | 250 mm Gate Valve | No | 1
1.2.12.3 | 200 mm Gate Valve | No | 1
1.2.12.4 | 160 mm Gate Valve | No | 1
1.2.12.5 | 110 mm Gate Valve | No | 1
1.2.12.6 | 90 mm Gate Valve | No | 1 |  | 0
1.2.12.7 | 75 mm Gate Valve | No | 1 |  | 0
1.2.12.8 | 63 mm Gate Valve | No | 1 |  | 0
(Kent or Similar approved,flanged and Drilled to SABS 1123,Table 16.)
1.2.13.1 | 90 mm dia.In Line Bulk Water Meter | No. | 0 |  | 0
1
SUB-TOTAL SCHEDULE L - SECTION 5 CARRIED FORWARD: |  |  |  |  | 0

## L-Pipe Works 4
0
SCHEDULE OF QUANTITIES:
SCHEDULE L: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 5: MEDIUM PRESSURE PIPELINES AND ANCILLARIES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
SUB-TOTAL SCHEDULE L - SECTION 5 BROUGHT FORWARD: |  |  |  |  | 0
L 4 | MEDIUM PRESSURE PIPES: (continues)
(As specified in SABS 1200 L, SABS 1200 GA and the Project Specifications.)
1.2.14 | Thrust Blocks:
1.2.14.1 | Concrete volume < 0,5m³ | No. | 1 |  | 0
1.2.14.2 | Concrete pipe line marker | No. | 1 |  | 0
1.2.15 | Valve Chambers:
1.2.15.1 | Valve chamber - Chamber: 1.2 m × 1.2 m, Depth: 1.5 m to 2 m complete including excavation, materials, plant, labour. | No. | 1 |  | 0
1.2.15.2 | Extra-over Item 3.15.1 for depth increments of 250 mm. | No. | 1 |  | 0
1.2.16 | Air Valve Chambers 2m x 2m, 2m x3m +depth complete including excavation and labour
1.2.16.1 | Equal Tee (315mm) | No. | 1
1.2.16.2 | VJ Coupling (315mm) | No. | 1
1.2.16.3 | Anchor piece (315mm) | No. | 1
1.2.16.4 | Air Valve (80mm) | No. | 1
1.2.16.5 | Adaptor (315 X 80) | No. | 1
1.2.16.6 | Gate valve (80) | No. | 1
1.2.16.7 | Dismantling Joint (315mm) | No. | 1
1.2.16.8 | Step Ladder | No. | 1
1.2.16.9 | Manhole Cover/Concrete Lid | No. | 1
1.2.16.10 | Air Valve (100mm) | No. | 1
1.2.16.11 | Anchor piece (400mm) | No. | 1
1.2.16.12 | Adaptor (355 X 100) | No. | 1
1.2.16.13 | Nips | No. | 1
1.2.16.14 | Gate valve (100) | No. | 0
1.2.16.15 | Drain pipe ( 110mm uPVC) | No. | 1
1.2.17 | Concrete Manholes
1.2.17.1 | a) 550 mm x 550 mm Fabricated manhole not exceeding 1.5m with cover and frame, galvanised | No | 1 |  | 0
1.2.17.2 | b) Extra -over for manhole of the depth exceeding 1.5m | No | 1 |  | 0
SUB-TOTAL SCHEDULE L - SECTION 5 CARRIED TO SUMMARY:

## L-Pipe Works Sewers
WATER AND SANITATION INFRASTRUCTURE BOQ THE APPOINTMENT PANEL OF CONTRACTORS (30) FOR CONSTRUCTION OF WATER AND WASTEWATER INFRASTRUCTURE IN POLOKWANE ON AS AN WHEN REQUIRED FOR A PERIOD OF THREE YEARS
SCHEDULE OF QUANTITIES:
SCHEDULE L: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 5: MEDIUM PRESSURE PIPELINES AND ANCILLARIES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
L 1 | SEWER PIPEWORK
As specified in SABS 1200 LD
1.1 | Supply, lay, joint, bed and test HDPE lined concrete bulk sewer pipeline (class 100D) with spigot and socket joints (Sans 677)
(The rates shall include disinfecting of pipes after completion of hydraulic pipe test.)
1.1.2 | 1500mm nominal diam. With HDPE lining | m | 6
1.1.3 | Extra over for spectials |  | 6 |  | 0
Rocker pipes (1.22 m Length) for the following diameters:
1.1.4 | 1500mm nominal diam. With HDPE lining- spigot side only | No. | 1 |  | 0
1.1.5 | 1500mm nominal diam. With HDPE lining- socket side only | No. | 1 |  | 0
| 1500mm nominal diam. With HDPE lining- spigot and socket | No. | 1
| Encasing of pipes in concrete | m2 | 1
| Marker posts, complete, installed | No. | 1
1.2 | Supply, handle lay, joint, test and bed in bedding cradle uPVC normal duty sewer pipe (class 51) to SABS 791:1986
8.1.1 | 160mm diameter | m | 6
8.1.2 | 200mm diameter | m | 6
8.1.13 | 250mm diameter | m | 6
1.2 | Sewer Structures
1.2.2 | Manholes
Supply and install 1050 dia precast concrete manholes, complete with reducing slab and Type 2A cast iron manhole covers and frame for depth over and up to
1.2.2.1 | 1m up to 1,5m | No | 1
1.2.2.2 | 1,5 up to 2m | No | 1
1.2.2.3 | 2m up to 2.5m | No | 1
1.2.2.4 | Apron slab (Sides) | m2 | 1 |  | 0
| Box Out Holes |  |  |  | 0
1.2.2.5 | Large, other shapes over 0.1 m2 up to 0.5 m2 in area, depth over and up to | No. | 1 |  | 0
1.2.2.6 | uPVC bends with 11,5 degree angle. | No. | 1 |  | 0
1.2.2.7 | 0m 0,5 (0.6x 0,6m square Manhole frame in base) | No. | 1 |  | 0
1.3 | Reinforcement
1.3.1 | Mild steel bars | t | 1
1.3.2 | High- tensil steel bars | t | 1
1.4 | Concrete
1.4.1 | Mass concrete, Class 15/22 for manhole base | m3 | 1
1.4.2 | Unformed surface finished | m3 | 1
1.4.3 | Wook-floated | m3 | 1
1.4.4 | Apron slab | m3 | 1
1.4.5 | Precast elements | m3 | 1
1.5 | Pre-cast Elements
1.5.1 | Pre-cast concrete manhole rings (750mmdia.x 500mm) from dolomitic aggregate. | No. | 1
1.5.2 | Precast concrete Cover slab (750mm dia x150 mm with heavy duty lid (560mm dia.) from dolomitic agregate. | No. | 1
1.6 | Grouting
1.6.1 | HD Bolts ect. | No | 1
1.6.2 | Step Irons | No | 1
1.7 | Miscellaneous
1.7.1 | Apply approved epozy coat (500 microns) to soffit of pre cast conctrete slab and inside of 1800mm dia. Manhole rings | m2 | 1 |  | 0
1.7.2 | Apply bitument wrapping and water sealant paint to joints between concrete pre cast rings | m | 1 |  | 0
1.7.3 | Reinforced fibreglass grid (6000mmx600mm) | No. | 1 |  | 0
0
0
0
SUB-TOTAL SCHEDULE L - SECTION 5 CARRIED FORWARD: |  |  |  |  | 0

## LF - ERF CONNECTIONS(WATER)
0
SCHEDULE OF QUANTITIES:
0
SCHEDULE B: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 3: MEDIUM PRESSURE PIPELINES AND ANCILLARIES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
LF 1 | ERF CONNECTIONS:
(As specified in SABS 1200 L, SABS 1200 LF)
1.1 | Provide yard connections complete with meter.
1.1.1 | Metered Standpipe yard connection | No. | 1
a) | Double short | No. | 1
b) | Double long | No. | 1
c) | Single short | No. | 1
d) | Single long | No. | 1
1.1.2 | Sewer connection | No. | 1
1.1.3 | Short Erf sewer collector using UPVC solid wall class 34 | No. | 1
1.1.4 | Raising or lowering of existing Manholes 0-500mm | No | 1
TOTAL SCHEDULE B - SECTION 3 CARRIED TO SUMMARY: |  |  |  |  | 0

## GA Concrete (Small works)
0
SCHEDULE OF QUANTITIES:
0
SCHEDULE B: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: EARTHWORKS FOR PIPE TRENCHES
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
GA 1 | CONCRETE (SMALL WORKS)
(As specified in SABS 1200 GA and the Project Specifications.)
1.1 | SCHEDULED FORMWORK ITEMS
1.1.1 | Rough surface finish (vertical) | m² | 1
1.1.2 | Smooth surface finish (vertical) | m² | 1
1.2 | SCHEDULED REINFORCEMENT ITEMS
1.2.1 | a) Mild steel bars | kg | 1
1.2.2 | b) High-tensile steel bars | t | 1
| Type Ref. 311 in concrete surface beds, slabs, etc. | m² | 1
1.3 | SCHEDULED CONCRETE ITEMS
1.3.1 | Reinforced Strength concrete, 30MPa/19mm | m³ | 1
1.3.2 | Blinding layer in 20 Mpa conctere,with 100mm thickness | m³ | 1
1.3 | CONCRETE CAST AGAINST EXCAVATED SURFACES
15MPa/20mm. concrete
1.3.1
| Surface blinding under footings and bases | m³ | 1
1.3.2 | 25MPa/20mm. concrete
| Bases | m³ | 1
| Columns in foundations (Provisional) | m³ | 1
1.3.3 | TEST BLOCKS
Making and testing a set of three 150 x 150 x 150mm. concrete strength test cubes (Provisional)
|  | no | 1
3.3 | MASONRY
FACE BRICKWORK
Face brick pointed with recessed horizontal and vertical joints.
3.3.1 | One brick walls in English bond pointed both sides | m² | 1
Reinforcement to brickwork
3.3.2 | 150mm wide brick force built in horizontally | m | 1
WATERPROOFING
One layer of 375 micron "Gundle plastic Brikgrip DPC" embossed damp proof course
3.3.3 | In walls | m² | 1
TOTAL SCHEDULE GA - SECTION 3 CARRIED TO SUMMARY:

## H Struct steel tank
0
SCHEDULE OF QUANTITIES:
0
SCHEDULE H: BULK SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: ANCILLARY WATER SUPPLY WORKS
ITEM NUMBER | PAYMENT CLAUSE | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
H 1 |  | STRUCTURAL STEELWORK
(As specified in the Project Specifications.)
1.1 | PSH 8.3.1 | CONSTRUCTION OF SERVICE RESERVOIRS
(Steel Tank shall be a Braithwaite type, or similar,pressed steel. All manufacturing to SABS standards with hot dip galvaising to SANS 121(ISO 1461), installation to be performed by the supplier)
1.1.1 |  | 108KL Steel Tank on a 5m Stand | No. | 1
1.1.2 |  | Handling cost and profit in respect of above item | %
1.1.3 |  | Offloading from suppliers delivery vehicle the complete | No | 1
structure (± 14.44 tons)
1.1.4 |  | 160kl steel tank on a 5m stand | No | 1
1.1.5 |  | Handling cost and profit in respect of above item | %
1.1.6 |  | 260kl steel tank on a 10m stand | No. | 1
1.1.7 |  | Handling cost and profit in respect of above item | %
1.1.8 |  | Supply 150g of Calcium Hyperchloride per m³ of water | kg | 120
for sterilising the elevated tank
1.2 |  | SCOUR
1.2.1 |  | 80mm ø GMS Flange threaded inside | No. | 1
1.2.3 |  | 80mm ø GMS Barrel nipple, 100mm long, | No. | 1
threaded both sides
1.2.6 |  | 80mm ø GMS Barrel nipple, 100mm long, | No. | 1
threaded one side
1.2.9 |  | 80mm ø Brass fullway gate valve | No. | 1
1.3 |  | OVERFLOW
1.3.1 |  | 100mm ø GMS pipe, 100mm long, flanged one end | No. | 1
1.4 |  | ELEVATED TANK INLET VALVE CHAMBER,
(Drilled SABS 1123, Table 1000/3):
1.4.1 |  | 110mm ø FBE steel pipe with puddle flange | No. | 1
1.4.2 |  | 110 x 80mm ø Flanged T-piece | No. | 1
1.4.3 |  | 110mm ø Flanged AVK gate valve | No. | 1
1.4.4 |  | 110mm ø Bermad strainer | No. | 1
1.4.5 |  | 110mm ø FOE steel pipe section with Aqualok | No. | 1
1.4.6 |  | adaptor
1.4.7 |  | 110mm ø Meinecke Cosmos water meter | No. | 1
1.4.8 |  | 110mm ø FBE steel pipe section | No. | 1
1.4.9 |  | 110mm ø Bermad 750/66 float control valve | No. | 1
1.4.10 |  | 110mm ø FBE steel pipe with puddle flange | No. | 1
1.4.11 |  | 80mm ø Flanged AVK gate valve | No. | 1
1.4.12 |  | 80RBX1601 Vent-O-Mat air release valve | No. | 1
TOTAL SCHEDULE H - SECTION 7 CARRIED TO SUMMARY:

## PME-ANCILLARY WORKS
0
SCHEDULE OF QUANTITIES:
0
SCHEDULE PME: WATER SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: ANCILLARY WATER SUPPLY WORKS
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
PME | ANCILLARY WORKS:
WATER TREATMENT PLANT
1.1 | Supply and Install and delivery of a complete water treatment plant by specialized subcontractor with all fittings and pipe work.67 kl per hour output. Training of Polokwane Emplyees to be inculded. | No | 1
1.2 | Supply, Installation and connection of 3 phase 25KVA trans toformer in accordance with Eskom requirements (±1 km) | No | 1
1.3 | Supply, Installation and connection of 3 phase 25 KVA transformere in accordance with Eskom requirements (±2 km) | No | 1
1.4 | Supply and Install 50KVA 22000/415 transformer (1km) | No | 1
TOTAL SCHEDULE PME - SECTION 10 CARRIED TO SUMMARY: |  |  |  |  | 0

## VC- PUMPS
SCHEDULE OF QUANTITIES:
SCHEDULE VC: WATER SUPPLY AND NETWORK DISTRIBUTION WORKS
SECTION 1: PUMPS
ITEM NUMBER | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
VC | PUMPS
(As specified in the Project Specifications.)
1.1 | Supply and Delivery of Pumps
1.1.2 | Supply, delivery, installation, commisioning and maintanance (during defect liability period) of a eqquipping of boreholes complete with Mono Pump with all accesories including pipework, motor, electrical cabling and control panels Monomeester BP 40L (min 11 KW motor or equivelent), for a borehole | No | 1
1.1.2 | Compile, Supply and delivery of a complete set of operation and maintenance manuals of a pumps as specified and measured in PMB-10.4 | No. | 1
1.1.3 | Testing of pumps
| (a) Complete workshop testing a specified, for each pump-set as scheduled in item 1.1.2 | No | 1
1.1.4 | Contractors handling costs, profits and all other charges in respect of item 1,1 | %
1.2 | PUMP HOUSING
1.2.1 | Supply, deliver and erect pre-cast pump house (3mx3m) complete with lockable device as per | No | 1
1.3 | FENCING
1.3.1 | Supply, deliver and erect clear-vu fence 1,8 m high including 10m sliding gate | m | 150
TOTAL SCHEDULE VC - SECTION 9 CARRIED TO SUMMARY:

## PMU COVER (hidden)
POLOKWANE LOCAL MUNICIPALITY
PROJECT MANAGEMENT UNIT
CONTRACT NR: |  |  |  | Date of issue | 2024-05-10
ENGINEERS BUDGET | 0
CONTRACTOR BUDGET | 0
TOTAL PROJECT COST | 0
Consultant Name: | XXXXXXXXX
A. Professional fees
Description |  |  | Approved budget | Cummulative | Previous | Current
1. PROFESSIONAL FEES |  |  | 0 |  | 0 | 0
2. SPECIALIST SERVICES SUM
2.1 Topographical Survey |  |  | 0 | 0 |  | 0
2.2 EIA |  |  | 0 | 0 |  | 0
2.3 Geotech |  |  | 0 | 0 | 0 | 0
2.4 OHS |  |  |  | 0 | 0 | 0
3 HEAD OFFICE TRAVEL |  |  | 0 | 0 | 0 | 0
4. SITE STAFF COSTS |  |  | 0 | 0 | 0 | 0
5. DOCUMENTS/PRINTING |  |  | 0 | 0 | 0 | 0
6. TIME BASIS |  |  | 0 | 0 | 0 | 0
Subtotal A |  |  | 0 | 0 | 0 | 0
15% VAT |  |  | 0 | 0 | 0 | 0
Total incl VAT |  |  | 0 | 0 | 0 | 0
Less amount previously paid |  |  | 0
Total due |  |  |  | 0
B. Contractors Fees |  |  |  | CERTIFICATE: | 2
Contract amount
Bill of Quantities |  |  | BUDGET | Cummulative | Previous | Current
Bill 1: Preliminary and General |  |  |  |  | 0
Bill 2: Site Clearance |  |  |  |  | 0
Bill 3: Earthworks |  |  |  |  | 0 | 0
Bill 4: Excavation for Pipeline Trenches |  |  |  | 0 | 0 | 0
Bill 5.Bedding for water Pipes |  |  |  | 0 | 0 | 0
Bill 6. Medium Pressure Pipes |  |  |  | 0 | 0 | 0
Bill 7. Borehole Pumps and Appurtenances |  |  |  | 0 | 0 | 0
Bill 8. Reinforced Concrete Structures |  |  |  | 0 | 0 | 0
Bill 9. Elevated Steel Tanks |  |  |  | 0 | 0 | 0
Bill 10. Electrification on Water Infrastructures |  |  |  | 0 | 0 | 0
Sub Total 1 |  |  | 0 | 0 | 0 | 0
Add 10% Contingencies |  |  | 0
Less 10% Retention |  |  |  | 0
Sub Total 2 |  |  | 0 | 0
Add Materials on site 80%
Sub Total 3 |  |  | 0 | 0
Add 6.5% CPA
ESCALATION(2%) |  |  | 0
Sub Total 4 |  |  | 0 | 0
Add VAT (15%) |  |  | 0 | 0
Total Incl. VAT |  |  | 0 | 0
Total amount now payable |  |  |  | 0
|  |  | BUDGET | CUMMULATIVE | PAID | DUE
NAME: XXXXXXXXX |  | NAME: Elliot Letlalo |  |  | NAME: Ms MD Shai
COMPANY NAME |  | PROJECT MANAGER |  |  | ACTING MANAGER:WATER AND SANITATION
SIGNATURE |  | SIGNATURE |  |  | SIGNATURE